## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Maintenance of kevote market road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of kevote market road |  | Kevote |  | Road | Road | Road | 2023-01-07 | 30/12/2023 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1999608 | N/A | N/A | Ongoing | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Classic Kanginga | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Classic Kanginga |  | kanginga |  | Road | Road | Road | 2023-01-07 | 30/12/2023 | 30/6/2024 | 30/6/2024 | 3700000 | 3700000 | 3700000 | County Treasury | N/A | 3700000 | N.A | 3700000 | 100% | 3623794 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ndumari Nguruka | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ndumari Nguruka |  | Ndumari |  | Road | Road | Road | 2023-01-07 | 30/12/2023 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4997454 | N/A | N/A | Ongoing | 100% | N/A | N/A | N/A | N/A | N/A
| 1. Upgrading To Bitumen Standards Of Exit Road From First Bus Park (Embu Runyenjes Bus Park) To Mama Ngina Street | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | 1. Upgrading To Bitumen Standards Of Exit Road From First Bus Park (Embu Runyenjes Bus Park) To Mama Ngina Street |  | Embu |  | Road | Road | Road | 2023-01-07 | 18/12/2023 | 30/6/2024 | 30/6/2024 | 25000000 | 25000000 | 25000000 | County Treasury | N/A | 25000000 | N.A | 25000000 | 100% | 22816910 | N/A | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A
| Rehabillitation of Kinyago (Kagunga) Dumpsite | Site assessment, vent installation, vegetative cover and landscaping | To mitigate the environmental and public health impacts caused by open dumpsite | To proper closure and rehabilitation of the dumpsite in accordance with environmental regulations | Road | Rehabillitation of Kinyago (Kagunga) Dumpsite |  | Kagunga |  | Road | Road | Road | 2023-01-07 | 2024-04-01 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4994264 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1 Grading And Gravelling Of Roads1. Rwika 2.5 – Rianjeru Road 2. Rwika Market Roads | Site clearing, grading, compaction and gravel placemnt | To improve road accessibility and connectivity between communites | An improved all-well gravel road suitable for daily trasportation | Road | 1 Grading And Gravelling Of Roads1. Rwika 2.5 – Rianjeru Road 2. Rwika Market Roads |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3995852 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening/ Grading Muramming And Surveying Of Rukira Market Access Roads | Surveying, road opening, grading and shaping | To provide access and connecivity between communities and main roads | An established and properly surveyed access road alignment | Road | Opening/ Grading Muramming And Surveying Of Rukira Market Access Roads |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2996152 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nthamari Nguire Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nthamari Nguire Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1498778 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening, Dozing And Maintenance Of Roads In Evurore Ward | Road construction and opening and road maintenance | To improve accessibility, transportation efficiency, and socio-economic developments | Reduced travel time and vehicle operating costs | Road | Opening, Dozing And Maintenance Of Roads In Evurore Ward |  | Evuvori |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3995226 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts And Gabions | Excavation, culvert laying and alignment | To ensure proper darinage and prevent water accumulation on road ways | Improved drainage efficiency and reduced risk of flooding | Road | Installation Of Culverts And Gabions |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2996512 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading/ Maintenance Of Roads (Muminji Ward) | Road clearing and cleaning and debris removal | To improve the smoothness, safety, and accessibility of existing roads | Restored and well-shaped road surfaces with improved drainage | Road | Grading/ Maintenance Of Roads (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3800000 | 3800000 | 3800000 | County Treasury | N/A | 3800000 | N.A | 3800000 | 100% | 3772320 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kivwe – Cavari And Kivwe Base Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kivwe – Cavari And Kivwe Base Roads |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1494892 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mukono - Kambaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mukono - Kambaru Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997556 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiumu Leaders Road, Maintenance Of Jane Kiande Loop Road, | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiumu Leaders Road, Maintenance Of Jane Kiande Loop Road, |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997950 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mathai – Mururiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mathai – Mururiri Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4996851 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads In Gaturi South | Route survey, clearing, excavation and construction | To open and establish new road alignments according to approved plans and standards | A fully opened and accessible road corridor ready for future improvement | Road | Opening Of Roads In Gaturi South |  | Gaturi |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4496392 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Kwa Kamwe - Kaseveni Road | Site preparation, grading and murraming | To grade and shape the road surface to the correct alignment and level | Well-shaped and compacted murram road suitable for all-weather use | Road | Grading And Murraming Of Kwa Kamwe - Kaseveni Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1497908 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance Of Kamiu Ksg Road 2.Maintenance Of Kiambuthi Loop Road, 3.Maintenance Of Kamiu Blue Valley Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance Of Kamiu Ksg Road 2.Maintenance Of Kiambuthi Loop Road, 3.Maintenance Of Kamiu Blue Valley Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4494026 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Kivumburi Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Kivumburi Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1497792 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Murraming Of Roads (Karaba – Gitaraka And Malikini – Kilia Roads) , 2. Grading Of Roads (Karaba – Gitaraka And Malikini – Kilia Roads | Site preparation, grading works, murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved and well-graded murram road | Road | 1. Murraming Of Roads (Karaba – Gitaraka And Malikini – Kilia Roads) , 2. Grading Of Roads (Karaba – Gitaraka And Malikini – Kilia Roads |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4995737 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Opening And Maintenance Of Mbita – Minuri – Kamaina Road, 2. Opening And Maintenance Of Kaweru – Munyori - Kamwimbi Road | Road opening, grading and shaping, drainage works and murraming | To open up an access road for road for improved connectivity and mobility | A fully opened and maintained road section of in good condition | Road | 1. Opening And Maintenance Of Mbita – Minuri – Kamaina Road, 2. Opening And Maintenance Of Kaweru – Munyori - Kamwimbi Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4983824 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Gravelling Of Muua – Karangiri – Karitiri Road 2.Grading And Gravelling Of Gatumbari Tbc Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Gravelling Of Muua – Karangiri – Karitiri Road 2.Grading And Gravelling Of Gatumbari Tbc Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998268 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening Of Kithunguthia Road |  |  |  | Road | Opening Of Kithunguthia Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 995373 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1.Grading And Gravelling Of Airstrip Road, 2. Grading And Gravelling Of Rupingazi Don Bosco Road 3.Grading And Gravelling Of Magecha – Catholic Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1.Grading And Gravelling Of Airstrip Road, 2. Grading And Gravelling Of Rupingazi Don Bosco Road 3.Grading And Gravelling Of Magecha – Catholic Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4495348 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1.Grading And Gravelling Of Kasarani Kirurumwe Road 2. Grading And Gravelling Ruvutiri Tea Buying Centre Road 3. Grading And Gravelling Of Mathiga Kamugere Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1.Grading And Gravelling Of Kasarani Kirurumwe Road 2. Grading And Gravelling Ruvutiri Tea Buying Centre Road 3. Grading And Gravelling Of Mathiga Kamugere Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2995700 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Gravelling Of Gichugu Primary Kavingazi, 2.Grading And Gravelling Of Itonguri Tbc Kirigi Ikunguru Road 3.Grading And Gravelling Of Gituri Kirangiri Kianjuki | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Gravelling Of Gichugu Primary Kavingazi, 2.Grading And Gravelling Of Itonguri Tbc Kirigi Ikunguru Road 3.Grading And Gravelling Of Gituri Kirangiri Kianjuki |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4497575 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Kianjokoma Gichagi Roads 2. Grading And Gravelling Of Kavari Kavutiri 3. Grading And Gravelling Of Kavutiri Market Gichagi Roads 4. Grading And Gravelling Of Kianyagi Gaikiro | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Kianjokoma Gichagi Roads 2. Grading And Gravelling Of Kavari Kavutiri 3. Grading And Gravelling Of Kavutiri Market Gichagi Roads 4. Grading And Gravelling Of Kianyagi Gaikiro |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4995354 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rwika Market – Kaninwanthiga Road | Re-grading, drainage maintenance and erosion contrl | To restore the road to safe and motorable condition | A well-maintained and accessible road | Road | Maintenance Of Rwika Market – Kaninwanthiga Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998332 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Kwa Meeten - Nthumo Road | Site preparation, grading works, murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved and well-graded murram road | Road | Grading And Murraming Of Kwa Meeten - Nthumo Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 15/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1487700 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndune Shrine Access Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ndune Shrine Access Roads |  | Embu |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4997048 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Mufu Social Hall - Karundiri Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Mufu Social Hall - Karundiri Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1300000 | 1300000 | 1300000 | County Treasury | N/A | 1300000 | N.A | 1300000 | 100% | 1299664 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatothia – Ngiiri Road ( Muminji Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatothia – Ngiiri Road ( Muminji Ward) |  | Muminji |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998854 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Roads-Repair of Ciakarundu Drift, Repair of Kiringa – Kivwe Drift, Repair of Karimari Itiira Drift, Repair of Mbarwari Kandomba Road | Grading and reshaping, cleaning, removal of debris and | To restore the damage drift and ensure safe passage across water crossing | A well-maintained road and repaired and functioning drift structure | Road | Maintenance of Roads-Repair of Ciakarundu Drift, Repair of Kiringa – Kivwe Drift, Repair of Karimari Itiira Drift, Repair of Mbarwari Kandomba Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 3000000 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Kithinji Kiragu and Ewasco Road (Ruguru Ngandori Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kithinji Kiragu and Ewasco Road (Ruguru Ngandori Ward) |  | Ruguru ngandori |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1996662 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Spot Murraming Of Kathiani – Misandukuni Junction Road- Makima Ward | Site preparation, spot murraming and drainage maintenance | To improve the condition and usability of the road through spot interventions | Improved and passable road sections along road | Road | Spot Murraming Of Kathiani – Misandukuni Junction Road- Makima Ward |  | Makima |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1997288 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Widening, Grading and Gravelling of Roads in Nginda Ward | Site clearance and preparation, road widening, grading and gravelling | To widen and improve the road to accommodate increased traffic flow | A widened, graded and well-gravelled road section in good condition | Road | Widening, Grading and Gravelling of Roads in Nginda Ward |  | Nginda |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4200000 | 4200000 | 4200000 | County Treasury | N/A | 4200000 | N.A | 4200000 | 100% | 4014667 | N/A | N/A | Ongoing | 96% | N/A | N/A | N/A | N/A | N/A
| Maintenance and Grading of Roads, Opening of Roads (Mavuria Ward) | Cleaning, filling, opening road and grading works | To maintain and open new road links to improve connectivity between communities | A fully opened, graded, and well-maintained road network | Road | Maintenance and Grading of Roads, Opening of Roads (Mavuria Ward) |  | Mavuria |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4999327 | N/A | N/A | Ongoing | 99% | N/A |  | N/A | N/A | N/A
| Opening, Grading and Gravelling of Nyaga Njara Road (Kithimu Ward) | Road opening, grading works and gravelling | To open and construct a new roasd section to improve connectivity and accessibility | A newly opened, graded, and gravelling road road in good condition | Road | Opening, Grading and Gravelling of Nyaga Njara Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N.A | 2500000 | 100% | 2420201 | N/A | N/A | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A
| Grading of Kerangi Primary School and Mabati Juu – Mutindwa Primary School Road (Kiambere Ward) | Site preparation, grading works and drainage improvement | To improve the surface condition and ride quality of the road | A well-graded and smooth road surface | Road | Grading of Kerangi Primary School and Mabati Juu – Mutindwa Primary School Road (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1900000 | 1900000 | 1900000 | County Treasury | N/A | 1900000 | N.A | 1900000 | 100% | 1898015 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts Kagaari South | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A properly installed and functional culvert | Road | Installation of Culverts Kagaari South |  | Kagaari |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1300000 | 1300000 | 1300000 | County Treasury | N/A | 1300000 | N.A | 1300000 | 100% | 1297692 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Nthumburi Road (Kyeni North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Nthumburi Road (Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1800000 | 1800000 | 1800000 | County Treasury | N/A | 1800000 | N.A | 1800000 | 100% | 1799076 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading of Roads Kagaari South, Murraming of Roads Kagaari South | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading of Roads Kagaari South, Murraming of Roads Kagaari South |  | Kagaari south |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3996896 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Bush Clearing, Heavy Grading and Gravelling – Kyeni South | Site assssment, reshaping, drainage works | To open and rehabilitate the road for improved all-weather accessibility | A fully cleared, graded, and gravelled road section | Road | Bush Clearing, Heavy Grading and Gravelling – Kyeni South |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3999657 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Ndiuri Road, Grading and Gravelling of Theruri Road,Grading and Gravelling of Gicago Road (Ruguru Ngandori Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Ndiuri Road, Grading and Gravelling of Theruri Road,Grading and Gravelling of Gicago Road (Ruguru Ngandori Ward) |  | Ruguru ngandori |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N.A | 5000000 | 100% | 4975553 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Gravelling of Roads in Kyeni South | Site clearing, grading, compaction and gravel placemnt | To improve the accessibility and usability of local roads in all weather conditions | Improved road surface and year-round accessility | Road | Gravelling of Roads in Kyeni South |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2999412 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening of Ngambari – King’ee Junction Road (Kiambere Ward) | Site survey, clearing and construction | To open and establish new road alignments according to approved plans and standards | Newly opened roads providing access to previously unreachable areas | Road | Opening of Ngambari – King’ee Junction Road (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1100000 | 1100000 | 1100000 | County Treasury | N/A | 1100000 | N.A | 1100000 | 100% | 1097267 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading, Gravelling and Installation of Culverts Of Iriari – Kithare Road (Kyeni North Ward | Site clearing and preparation, grading, gravelling and installation of culverts | To improve the condition and accessibility of rural and feeder roads | Improved and more durable road surface suitable for all-weather use | Road | Grading, Gravelling and Installation of Culverts Of Iriari – Kithare Road (Kyeni North Ward |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2999830 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Kathari Gaturi Ithigira Road, Grading And Gravelling of Kiaganari Road,Grading and Gravelling of Kathari Catholic Road ( Kyeni North) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kathari Gaturi Ithigira Road, Grading And Gravelling of Kiaganari Road,Grading and Gravelling of Kathari Catholic Road ( Kyeni North) |  | Embu |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 3700000 | 3700000 | 3700000 | County Treasury | N/A | 3700000 | N.A | 3700000 | 100% | 3698850 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening, Widening, Grading and Gravelling of Various Roads – Kyeni South | Site clearing, grading, gravelling and widening | To widen existing roads to omprove traffic flow and enhance safety | A well-widened road fully functional | Road | Opening, Widening, Grading and Gravelling of Various Roads – Kyeni South |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4100000 | 4100000 | 4100000 | County Treasury | N/A | 4100000 | N.A | 4100000 | 100% | 4099811 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Murari - Kivoi Road- Kyeni South Ward | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Murari - Kivoi Road- Kyeni South Ward |  |  |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3999448 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening of Roads in Kagaari South | Site survey, clearing and construction | To open and establish new road alignments according to approved plans and standards | Newly opened roads providing access to previously unreachable areas | Road | Opening of Roads in Kagaari South |  | Kagaari South |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3995968 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Gatururi (Ngimari) Road, Grading And Gravelling of Ngumbuko Gaciigi Road (Ruguru Ngandori Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Gatururi (Ngimari) Road, Grading And Gravelling of Ngumbuko Gaciigi Road (Ruguru Ngandori Ward) |  | Ngandori ward |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1920867 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Father Peter Gaciigi Road-(Ruguru Ngandori Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Father Peter Gaciigi Road-(Ruguru Ngandori Ward) |  | Ngandori ward |  | Road | Road | Road | 2023-01-07 | 21/02/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1496261 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Kathugu –Catholic Road (Kagaari South Ward | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kathugu –Catholic Road (Kagaari South Ward |  | Kagaari south |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1995548 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of roads in Gaturi South ward | Site preparation, grading works, murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved and well-graded murram road | Road | Grading and Murraming of roads in Gaturi South ward |  | Gaturi South |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4496740 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of culverts in Gaturi South | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A properly installed and functional culvert | Road | Installation of culverts in Gaturi South |  | Gaturi South |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 999920 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kwa Mathuvi To River Thiba –Mashamba secondary school road | Surveying, road opening, grading and shaping | To open new road corridors to improve connectivity between communities | Newly opened roads providing access to previously unreachable areas | Road | Opening and Grading of Kwa Mathuvi To River Thiba –Mashamba secondary school road |  | Embu |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1499944 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Nembure Road- Gaturi South | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Nembure Road- Gaturi South |  | Gaturi South |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1995432 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts in Mbeti North | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A properly installed and functional culvert | Road | Installation of Culverts in Mbeti North |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1497560 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Hire of Dozer –Mwea Ward | Mobilization. Negotiation, hiring | To provide mechanical support for road opening, grading, and general earthworks | Efficient completion of earthworks and road formation activities | Road | Hire of Dozer –Mwea Ward |  | Mwea |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3994460 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1.) Grading & Gravelling of Gacengi Muchagori Road 2.) Grading & Gravelling –Kianjokoma Kathimba Road – Gaturi North Ward | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1.) Grading & Gravelling of Gacengi Muchagori Road 2.) Grading & Gravelling –Kianjokoma Kathimba Road – Gaturi North Ward |  | Gaturi North |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | N.A | 3500000 | 100% | 3495544 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamugere, Muchagori, Kiangungi Muva Road-Gaturi North Ward | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Kamugere, Muchagori, Kiangungi Muva Road-Gaturi North Ward |  | Gaturi North |  | Road | Road | Road | 2023-01-07 | 14/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997138 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gaciigi Keria | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Gaciigi Keria |  | Embu |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997092 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kageri – Kabachi - Michegethio Road | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kageri – Kabachi - Michegethio Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997846 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangariri Muvandori Road (Ngindaward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathangariri Muvandori Road (Ngindaward) |  | Nginda |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997846 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Newsite – Ndithiri – Njigi Road (Kiambere Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Newsite – Ndithiri – Njigi Road (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2914175 | N/A | N/A | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A
| Construction Of Upper Ngarira Drift (Mavuria Ward |  |  |  | Road | Construction Of Upper Ngarira Drift (Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2998020 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Old Stadium And Majengo Access Roads (Kirimari Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Old Stadium And Majengo Access Roads (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998100 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Slaughter Kivumbu Kiangungi Road (Kyeni North Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Slaughter Kivumbu Kiangungi Road (Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997672 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Managia Salvation Army Kavuru Road (Kagaari South Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Managia Salvation Army Kavuru Road (Kagaari South Ward) |  | Kagaari south |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997556 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbui Njeru Gaikama Mairori Road (Kagaari North Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbui Njeru Gaikama Mairori Road (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2998557 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Dubai Micakaranda Road (Gaturi South Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Dubai Micakaranda Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2999180 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kcc Kang’ethire Road (Runyenjes Central Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kcc Kang’ethire Road (Runyenjes Central Ward) |  | Runyenjes Central |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997440 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathunguri Karurumo Road (Kyeni South Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathunguri Karurumo Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2999602 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Macarelo – Rianjeru Father Kirimi Road (Mbeti North Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Macarelo – Rianjeru Father Kirimi Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2996222 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Snake Road (Evurore Ward | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Snake Road (Evurore Ward |  | Evuvori |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2998020 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Iria Itune – Kikumini – Gitaraka Road (Mwea Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Iria Itune – Kikumini – Gitaraka Road (Mwea Ward) |  | Mwea |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2991292 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithimu Kimangaru Road (Kithimu Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kithimu Kimangaru Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2937828 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Proposed Repair Of Kiogora Drift (Muminji Ward) |  |  |  | Road | Proposed Repair Of Kiogora Drift (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997881 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muraru - Mbita Road (Mbeti South Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Muraru - Mbita Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2999528 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Munyaka Road (Mavuria Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Munyaka Road (Mavuria Ward) |  | Mavuria |  | Road | Road | Road | 2023-01-07 | 22/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2983590 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening, Dozing and Grading of Roads-(Nginda Ward) | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening, Dozing and Grading of Roads-(Nginda Ward) |  | Nginda |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2971154 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Roads in Kirimari | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Roads in Kirimari |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3996664 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening of Roads in Kirimari Ward amounting | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Roads in Kirimari Ward amounting |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3996316 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Roads- (Nginda Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Roads- (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3997824 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Roads in Kirimari | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Roads in Kirimari |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 3800000 | 3800000 | 3800000 | County Treasury | N/A | 3800000 | N.A | 3800000 | 100% | 3799592 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening of Roads in Kirimari Ward amounting | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Roads in Kirimari Ward amounting |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N.A | 2500000 | 100% | 2498988 | N/A | N/A | Ongoing | 99% | N/A | N/A |  | N/A | N/A
| Grading And Gravelling Of Roads- (Nginda Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Roads- (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2023-01-07 | 27/03/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1498198 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Construction Of Drift In Evurori- Evurore Ward | Site preparation, drilling, construction | To construct a stable, safe, and properly supported drift of specified dimensions | A fully excavated and supported drift | Road | Construction Of Drift In Evurori- Evurore Ward |  | Evuvori |  | Road | Road | Road | 2023-01-07 | 2024-02-04 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2996744 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Construction of Kiritiri Drift- Mavuria Ward | Site preparation, drilling, construction | To construct a stable, safe, and properly supported drift of specified dimensions | A fully excavated and supported drift | Road | Construction of Kiritiri Drift- Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4497610 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening of Mariari SDA – Gicigori-Ciamiatu-Kirimu Ntharawe Road – (Kiambere Ward) | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Mariari SDA – Gicigori-Ciamiatu-Kirimu Ntharawe Road – (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3191600 | 3191600 | 3191600 | County Treasury | N/A | 3191600 | N.A | 3191600 | 100% | 3119994 | N/A | N/A | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A
| Drainage In The Miraa Market (Kirimari Ward) | Site survey, excavation, construction | To construct a suitable and efficient drainage network | Completed drainage channels with access covers and manholes | Road | Drainage In The Miraa Market (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2499094 | 2499094 | 2499094 | County Treasury | N/A | 2499094 | N.A | 2499094 | 100% | 2497364 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A |  | N/A
| Grading and Gravelling of Kathangariri-Catholic-Mucangi-Chege Njeru Metumi Road – (Nginda Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kathangariri-Catholic-Mucangi-Chege Njeru Metumi Road – (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1933964 | N/A | N/A | Ongoing | 96% | N/A | N/A | N/A | N/A
| Grading and Murraming of Kathundiri-Karue and Makengi Nguiri-(Gaturi North Ward) | Clearing, excavation, grading and murraming | To ensure smooth and safe riding | A fully functional road suitable for all-weather seasons | Road | Grading and Murraming of Kathundiri-Karue and Makengi Nguiri-(Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1441114.96 | N/A | N/A | Ongoing | 96% | N/A | N/A | N/A | N/A | N/A
| Construction of Drifts and Culverts of Kiangeni- Musingini- Makima – ( Makima Ward) | Site preparation, drilling, construction | To construct a stable, safe, and properly supported drift and culverts of specified dimensions | A fully excavated and supported drift and culcerts | Road | Construction of Drifts and Culverts of Kiangeni- Musingini- Makima – ( Makima Ward) |  | Makima |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 999920 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kambiti Kwa Kimuyu Misandukuni Junction Road | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Kambiti Kwa Kimuyu Misandukuni Junction Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2300000 | 2300000 | 2300000 | County Treasury | N/A | 2300000 | N.A | 2300000 | 100% | 2298076 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading of Roads – (Nthawa Ward) | Site preparation, grading | To regrade and smoothen existing road surface for improved riding quality | Regraded and compacted road surface | Road | Grading of Roads – (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 800000 | 800000 | 800000 | County Treasury | N/A | 800000 | N.A | 800000 | 100% | 798556 | N/A | N/A | Ongoing | 99% | N/A |  | N/A | N/A | N/A
| Maintenance of Njukiri Scheme Road-(Kirimari Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Njukiri Scheme Road-(Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3800000 | 3800000 | 3800000 | County Treasury | N/A | 3800000 | N.A | 3800000 | 100% | 3797840 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Gwa Kihanya Road – (Mbeti North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Gwa Kihanya Road – (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3995620 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1.Maintenance of Kiaragana – Kaveti Road 2. Grading and Murraming of Line Saba Kiaragana Road-(Kyeni North Ward) | Site survey, cleaning, grading and murraming | To maintain the condition of the road and better it for trasnportation | A well-maindained and murrammed road | Road | 1.Maintenance of Kiaragana – Kaveti Road 2. Grading and Murraming of Line Saba Kiaragana Road-(Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 900000 | 900000 | 900000 | County Treasury | N/A | 900000 | N.A | 900000 | 100% | 898420 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading, Dozing and Maintenance Of Roads Makima ( Makima Ward) | Site inspection, clearing, dozing and reshaping | To regrade and level existing roads for improved surface smoothness and drainage | Regraded and compacted road surface | Road | Grading, Dozing and Maintenance Of Roads Makima ( Makima Ward) |  | Makima |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1498778 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Kamiu –Murandi (Mbeti North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kamiu –Murandi (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1700000 | 1700000 | 1700000 | County Treasury | N/A | 1700000 | N.A | 1700000 | 100% | 1699806 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Gabions and Culverts (Nthawa Ward) | Site clearing, excavation, installation and construction | To ensure safe passage of stormwater under road embankments and access routes | Completed erosion and improved drainage efficiency | Road | Installation of Gabions and Culverts (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N.A | 2500000 | 100% | 2497480 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening , Grading and Gabions Kwa Alphonce-Wambua Ngoma- Kwa Kaitio Road ( Makima Ward) | Surveying, road opening, grading and shaping | To enhance transportation efficiency, safety, and environmental protection | Site restored and fully operational for vehicle acccess | Road | Opening , Grading and Gabions Kwa Alphonce-Wambua Ngoma- Kwa Kaitio Road ( Makima Ward) |  | Makima |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 997832 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Grading, Opening and Murraming of Kiandongo and Mutinori Roads 2. Murraming of Mung’aru- Maciara Road ( Kagaari North Ward | Site survey, clearing and opening, grading and murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | 1. Grading, Opening and Murraming of Kiandongo and Mutinori Roads 2. Murraming of Mung’aru- Maciara Road ( Kagaari North Ward |  | Kagaari North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997788 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading of Kanja Town Roads ( Kagaari North Ward) | Site preparation, grading | To regrade and smoothen existing road surface for improved riding quality | Regraded and compacted road surface | Road | Grading of Kanja Town Roads ( Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2998113 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening, Grading and Murraming and Installation of Culverts Of Kathiruri – Kamagambo (Kagaari North Ward) | Site survey, clearing and opening, grading and murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | Opening, Grading and Murraming and Installation of Culverts Of Kathiruri – Kamagambo (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N.A | 1500000 | 100% | 1496284 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Muchagori -Makengi Road (Gaturi North Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Muchagori -Makengi Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 800000 | 800000 | 800000 | County Treasury | N/A | 800000 | N.A | 800000 | 100% | 798080 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Murraming of Roads (Mwea Ward) | Site preparation, spreading, moisturing and compaction | To provide durable surface layer on existing road formation | Improved road durability and riding comfort | Road | Murraming of Roads (Mwea Ward) |  | Mwea |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3996200 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Njumbiri- Kariari – Karurina Road ( Mbeti North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Njumbiri- Kariari – Karurina Road ( Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | N.A | 3500000 | 100% | 3499256 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Roads Ishiara/ Ndurumori/Kiang’ombe/ Kanyuombora Areas 2. Rock Blasting of – (Kamumu Rwanjeru Road)- (Evurori Ward) | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Roads Ishiara/ Ndurumori/Kiang’ombe/ Kanyuombora Areas 2. Rock Blasting of – (Kamumu Rwanjeru Road)- (Evurori Ward) |  | Evuvori |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | N.A | 3500000 | 100% | 3498560 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Grading and Murraming of Kiregi Ngorweri Road 2. Grading and Murraming of Eapc-Kiangungi-Gatumbi Market Road-(Kyeni North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading and Murraming of Kiregi Ngorweri Road 2. Grading and Murraming of Eapc-Kiangungi-Gatumbi Market Road-(Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N.A | 2500000 | 100% | 2498500 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A
| 1.Grading, Gravelling of Kimangaru Gikingiri Roads 2. Grading Gravelling of Air Strip Gate Road-(Mbeti North Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1.Grading, Gravelling of Kimangaru Gikingiri Roads 2. Grading Gravelling of Air Strip Gate Road-(Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 2900000 | 2900000 | 2900000 | County Treasury | N/A | 2900000 | N.A | 2900000 | 100% | 2896810 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Gacogori Road and Kathuraku Road-(Kagaari North Ward) | Site survey, clearing and opening, grading | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | Opening and Grading of Gacogori Road and Kathuraku Road-(Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2023-01-07 | 22/04/2024 | 30/6/2024 | 30/6/2024 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N.A | 4000000 | 100% | 3995736 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gituuri – Kwa Mark Road | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gituuri – Kwa Mark Road |  | Gituuri |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 2300000 | 2300000 | 2300000 | County Treasury | N/A | 2300000 | N.A | 2300000 | 100% | 2299004 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Construction of a Foot Bridge at Mang’ote Ena River- Evurore Ward | Site survey and preparation, construction | To provide a safe and reliable pedestrian crossing point | Safe and reliable pedestrian crossing for community members | Road | Construction of a Foot Bridge at Mang’ote Ena River- Evurore Ward |  | Evuvori |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998680 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kivoo Kigumo Road- Kyeni South Ward | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Kivoo Kigumo Road- Kyeni South Ward |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 4010000 | 4010000 | 4010000 | County Treasury | N/A | 4010000 | N.A | 4010000 | 100% | 4009308 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Opening, Grading and Murraming of Itenge Tenge Road- Kithimu Ward) | Site survey, clearing and opening, grading and murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | Opening, Grading and Murraming of Itenge Tenge Road- Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998518 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance of Karurumo Kariru Road 2. Maintenance of Kigumo Gititi Kanginga Road- Kyeni South Ward | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | 1. Maintenance of Karurumo Kariru Road 2. Maintenance of Kigumo Gititi Kanginga Road- Kyeni South Ward |  | Kyeni South |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 4010000 | 4010000 | 4010000 | County Treasury | N/A | 4010000 | N.A | 4010000 | 100% | 4009308 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Gatumbi Junction- Wakanye Road- Kyeni North Ward | Site survey, clearing and opening, grading and murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | Grading and Murraming of Gatumbi Junction- Wakanye Road- Kyeni North Ward |  | Kyeni North |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N.A | 2000000 | 100% | 1998518 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts – Mwea Ward | Site preparation, construction | To prevent flooding and erosion along critical sections of the roadway | Improved drainage efficiency and reduced risk of flooding | Road | Installation of Culverts – Mwea Ward |  | Mwea |  | Road | Road | Road | 2023-01-07 | 21/05/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 998876 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Grading of Roads in Mwea ward | Site preparation, grading, compaction and finishing | To level and shape road surface for improved drivability andsafety | Improved accessibility and transportation efficiency | Road | Grading of Roads in Mwea ward |  | Mwea |  | Road | Road | Road | 2023-01-07 | 19/06/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 997507 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Widening, grading and maintenance of kagaari ciakungugu- kang’ote road | Road widening, grading, maintenance | To wide roads to accommodate increased traffic and improve vehicle movement | Reduced travel time, vehicle maintenance costs and accidents | Road | Widening, grading and maintenance of kagaari ciakungugu- kang’ote road |  | Kagaari |  | Road | Road | Road | 2023-01-07 | 19/06/2024 | 30/6/2024 | 30/6/2024 | 1498664 | 1498664 | 1498664 | County Treasury | N/A | 1498664 | N.A | 1498664 | 100% | 1497328 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance And Storm Water Drainage Works Of Karundori Kiangungi Road | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance And Storm Water Drainage Works Of Karundori Kiangungi Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 19/06/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2997394 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Makima kwa Mutundu Junction | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Makima kwa Mutundu Junction |  | Makima |  | Road | Road | Road | 2023-01-07 | 19/06/2024 | 30/6/2024 | 30/6/2024 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N.A | 3000000 | 100% | 2996164 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kathugu Ngiyori Road | Site assessment, grading and reshaping, spot gravelling, vegetation control | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance of Kathugu Ngiyori Road |  | Embu |  | Road | Road | Road | 2023-01-07 | 19/06/2024 | 30/6/2024 | 30/6/2024 | 1800000 | 1800000 | 1800000 | County Treasury | N/A | 1800000 | N.A | 1800000 | 100% | 1799856 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Construction Thura Foot Bridge | Site preparation and construction | To provide a safe and reliable pedestrian crossing point | Improved eccessibility and mobility for pedestrians | Road | Construction Thura Foot Bridge |  | Embu |  | Road | Road | Road | 2023-01-07 | 21/06/2024 | 30/6/2024 | 30/6/2024 | 10000000 | 10000000 | 10000000 | County Treasury | N/A | 10000000 | N.A | 10000000 | 100% | 9503811 | N/A | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A
| Installation of Solar Floodlights at Karura Market-(Kiambere Ward) | Site survey, procurement and installation | To provide reliable lighting for improved visibility and safety during night-time | Improved safety and security in public spaces during the night | Road | Installation of Solar Floodlights at Karura Market-(Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 |  | 30/6/2024 | 30/6/2024 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N.A | 500000 | 100% | 497779 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Solar Floodlights at Karura Market-(Kiambere Ward) | Site survey, procurement and installation | To provide reliable lighting for improved visibility and safety during night-time | Improved safety and security in public spaces during the night | Road | Installation of Solar Floodlights at Karura Market-(Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 |  | 30/6/2024 | 30/6/2024 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N.A | 500000 | 100% | 497779 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation of Solar Floodlight at Kathiga Kanyonga- (Kiambere Ward) | Site survey, procurement and installation | To provide reliable lighting for improved visibility and safety during night-time | Improved safety and security in public spaces during the night | Road | Installation of Solar Floodlight at Kathiga Kanyonga- (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2023-01-07 |  | 30/6/2024 | 30/6/2024 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N.A | 500000 | 100% | 496899 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation Of Streetlights At Gatunduri And Kivue- phase 2 | Site survey procurement and installation | To improve visibility and safety along roads, streets and public spaces | Improved road safet and visibility at night | Road | Installation Of Streetlights At Gatunduri And Kivue- phase 2 |  | Kivue |  | Road | Road | Road | 2023-01-07 | 16/05/2024 | 30/6/2024 | 30/6/2024 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N.A | 1000000 | 100% | 997325 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Perimeter wall, gate and landscaping in former county treasurer's house | Perimeter wall construction, gate installation, and landscaping works | To create an environmentally friendly and low-maintenance outdoor spaces | Improved environmental quality of the area | Road | Perimeter wall, gate and landscaping in former county treasurer's house |  | Embu |  | Road | Road | Road | 2023-01-07 | 23/5/2024 | 30/6/2024 | 30/6/2024 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N.A | 4500000 | 100% | 4492392 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Motor vehicles GKA 396H and GKA | Engine oil change, brakes adjustments, tire inspection etc | To ensure all motor vehicles are safe, roadworthy and operational | Reduced vehicle downtime and operational disruptions | Road | Maintenance of Motor vehicles GKA 396H and GKA |  | Embu |  | Road | Road | Road | 2023-01-07 | 2024-01-07 | 30/6/2024 | 30/6/2024 | 488300 | 488300 | 488300 | County Treasury | N/A | 488300 | N.A | 488300 | 100% | 484288 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Installation & floodlights | Site survey, procurement and installation | To provide reliable lighting for improved visibility and safety during night-time | Improved safety and security in public spaces during the night | Road | Installation & floodlights |  | Embu |  | Road | Road | Road | 2023-01-07 | 2024-01-07 | 30/6/2024 | 30/6/2024 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N.A | 1200000 | 100% | 1185207 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Motor vehicles KBY 827C and KBY 930C make case 865B | Engine oil change, brakes adjustments, tire inspection etc | To ensure all motor vehicles are safe, roadworthy and operational | Reduced vehicle downtime and operational disruptions | Road | Maintenance of Motor vehicles KBY 827C and KBY 930C make case 865B |  | Embu |  | Road | Road | Road | 2023-01-07 | 14/6/2025 | 30/6/2024 | 30/6/2024 | 1800000 | 1800000 | 1800000 | County Treasury | N/A | 1800000 | N.A | 1800000 | 100% | 1781760 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
| Repair of motor vehicle | Engine oil change, brakes adjustments, tire inspection etc | To ensure all motor vehicles are safe, roadworthy and operational | Reduced vehicle downtime and operational disruptions | Road | Repair of motor vehicle |  | Embu |  | Road | Road | Road | 2023-01-07 | 2024-10-07 | 30/6/2024 | 30/6/2024 | 386200 | 386200 | 386200 | County Treasury | N/A | 386200 | N.A | 386200 | 100% | 386200 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
2022/2023
| Proposed Civil Works Construction of Toilet,Shed and Fencing for Lorries holding site at Majimbo | Procurement, design, delivery and installation | To improve working conditions for lorry drevers, promote public health, enhance security | Reduced accidents and security threats | Road | Proposed Civil Works Construction of Toilet,Shed and Fencing for Lorries holding site at Majimbo |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-08-03 | 30/6/2023 | 30/6/2023 | 2975678 | 2975678 | 2975678 | County treasury | N/A | 2975678 | N/A | 2975678 | 100% | 2975678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Prosed construction of Miraa Trading Market Phase I | Procurement, design, brick laying and levelling | To enhance security and health | Well maintained miraaa tradin g centre | Road | Prosed construction of Miraa Trading Market Phase I |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-12-04 | 30/6/2023 | 30/6/2023 | 12014143 | 12014143 | 12014143 | County treasury | N/A | 12014143 | N/A | 12014143 | 100% | 12014143 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Manyatta Road (Ruguru Ngandori) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Manyatta Road (Ruguru Ngandori) |  | Ruguru Ngandori |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1997346 | 1997346 | 1997346 | County treasury | N/A | 1997346 | N/A | 1997346 | 100% | 1997346 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kathogu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kathogu Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2997672 | 2997672 | 2997672 | County treasury | N/A | 2997672 | N/A | 2997672 | 100% | 2997672 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamama Road (Ruguru Ngandori) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kamama Road (Ruguru Ngandori) |  | Ruguru Ngandori |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening, Grading And Gravelling of Karururi – Ithata Loop Road | Road opening, grading works and gravelling | To open and construct a new roasd section to improve connectivity and accessibility | A newly opened, graded, and gravelling road road in good condition | Road | Opening, Grading And Gravelling of Karururi – Ithata Loop Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3983150 | 3983150 | 3983150 | County treasury | N/A | 3983150 | N/A | 3983150 | 100% | 3983150 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling of Kamwove Road (Nginda Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling of Kamwove Road (Nginda Ward) |  | Nginda Ward |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2996582 | 2996582 | 2996582 | County treasury | N/A | 2996582 | N/A | 2996582 | 100% | 2996582 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening, Grading, Gravelling And Culverts of Kianguri Road | Road opening, grading works and gravelling | To open and construct a new roasd section to improve connectivity and accessibility | A newly opened, graded, and gravelling road road in good condition | Road | Opening, Grading, Gravelling And Culverts of Kianguri Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2398926 | 2398926 | 2398926 | County treasury | N/A | 2398926 | N/A | 2398926 | 100% | 2398926 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance of Ngarari – Kiamuringa Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance of Ngarari – Kiamuringa Road |  |  |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3498414 | 3498414 | 3498414 | County treasury | N/A | 3498414 | N/A | 3498414 | 100% | 3498414 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Gravelling of Yonder – Kangeta And Muraru – Market Road | Clearing , shaping and grading | To achieve a stable all-weather road | Enhanced transport efficiency | Road | 2. Gravelling of Yonder – Kangeta And Muraru – Market Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3498414 | 3498414 | 3498414 | County treasury | N/A | 3498414 | N/A | 3498414 | 100% | 3498414 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murramming And Widening of Karigiri – Njeruri Road (Kyeni North) | Clearing , preparation of road reserve | To enhance road safety | Smooth movement of vehicles and pendestrians | Road | Murramming And Widening of Karigiri – Njeruri Road (Kyeni North) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2998716 | 2998716 | 2998716 | County treasury | N/A | 2998716 | N/A | 2998716 | 100% | 2998716 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Gravelling Of Kithangari – Gotongoro Road (Gaturi North) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Gravelling Of Kithangari – Gotongoro Road (Gaturi North) |  | Gaturi North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4496752 | 4496752 | 4496752 | County treasury | N/A | 4496752 | N/A | 4496752 | 100% | 4496752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading And Gravelling Of Kiethetu – Ndagakira Road 3. Grading And Gravelling Of Kathiiri – Gituri Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Grading And Gravelling Of Kiethetu – Ndagakira Road 3. Grading And Gravelling Of Kathiiri – Gituri Road |  | Gituri |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4496752 | 4496752 | 4496752 | County treasury | N/A | 4496752 | N/A | 4496752 | 100% | 4496752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murramming Of Gwa Josiah – Kwa Kavengi Road 2. Grading And Gravelling of Mugaari – Kiaragana Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Murramming Of Gwa Josiah – Kwa Kavengi Road 2. Grading And Gravelling of Mugaari – Kiaragana Road |  | Kiaragana |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2996280 | 2996280 | 2996280 | County treasury | N/A | 2996280 | N/A | 2996280 | 100% | 2996280 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murramming Of Kyeni Upper Kiregi – Kiunguri Road (Kyeni North)2.Murraming Of Rukuriri – Kariari Road 3. Grading And Gravelling Of Kathari – Gitwa Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Murramming Of Kyeni Upper Kiregi – Kiunguri Road (Kyeni North)2.Murraming Of Rukuriri – Kariari Road 3. Grading And Gravelling Of Kathari – Gitwa Road |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2984557 | 2984557 | 2984557 | County treasury | N/A | 2984557 | N/A | 2984557 | 100% | 2984557 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| . Widening, Grading And Gravelling Of Kwa Machaki Road (Mbeti North) | Clearing, grading and gravelling | To ensure reliable access throughout the year | Reduced road maintenace | Road | . Widening, Grading And Gravelling Of Kwa Machaki Road (Mbeti North) |  | Mbeti North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4395646 | 4395646 | 4395646 | County treasury | N/A | 4395646 | N/A | 4395646 | 100% | 4395646 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (2). Widening, Grading And Gravelling Of Kwa Gwa Gititi Road, (3). Widening, Grading Of Gwa Gicovi – Rwarari Road,(4.) Grading And Gravelling Of Ikonguu Road | Clearing, grading and gravelling | To ensure reliable access throughout the year | Reduced road maintenace | Road | (2). Widening, Grading And Gravelling Of Kwa Gwa Gititi Road, (3). Widening, Grading Of Gwa Gicovi – Rwarari Road,(4.) Grading And Gravelling Of Ikonguu Road |  | Ikonguu Road |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4395646 | 4395646 | 4395646 | County treasury | N/A | 4395646 | N/A | 4395646 | 100% | 4395646 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Kamugere Kathangari Kianjuki Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Kamugere Kathangari Kianjuki Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3298715 | 3298715 | 3298715 | County treasury | N/A | 3298715 | N/A | 3298715 | 100% | 3298715 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing And Grading Of Mutuobare Sports Ground Area | Site clearing, grading and shaping | To ensure proper surface smoothness and compaction | Increased player safety | Road | Dozing And Grading Of Mutuobare Sports Ground Area |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1481820 | 1481820 | 1481820 | County treasury | N/A | 1481820 | N/A | 1481820 | 100% | 1481820 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Grading Of Roads (Kagaari South) | Site clearing, shaping | To ensure proper surface smoothness and compaction | Improved community well | Road | (1) Grading Of Roads (Kagaari South) |  | Kagaari South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4994647 | 4994647 | 4994647 | County treasury | N/A | 4994647 | N/A | 4994647 | 100% | 4994647 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Murraming Of Roads In Kagaari South) | Clearing, shaping and grading | To improve their structural strength and durabilty | Low vehicle operating cost | Road | 2. Murraming Of Roads In Kagaari South) |  | Kagaari South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4994647 | 4994647 | 4994647 | County treasury | N/A | 4994647 | N/A | 4994647 | 100% | 4994647 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kambevo Road In Nginda | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kambevo Road In Nginda |  | Nginda |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1994040 | 1994040 | 1994040 | County treasury | N/A | 1994040 | N/A | 1994040 | 100% | 1994040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Mathai – Munou Road | Site preparation, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Murraming Of Mathai – Munou Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3493920 | 3493920 | 3493920 | County treasury | N/A | 3493920 | N/A | 3493920 | 100% | 3493920 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gerish Mama Rishi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gerish Mama Rishi Road |  | Rishi |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 990872 | 990872 | 990872 | County treasury | N/A | 990872 | N/A | 990872 | 100% | 990872 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads In Kagaari South | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening Of Roads In Kagaari South |  | Kagaari South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3997459 | 3997459 | 3997459 | County treasury | N/A | 3997459 | N/A | 3997459 | 100% | 3997459 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Grading And Gravelling Of Gitumbi – Kirivu – Gichagi Road (2) Grading And Gravelling Of Itonguri – Gicugu Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | (1) Grading And Gravelling Of Gitumbi – Kirivu – Gichagi Road (2) Grading And Gravelling Of Itonguri – Gicugu Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3498374 | 3498374 | 3498374 | County treasury | N/A | 3498374 | N/A | 3498374 | 100% | 3498374 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts And Gabions (Agpo Youth) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts And Gabions (Agpo Youth) |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1998796 | 1998796 | 1998796 | County treasury | N/A | 1998796 | N/A | 1998796 | 100% | 1998796 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening of Roads In Kyeni South | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Roads In Kyeni South |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2999470 | 2999470 | 2999470 | County treasury | N/A | 2999470 | N/A | 2999470 | 100% | 2999470 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Kimuri Wanaruona Road (Mbeti North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | (1) Kimuri Wanaruona Road (Mbeti North) |  | Mbeti North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3976758 | 3976758 | 3976758 | County treasury | N/A | 3976758 | N/A | 3976758 | 100% | 3976758 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (2) Itabua Gichegeri Road (Mbeti North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | (2) Itabua Gichegeri Road (Mbeti North) |  | Mbeti North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3976758 | 3976758 | 3976758 | County treasury | N/A | 3976758 | N/A | 3976758 | 100% | 3976758 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widening /Maintenance Of Kwa Muthugu Njugu Njagi Road | Clearing, and grubbing | To improve traffic flow, safety and road safety performance | To improve traffic flow, safety and road safety performance | Road | Widening /Maintenance Of Kwa Muthugu Njugu Njagi Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1490310 | 1490310 | 1490310 | County treasury | N/A | 1490310 | N/A | 1490310 | 100% | 1490310 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Kithegi –Gitituri – Mvangwa Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening Of Kithegi –Gitituri – Mvangwa Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1393740 | 1393740 | 1393740 | County treasury | N/A | 1393740 | N/A | 1393740 | 100% | 1393740 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts And Gabions In Various Roads | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts And Gabions In Various Roads |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1990560 | 1990560 | 1990560 | County treasury | N/A | 1990560 | N/A | 1990560 | 100% | 1990560 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads In Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Roads In Kyeni South |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2497654 | 2497654 | 2497654 | County treasury | N/A | 2497654 | N/A | 2497654 | 100% | 2497654 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kiambogo (A) Road In Gaturi South | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kiambogo (A) Road In Gaturi South |  | Gaturi South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1993924 | 1993924 | 1993924 | County treasury | N/A | 1993924 | N/A | 1993924 | 100% | 1993924 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Grading And Gravelling Of Muva Road (Gaturi North) (2) Grading And Gravelling Of Gaikiro B And A Road (Gaturi North) (3) Grading And Gravelling Of Kiandari – Kasarani Road (Gaturi North) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | (1) Grading And Gravelling Of Muva Road (Gaturi North) (2) Grading And Gravelling Of Gaikiro B And A Road (Gaturi North) (3) Grading And Gravelling Of Kiandari – Kasarani Road (Gaturi North) |  | Gaturi North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4495742 | 4495742 | 4495742 | County treasury | N/A | 4495742 | N/A | 4495742 | 100% | 4495742 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gangaru – Ntambo-Gitwe Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gangaru – Ntambo-Gitwe Roads |  | Gitwe |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3999471 | 3999471 | 3999471 | County treasury | N/A | 3999471 | N/A | 3999471 | 100% | 3999471 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Roads In Kyeni South | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling Of Roads In Kyeni South |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2497944 | 2497944 | 2497944 | County treasury | N/A | 2497944 | N/A | 2497944 | 100% | 2497944 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Maintenance Of Katharuku Gogo Road, | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | (1) Maintenance Of Katharuku Gogo Road, |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2998832 | 2998832 | 2998832 | County treasury | N/A | 2998832 | N/A | 2998832 | 100% | 2998832 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (2) Maintenance Of Gaturi Nduuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | (2) Maintenance Of Gaturi Nduuri Road |  |  |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2998832 | 2998832 | 2998832 | County treasury | N/A | 2998832 | N/A | 2998832 | 100% | 2998832 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads In Kirimari | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | A well-graded and gvavelled road section of in good condition | Road | Opening Of Roads In Kirimari |  | Kirimari |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3999030 | 3999030 | 3999030 | County treasury | N/A | 3999030 | N/A | 3999030 | 100% | 3999030 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Kagaari South | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts In Kagaari South |  | Kagaari South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 996150 | 996150 | 996150 | County treasury | N/A | 996150 | N/A | 996150 | 100% | 996150 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widening/Maintenance Of Driftiri Mwana Wa Gitii Road (2) Maintenance Of Mwana Wa Gitii Road | Clearing, and grubbing | To improve traffic flow, safety and road safety performance | To improve traffic flow, safety and road safety performance | Road | Widening/Maintenance Of Driftiri Mwana Wa Gitii Road (2) Maintenance Of Mwana Wa Gitii Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3776055 | 3776055 | 3776055 | County treasury | N/A | 3776055 | N/A | 3776055 | 100% | 3776055 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiini Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiini Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1992880 | 1992880 | 1992880 | County treasury | N/A | 1992880 | N/A | 1992880 | 100% | 1992880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Maintenance Of Roads In Runyenjes Central | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | (1) Maintenance Of Roads In Runyenjes Central |  | Runyenjes |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3069557 | 3069557 | 3069557 | County treasury | N/A | 3069557 | N/A | 3069557 | 100% | 3069557 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Installation Of Culverts In Runyenjes Central | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | 2. Installation Of Culverts In Runyenjes Central |  | Runyenjes |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3069557 | 3069557 | 3069557 | County treasury | N/A | 3069557 | N/A | 3069557 | 100% | 3069557 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurina Makathi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurina Makathi Road |  | Karurina |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1990270 | 1990270 | 1990270 | County treasury | N/A | 1990270 | N/A | 1990270 | 100% | 1990270 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Cianyi – Mwangaza Road | Site preparation, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Murraming Of Cianyi – Mwangaza Road |  | mwangaza |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1999956 | 1999956 | 1999956 | County treasury | N/A | 1999956 | N/A | 1999956 | 100% | 1999956 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading, Dozing, Gravelling And Culverts Of Kiambogo (B) Road In Gaturi South 2. Grading And Gravelling Of Ack Road In Gaturi South | Dozing, clearing, cut doun high and grading | To improve surface condition and structural strength | Improved roads | Road | 1. Grading, Dozing, Gravelling And Culverts Of Kiambogo (B) Road In Gaturi South 2. Grading And Gravelling Of Ack Road In Gaturi South |  | Gaturi South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3997685 | 3997685 | 3997685 | County treasury | N/A | 3997685 | N/A | 3997685 | 100% | 3997685 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Gitumbi Tujenge Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening Of Gitumbi Tujenge Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1348848 | 1348848 | 1348848 | County treasury | N/A | 1348848 | N/A | 1348848 | 100% | 1348848 | N/A | N/A | Completed | 100% | N/A |  | N/A | N/A | N/A | N/A | N/A
| (1) Murraming Of Kiangungi – Ndiu-Igumu Road (Kyeni) (2) Grading Of Njikoya – Ngorweri – Muganjuki Junction Road (Kyeni North) (Agpo Pwd) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | (1) Murraming Of Kiangungi – Ndiu-Igumu Road (Kyeni) (2) Grading Of Njikoya – Ngorweri – Muganjuki Junction Road (Kyeni North) (Agpo Pwd) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3989565 | 3989565 | 3989565 | County treasury | N/A | 3989565 | N/A | 3989565 | 100% | 3989565 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Kwa Mutuwaru – Kwa Makenge Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Murraming Of Kwa Mutuwaru – Kwa Makenge Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 2933408 | 2933408 | 2933408 | County treasury | N/A | 2933408 | N/A | 2933408 | 100% | 2933408 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Mbuvori Gatareri Road (Nginda Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Mbuvori Gatareri Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1995780 | 1995780 | 1995780 | County treasury | N/A | 1995780 | N/A | 1995780 | 100% | 1995780 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Grading Dozing, Gravelling And Culverts Of Rututu | Dozing, clearing, cut doun high and grading | To improve surface condition and structural strength | Improved roads | Road | (1) Grading Dozing, Gravelling And Culverts Of Rututu |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3997012 | 3997012 | 3997012 | County treasury | N/A | 3997012 | N/A | 3997012 | 100% | 3997012 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading, Dozing, Gravelling And Culverts Of Njakairi Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Grading, Dozing, Gravelling And Culverts Of Njakairi Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3997012 | 3997012 | 3997012 | County treasury | N/A | 3997012 | N/A | 3997012 | 100% | 3997012 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njumbiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njumbiri Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1290256 | 1290256 | 1290256 | County treasury | N/A | 1290256 | N/A | 1290256 | 100% | 1290256 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Gravelling Of Gakwegori – Gacenga Road (Kyeni South) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Gravelling Of Gakwegori – Gacenga Road (Kyeni South) |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3991502 | 3991502 | 3991502 | County treasury | N/A | 3991502 | N/A | 3991502 | 100% | 3991502 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading And Gravelling Of Kinthithe – Nyagari Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Grading And Gravelling Of Kinthithe – Nyagari Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3991502 | 3991502 | 3991502 | County treasury | N/A | 3991502 | N/A | 3991502 | 100% | 3991502 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance Of Kiumu – Gakwegori Road 2. Widening | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance Of Kiumu – Gakwegori Road 2. Widening |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 4681702 | 4681702 | 4681702 | County treasury | N/A | 4681702 | N/A | 4681702 | 100% | 4681702 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Gravelling Of Gakwegori – Gacenga Road (Kyeni South) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Gravelling Of Gakwegori – Gacenga Road (Kyeni South) |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3991502 | 3991502 | 3991502 | County treasury | N/A | 3991502 | N/A | 3991502 | 100% | 3991502 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading And Gravelling Of Kinthithe – Nyagari Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Grading And Gravelling Of Kinthithe – Nyagari Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 3991502 | 3991502 | 3991502 | County treasury | N/A | 3991502 | N/A | 3991502 | 100% | 3991502 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling/ Maitenance Of Rwika 43 Road | Grading, reshaping, | To improve road surface and durability | Gravelled and well-maintained road | Road | Gravelling/ Maitenance Of Rwika 43 Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-05 | 30/6/2023 | 30/6/2023 | 1990560 | 1990560 | 1990560 | County treasury | N/A | 1990560 | N/A | 1990560 | 100% | 1990560 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading and Gravelling of Kathari Eapc - Junction Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading and Gravelling of Kathari Eapc - Junction Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3494326 | 3494326 | 3494326 | County treasury | N/A | 3494326 | N/A | 3494326 | 100% | 3494326 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading and Gravelling of Muganjuki Gitwa Road (Kyeni Morth) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Grading and Gravelling of Muganjuki Gitwa Road (Kyeni Morth) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3494326 | 3494326 | 3494326 | County treasury | N/A | 3494326 | N/A | 3494326 | 100% | 3494326 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening, Grading and Widening of Roads (Nginda Ward) | Bush clearing, grubbing road alignment | To improve accessibilty, safety and trafiic flow | Improved roads | Road | Opening, Grading and Widening of Roads (Nginda Ward) |  | Nginda Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3988080 | 3988080 | 3988080 | County treasury | N/A | 3988080 | N/A | 3988080 | 100% | 3988080 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (Agpo Women) Description: Grading Of Gwakarigu Road (Kiambere Ward) | Reshaping, camber and leveling | To restore proper road profile and improve surface condition | Smoother surface, reduced water ponding | Road | (Agpo Women) Description: Grading Of Gwakarigu Road (Kiambere Ward) |  | Kiambere Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1495820 | 1495820 | 1495820 | County treasury | N/A | 1495820 | N/A | 1495820 | 100% | 1495820 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Bush Clearing Of Roads | Cutting and clearing | To improve visibility, accessibility and road safety | Cleared road corridors | Road | Bush Clearing Of Roads |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 994932 | 994932 | 994932 | County treasury | N/A | 994932 | N/A | 994932 | 100% | 994932 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (Agpo Women) Description: Grading And Gravelling Of Nthunguri - Njeruri Road (Kyeni North) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | (Agpo Women) Description: Grading And Gravelling Of Nthunguri - Njeruri Road (Kyeni North) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1299455 | 1299455 | 1299455 | County treasury | N/A | 1299455 | N/A | 1299455 | 100% | 1299455 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Kianjokoma - Kathangari Road (Gaturi North) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Kianjokoma - Kathangari Road (Gaturi North) |  | Gaturi North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1299014 | 1299014 | 1299014 | County treasury | N/A | 1299014 | N/A | 1299014 | 100% | 1299014 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening (Dozing) Of Roads (Muminji Ward) | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening (Dozing) Of Roads (Muminji Ward) |  | Muminji Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3499488 | 3499488 | 3499488 | County treasury | N/A | 3499488 | N/A | 3499488 | 100% | 3499488 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Gitumbi Quarry Road (Kithimu Ward) | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening Of Gitumbi Quarry Road (Kithimu Ward) |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1390086 | 1390086 | 1390086 | County treasury | N/A | 1390086 | N/A | 1390086 | 100% | 1390086 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Kwa Andu A Njiru Drift (Mavuria Ward) | Site clearing, excavation and foundation preparation | To provide a reliable and safe low-level crossing for vehicles and pedestrians | Undisrupted travel | Road | Construction Of Kwa Andu A Njiru Drift (Mavuria Ward) |  | Mavuria Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2499104 | 2499104 | 2499104 | County treasury | N/A | 2499104 | N/A | 2499104 | 100% | 2499104 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiumu – Gakwegori Roads In Mavuria Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiumu – Gakwegori Roads In Mavuria Ward |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4491810 | 4491810 | 4491810 | County treasury | N/A | 4491810 | N/A | 4491810 | 100% | 4491810 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ena River Foot Bridge At Kangiri – Evurore Word | Site clearing, excavation, and foundation preparation | To provide safe and eliable crossing for pedestrians | uninterupted access to community | Road | Construction Of Ena River Foot Bridge At Kangiri – Evurore Word |  | Evurore |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3999680 | 3999680 | 3999680 | County treasury | N/A | 3999680 | N/A | 3999680 | 100% | 3999680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance Gitakari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance Gitakari Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1999202 | 1999202 | 1999202 | County treasury | N/A | 1999202 | N/A | 1999202 | 100% | 1999202 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Maintenance Kiande – Kiithanje - Irangi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 2. Maintenance Kiande – Kiithanje - Irangi Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1999202 | 1999202 | 1999202 | County treasury | N/A | 1999202 | N/A | 1999202 | 100% | 1999202 | N/A | N/A | Completed | 100% | N/A | N/A |  | N/A | N/A | N/A | N/A
| (Agpo Women) Description: Grading, Dozing and Culverts of Kithare Kithiruri Road (Kyeni North Ward) | Dozing, clearing, cut doun high and grading | To improve surface condition and structural strength | Improved roads | Road | (Agpo Women) Description: Grading, Dozing and Culverts of Kithare Kithiruri Road (Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1699864 | 1699864 | 1699864 | County treasury | N/A | 1699864 | N/A | 1699864 | 100% | 1699864 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Opening, Grading and Murramming of Kwa Tee – Koma Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Opening, Grading and Murramming of Kwa Tee – Koma Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3998752 | 3998752 | 3998752 | County treasury | N/A | 3998752 | N/A | 3998752 | 100% | 3998752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Maintenance Of Gatuiri – Maviani Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 2. Maintenance Of Gatuiri – Maviani Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3998752 | 3998752 | 3998752 | County treasury | N/A | 3998752 | N/A | 3998752 | 100% | 3998752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Opening and Dozing of Roads in Evurore | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 1. Opening and Dozing of Roads in Evurore |  | Evurore |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3998630 | 3998630 | 3998630 | County treasury | N/A | 3998630 | N/A | 3998630 | 100% | 3998630 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Grading and Maintenance of Road | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | 2. Grading and Maintenance of Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3998630 | 3998630 | 3998630 | County treasury | N/A | 3998630 | N/A | 3998630 | 100% | 3998630 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening And Grading Of Kwa Musomba – Kituluni Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening And Grading Of Kwa Musomba – Kituluni Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3997221 | 3997221 | 3997221 | County treasury | N/A | 3997221 | N/A | 3997221 | 100% | 3997221 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Opening And Grading Of Kilaani – Kwa Katuku Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 2. Opening And Grading Of Kilaani – Kwa Katuku Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3997221 | 3997221 | 3997221 | County treasury | N/A | 3997221 | N/A | 3997221 | 100% | 3997221 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3. Opening And Grading Of Ack Kilia – Muasa Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 3. Opening And Grading Of Ack Kilia – Muasa Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3997221 | 3997221 | 3997221 | County treasury | N/A | 3997221 | N/A | 3997221 | 100% | 3997221 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading of Kariguri – Kamaunju Road | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading of Kariguri – Kamaunju Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1999364 | 1999364 | 1999364 | County treasury | N/A | 1999364 | N/A | 1999364 | 100% | 1999364 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Repair and Distilling Culverts (Kithimu Ward) | Clearing accumulated silt and debris | To ensure proper drainage and prolong the service life of the structure | Functioning culverts | Road | (1) Repair and Distilling Culverts (Kithimu Ward) |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 749, 858.80 | 749, 858.80 | 749, 858.80 | County treasury | N/A | 749, 858.80 | N/A | 749, 858.80 | 100% | 749, 858.80 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (2) Intallation of Gakurungu Bridge Gabions | Site clearing, excavation foundation laying and installation | To provide safe and reliable crossing over the river | Uninterupted all-weather connectivity | Road | (2) Intallation of Gakurungu Bridge Gabions |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 749, 858.80 | 749, 858.80 | 749, 858.80 | County treasury | N/A | 749, 858.80 | N/A | 749, 858.80 | 100% | 1499358 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gitaugu – Manjatiri Road (Muminji Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gitaugu – Manjatiri Road (Muminji Ward) |  | Muminji Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1499358 | 1499358 | 1499358 | County treasury | N/A | 1499358 | N/A | 1499358 | 100% | 1499358 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Roads in Kiambere Ward | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Roads in Kiambere Ward |  | Kiambere Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4985970 | 4985970 | 4985970 | County treasury | N/A | 4985970 | N/A | 4985970 | 100% | 4985970 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Description: Opening and Grading of Roads in Nthawa Ward | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Description: Opening and Grading of Roads in Nthawa Ward |  | Nthawa |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4489490 | 4489490 | 4489490 | County treasury | N/A | 4489490 | N/A | 4489490 | 100% | 4489490 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts in Kyeni South | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts in Kyeni South |  | Kyeni |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1299664 | 1299664 | 1299664 | County treasury | N/A | 1299664 | N/A | 1299664 | 100% | 1299664 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening, Grading and Murramming of Karaba - Gitaraka Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Opening, Grading and Murramming of Karaba - Gitaraka Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2991180 | 2991180 | 2991180 | County treasury | N/A | 2991180 | N/A | 2991180 | 100% | 2991180 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Improvement of Itiira Road (Muminji Ward) | Bgrubbing, clearing, grading, reshaping and gravelling | To enhance accessibility, safety, and overall perfomance | Supported economic and social activities | Road | Improvement of Itiira Road (Muminji Ward) |  | Muminji Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 1996081 | 1996081 | 1996081 | County treasury | N/A | 1996081 | N/A | 1996081 | 100% | 1996081 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Roads in Muminji Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Roads in Muminji Ward |  | Muminji |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2999607 | 2999607 | 2999607 | County treasury | N/A | 2999607 | N/A | 2999607 | 100% | 2999607 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakwegori – Karago Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gakwegori – Karago Road (Kyeni South Ward) |  | Kyeni South Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2499835 | 2499835 | 2499835 | County treasury | N/A | 2499835 | N/A | 2499835 | 100% | 2499835 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening of Roads in Mavuria Ward | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Roads in Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3, 497,980.00 | 3, 497,980.00 | 3, 497,980.00 | County treasury | N/A | 3, 497,980.00 | N/A | 3, 497,980.00 | 100% | 3, 497,980.00 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading and Gravelling of Kivumbiri Kaithege Road (Kyeni N. Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading and Gravelling of Kivumbiri Kaithege Road (Kyeni N. Ward) |  | Kyeni North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 995744 | 995744 | 995744 | County treasury | N/A | 995744 | N/A | 995744 | 100% | 995744 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| (1) Spot Grading And Murramming Of Mwanzo – Gatwanyaga – Kavengele Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | (1) Spot Grading And Murramming Of Mwanzo – Gatwanyaga – Kavengele Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2999760 | 2999760 | 2999760 | County treasury | N/A | 2999760 | N/A | 2999760 | 100% | 2999760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Spot Grading And Murramming Of Mwanzo Aic Ndune – Safaricom Mast – Mbondoni Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Spot Grading And Murramming Of Mwanzo Aic Ndune – Safaricom Mast – Mbondoni Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2999760 | 2999760 | 2999760 | County treasury | N/A | 2999760 | N/A | 2999760 | 100% | 2999760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction of Culverts and Drifts in Evurore Ward | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Culverts and Drifts in Evurore Ward |  | Evurore |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 2498988 | 2498988 | 2498988 | County treasury | N/A | 2498988 | N/A | 2498988 | 100% | 2498988 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading And Murramming Of Mbonzuki – Kilia Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading And Murramming Of Mbonzuki – Kilia Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4999020 | 4999020 | 4999020 | County treasury | N/A | 4999020 | N/A | 4999020 | 100% | 4999020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Opening, Grading And Murramming Of Makutano Kobil – Karuku Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Opening, Grading And Murramming Of Makutano Kobil – Karuku Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4999020 | 4999020 | 4999020 | County treasury | N/A | 4999020 | N/A | 4999020 | 100% | 4999020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Roads Drainage Systems (Gatete - Karura Box Culverts) In Kiambere Ward | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Roads Drainage Systems (Gatete - Karura Box Culverts) In Kiambere Ward |  | Kiambere Ward |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 3499488 | 3499488 | 3499488 | County treasury | N/A | 3499488 | N/A | 3499488 | 100% | 3499488 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing, Opening, Graveling and Grading Of Roads In Gaturi North Ward | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Dozing, Opening, Graveling and Grading Of Roads In Gaturi North Ward |  | Gaturi North |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4499095 | 4499095 | 4499095 | County treasury | N/A | 4499095 | N/A | 4499095 | 100% | 4499095 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Grading and Murramming of Mbonzuki – Kilia Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 1. Grading and Murramming of Mbonzuki – Kilia Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4999020 | 4999020 | 4999020 | County treasury | N/A | 4999020 | N/A | 4999020 | 100% | 4999020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Opening, Grading and Murramming of Makutano Kobil – Karuku Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | 2. Opening, Grading and Murramming of Makutano Kobil – Karuku Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-10-05 | 30/6/2023 | 30/6/2023 | 4999020 | 4999020 | 4999020 | County treasury | N/A | 4999020 | N/A | 4999020 | 100% | 4999020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| .re-advertisement of opening of mucegethiu – kandari road | Vegetation clearing, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | .re-advertisement of opening of mucegethiu – kandari road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000492 | 4000492 | 4000492 | County treasury | N/A | 4000492 | N/A | 4000492 | 100% | 4000492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. re-advertisement of maintenance of kivue intake road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. re-advertisement of maintenance of kivue intake road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000492 | 4000492 | 4000492 | County treasury | N/A | 4000492 | N/A | 4000492 | 100% | 4000492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3. re-advertisement of maintenance of gitaungu road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 3. re-advertisement of maintenance of gitaungu road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000492 | 4000492 | 4000492 | County treasury | N/A | 4000492 | N/A | 4000492 | 100% | 4000492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Re-Advertisement Of Heavy Grading Of Gatumbiri Road – Mavuria | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1. Re-Advertisement Of Heavy Grading Of Gatumbiri Road – Mavuria |  | Mavuria |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000434 | 4000434 | 4000434 | County treasury | N/A | 4000434 | N/A | 4000434 | 100% | 4000434 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2.Re-Advertisement Of Heavy Grading Of Kabuguri Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2.Re-Advertisement Of Heavy Grading Of Kabuguri Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000434 | 4000434 | 4000434 | County treasury | N/A | 4000434 | N/A | 4000434 | 100% | 4000434 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Re-Advertisement Of Maintenance Of Kigumo – Gititi –Kanginga Road, Re-Advertisement Of Karurumo – Kariru Road (Kyeni South) | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | Re-Advertisement Of Maintenance Of Kigumo – Gititi –Kanginga Road, Re-Advertisement Of Karurumo – Kariru Road (Kyeni South) |  | Kyeni South |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4005735 | 4005735 | 4005735 | County treasury | N/A | 4005735 | N/A | 4005735 | 100% | 4005735 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Re-Advertisement Of Maintenance Of Gachuriri – Rukagori Road, Mbeti South | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | Re-Advertisement Of Maintenance Of Gachuriri – Rukagori Road, Mbeti South |  | Mbeti South |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4058028 | 4058028 | 4058028 | County treasury | N/A | 4058028 | N/A | 4058028 | 100% | 4058028 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Re- Advertisement Of Maintenance Of Kirima –Ngigeri – Gicharu Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. Re- Advertisement Of Maintenance Of Kirima –Ngigeri – Gicharu Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4058028 | 4058028 | 4058028 | County treasury | N/A | 4058028 | N/A | 4058028 | 100% | 4058028 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1.Re-Advertisement Of Grading And Gravelling Of Kangaru Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1.Re-Advertisement Of Grading And Gravelling Of Kangaru Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4003508 | 4003508 | 4003508 | County treasury | N/A | 4003508 | N/A | 4003508 | 100% | 4003508 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Gravelling Of Makathi – Kiangoma Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading And Gravelling Of Makathi – Kiangoma Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4003508 | 4003508 | 4003508 | County treasury | N/A | 4003508 | N/A | 4003508 | 100% | 4003508 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kithungururu – Kathangari Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Kithungururu – Kathangari Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 3803872 | 3803872 | 3803872 | County treasury | N/A | 3803872 | N/A | 3803872 | 100% | 3803872 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamugere – Kevote Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamugere – Kevote Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4008310 | 4008310 | 4008310 | County treasury | N/A | 4008310 | N/A | 4008310 | 100% | 4008310 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kevote – Karue Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kevote – Karue Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4008310 | 4008310 | 4008310 | County treasury | N/A | 4008310 | N/A | 4008310 | 100% | 4008310 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| DOZING, GRADING, DRIFTS AND CULVERTS OF KANGO – KIATHAMBU ROAD 2. DOZING, GRADING AND CULVERTS OF KAURACIRI – MUNGETHO ROAD | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | DOZING, GRADING, DRIFTS AND CULVERTS OF KANGO – KIATHAMBU ROAD 2. DOZING, GRADING AND CULVERTS OF KAURACIRI – MUNGETHO ROAD |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4554891 | 4554891 | 4554891 | County treasury | N/A | 4554891 | N/A | 4554891 | 100% | 4554891 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Culverts, Drifts And Gravelling Of Ndune – Kalisa – Mbonzuki Road | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Culverts, Drifts And Gravelling Of Ndune – Kalisa – Mbonzuki Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000753 | 4000753 | 4000753 | County treasury | N/A | 4000753 | N/A | 4000753 | 100% | 4000753 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading And Opening Of Mbuvori - Karau Primary School Road 2. Re-Advertising Grading And Opening Of Mutuandu – Gatiguri Road 3. Re- Advertising Gravelling Of Rutune Primary School Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | Grading And Opening Of Mbuvori - Karau Primary School Road 2. Re-Advertising Grading And Opening Of Mutuandu – Gatiguri Road 3. Re- Advertising Gravelling Of Rutune Primary School Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000821 | 4000821 | 4000821 | County treasury | N/A | 4000821 | N/A | 4000821 | 100% | 4000821 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Re- Advertisement Of Maintenance Of Kamugere – Kirimari Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1. Re- Advertisement Of Maintenance Of Kamugere – Kirimari Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4010816 | 4010816 | 4010816 | County treasury | N/A | 4010816 | N/A | 4010816 | 100% | 4010816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Re-Advertisement Of Maintenance Of Kithiruri – Giceceni Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. Re-Advertisement Of Maintenance Of Kithiruri – Giceceni Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4010816 | 4010816 | 4010816 | County treasury | N/A | 4010816 | N/A | 4010816 | 100% | 4010816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3. Re- Advertisement Of Maintenance Of Kianyingi Road In Kagaari North | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 3. Re- Advertisement Of Maintenance Of Kianyingi Road In Kagaari North |  | Kagaari North |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4010816 | 4010816 | 4010816 | County treasury | N/A | 4010816 | N/A | 4010816 | 100% | 4010816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1.Re-Advertisement Of Murramming, Compacting And Drainage Systems Of Mariari -Sda Kianjokoma Road 2. Re-Advertisement Of Box Culverts At Gatete – Karura Secondary Road | Reshaping, suply, spreading, water spilling and dozing | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1.Re-Advertisement Of Murramming, Compacting And Drainage Systems Of Mariari -Sda Kianjokoma Road 2. Re-Advertisement Of Box Culverts At Gatete – Karura Secondary Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 3796158 | 3796158 | 3796158 | County treasury | N/A | 3796158 | N/A | 3796158 | 100% | 3796158 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Opening, Grading And Gravelling Of Mivukori Road | Site preparation, gravelling, grading | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 1. Opening, Grading And Gravelling Of Mivukori Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000492 | 4000492 | 4000492 | County treasury | N/A | 4000492 | N/A | 4000492 | 100% | 4000492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Opening, Grading And Gravelling Of Itengetenge – Kamwea Road Kithimu Ward | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 2. Opening, Grading And Gravelling Of Itengetenge – Kamwea Road Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4000492 | 4000492 | 4000492 | County treasury | N/A | 4000492 | N/A | 4000492 | 100% | 4000492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Re-Advertisement Of Maintenance Of Kathungu – Muthithiri Ngeniari Road, 2. Re-Advertisement Of Maintenance Of Kawanjara – Kavangua Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1. Re-Advertisement Of Maintenance Of Kathungu – Muthithiri Ngeniari Road, 2. Re-Advertisement Of Maintenance Of Kawanjara – Kavangua Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 3846908 | 3846908 | 3846908 | County treasury | N/A | 3846908 | N/A | 3846908 | 100% | 3846908 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1.Re-Advertisement Of Grading And Gravelling Of Wendo Muthuari Road, | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1.Re-Advertisement Of Grading And Gravelling Of Wendo Muthuari Road, |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4122988 | 4122988 | 4122988 | County treasury | N/A | 4122988 | N/A | 4122988 | 100% | 4122988 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Re-Advertisement Of Grading And Gravelling Of Gichiche – Kangunu Factory – Kithugururu, 3.Re-Advertisement Of Grading And Gravelling Of Gatinda – Muthauri Road (Covid Road) Agpo | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. Re-Advertisement Of Grading And Gravelling Of Gichiche – Kangunu Factory – Kithugururu, 3.Re-Advertisement Of Grading And Gravelling Of Gatinda – Muthauri Road (Covid Road) Agpo |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4122988 | 4122988 | 4122988 | County treasury | N/A | 4122988 | N/A | 4122988 | 100% | 4122988 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Re-Advertisement Of Grading And Graveling Of Gichegeri Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1. Re-Advertisement Of Grading And Graveling Of Gichegeri Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4005480 | 4005480 | 4005480 | County treasury | N/A | 4005480 | N/A | 4005480 | 100% | 4005480 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Re-Advertisement Of Grading And Graveling Of Makumbiri Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. Re-Advertisement Of Grading And Graveling Of Makumbiri Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4005480 | 4005480 | 4005480 | County treasury | N/A | 4005480 | N/A | 4005480 | 100% | 4005480 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3. Re-Advertisement Of Grading And Graveling Of Kwa Waritho Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 3. Re-Advertisement Of Grading And Graveling Of Kwa Waritho Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4005480 | 4005480 | 4005480 | County treasury | N/A | 4005480 | N/A | 4005480 | 100% | 4005480 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1.Re-Advertisement Of Maintenance Of Rwere – Kenga Road2. Re-Advertisement Of Maintenance Of Kigari Road | Grading, dozing, gravelling, pathole repair, drainage improvement | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1.Re-Advertisement Of Maintenance Of Rwere – Kenga Road2. Re-Advertisement Of Maintenance Of Kigari Road |  | Kigari |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4100113 | 4100113 | 4100113 | County treasury | N/A | 4100113 | N/A | 4100113 | 100% | 4100113 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance Of Kathari – Gaturi Road 2. Maintenance Of Iriari Market – Gichegeni Road – (Agpo- Youth) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance Of Kathari – Gaturi Road 2. Maintenance Of Iriari Market – Gichegeni Road – (Agpo- Youth) |  | Gaturi |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 3931066 | 3931066 | 3931066 | County treasury | N/A | 3931066 | N/A | 3931066 | 100% | 3931066 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Re-Advertisement Grading And Graveling Of Ngandi Nganga – Kyuasini Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 1. Re-Advertisement Grading And Graveling Of Ngandi Nganga – Kyuasini Road |  | Nginda |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4012788 | 4012788 | 4012788 | County treasury | N/A | 4012788 | N/A | 4012788 | 100% | 4012788 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Re- Advertisement Grading And Graveling Of Ngandi Kwa Kivuva – Mbonzuki Road | Site preparation, gravelling, grading | To engage qualified contractors for the upkeep and improvement of the existing road | Qualified contractors aquired | Road | 2. Re- Advertisement Grading And Graveling Of Ngandi Kwa Kivuva – Mbonzuki Road |  | nginda |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4012788 | 4012788 | 4012788 | County treasury | N/A | 4012788 | N/A | 4012788 | 100% | 4012788 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Gravelling Of Siakago Town Roads, 2. Maintenance Of Muchonoke – Kiarwara Road (Agpo Women) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Gravelling Of Siakago Town Roads, 2. Maintenance Of Muchonoke – Kiarwara Road (Agpo Women) |  | Siakago |  | Road | Road | Road | 2022-01-07 | 29/05/2023 | 30/6/2023 | 30/6/2023 | 4, 000,028.00 | 4, 000,028.00 | 4, 000,028.00 | County treasury | N/A | 4, 000,028.00 | N/A | 4, 000,028.00 | 100% | 4, 000,028.00 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mwalimu Kwa Loise Road- Gaturi South Ward. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Mwalimu Kwa Loise Road- Gaturi South Ward. |  | Gaturi South |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 3430236 | 3430236 | 3430236 | County treasury | N/A | 3430236 | N/A | 3430236 | 100% | 3430236 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Maintenance Of Maciara-Mungaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. Maintenance Of Maciara-Mungaru Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2998268 | 2998268 | 2998268 | County treasury | N/A | 2998268 | N/A | 2998268 | 100% | 2998268 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2. Maintenance Of Kathande- Kiorirori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 2. Maintenance Of Kathande- Kiorirori Road |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2998268 | 2998268 | 2998268 | County treasury | N/A | 2998268 | N/A | 2998268 | 100% | 2998268 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 3. Maintenance Of Ngaragatiri Road. – Kagaari North Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 3. Maintenance Of Ngaragatiri Road. – Kagaari North Ward |  | Kagaari North |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2998268 | 2998268 | 2998268 | County treasury | N/A | 2998268 | N/A | 2998268 | 100% | 2998268 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamviu Road- Ruguru Ngandori Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kamviu Road- Ruguru Ngandori Ward |  | Ruguru Ngandori |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 1496632 | 1496632 | 1496632 | County treasury | N/A | 1496632 | N/A | 1496632 | 100% | 1496632 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts And Drainage Of Kanja- Kagaari North Ward | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts And Drainage Of Kanja- Kagaari North Ward |  | Kagaari North |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 1998239 | 1998239 | 1998239 | County treasury | N/A | 1998239 | N/A | 1998239 | 100% | 1998239 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Macira Road- Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Macira Road- Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2816944 | 2816944 | 2816944 | County treasury | N/A | 2816944 | N/A | 2816944 | 100% | 2816944 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. MAINTENANCE OF SOWETO KIATHARI ROAD 2. MAINTENANCE OF MBOGORI ROAD 3. MAINTENANCE OF GICHUKI- MUGUI ROAD- KAGAARI NORTH WARD. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | 1. MAINTENANCE OF SOWETO KIATHARI ROAD 2. MAINTENANCE OF MBOGORI ROAD 3. MAINTENANCE OF GICHUKI- MUGUI ROAD- KAGAARI NORTH WARD. |  | Kagaari North |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2993438 | 2993438 | 2993438 | County treasury | N/A | 2993438 | N/A | 2993438 | 100% | 2993438 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatumu Nthanje Road- Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatumu Nthanje Road- Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2978880 | 2978880 | 2978880 | County treasury | N/A | 2978880 | N/A | 2978880 | 100% | 2978880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gwa Karobo Road- Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Qualified contractors aquired | Road | Maintenance Of Gwa Karobo Road- Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2823428 | 2823428 | 2823428 | County treasury | N/A | 2823428 | N/A | 2823428 | 100% | 2823428 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kwa David Kiangoma Road- Gaturi South Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kwa David Kiangoma Road- Gaturi South Ward |  | Gaturi South |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2998252 | 2998252 | 2998252 | County treasury | N/A | 2998252 | N/A | 2998252 | 100% | 2998252 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Kiangoma Wainara Road- Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Kiangoma Wainara Road- Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2685818 | 2685818 | 2685818 | County treasury | N/A | 2685818 | N/A | 2685818 | 100% | 2685818 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading & Gravelling Of Kang’ethia Ndunduri Road- Nginda Ward. | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading & Gravelling Of Kang’ethia Ndunduri Road- Nginda Ward. |  | Nginda |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 996254 | 996254 | 996254 | County treasury | N/A | 996254 | N/A | 996254 | 100% | 996254 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rugumu Primary To Mukongoro Road – Nginda Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rugumu Primary To Mukongoro Road – Nginda Ward |  | nginda |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 3684589 | 3684589 | 3684589 | County treasury | N/A | 3684589 | N/A | 3684589 | 100% | 3684589 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading & Gravelling of Rugumu Road. - Nginda Ward | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading & Gravelling of Rugumu Road. - Nginda Ward |  | nginda |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 998755 | 998755 | 998755 | County treasury | N/A | 998755 | N/A | 998755 | 100% | 998755 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Giekawa Ndatu Access & Bridge, Kyandundu Primary Gakurungu Access Road- Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Giekawa Ndatu Access & Bridge, Kyandundu Primary Gakurungu Access Road- Kithimu Ward |  | Kithimu Ward |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 3119240 | 3119240 | 3119240 | County treasury | N/A | 3119240 | N/A | 3119240 | 100% | 3119240 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kagumori Road- Nginda Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kagumori Road- Nginda Ward |  | Nginda |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2997974 | 2997974 | 2997974 | County treasury | N/A | 2997974 | N/A | 2997974 | 100% | 2997974 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Drifts & Culverts On Various Roads- Makima Ward | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Drifts & Culverts On Various Roads- Makima Ward |  | Makima |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2395481 | 2395481 | 2395481 | County treasury | N/A | 2395481 | N/A | 2395481 | 100% | 2395481 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathima Road- Gaturi South Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathima Road- Gaturi South Ward |  | Gaturi South |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 3133647 | 3133647 | 3133647 | County treasury | N/A | 3133647 | N/A | 3133647 | 100% | 3133647 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Mukangu Access Road- Ruguru Ngandori Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Mukangu Access Road- Ruguru Ngandori Ward |  | Ngandori |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2226504 | 2226504 | 2226504 | County treasury | N/A | 2226504 | N/A | 2226504 | 100% | 2226504 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njiru Mbossa Kwa Kariuki Njuma Road –Kagaari South Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njiru Mbossa Kwa Kariuki Njuma Road –Kagaari South Ward |  | Kagaari South |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2053780 | 2053780 | 2053780 | County treasury | N/A | 2053780 | N/A | 2053780 | 100% | 2053780 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading & Gravelling Of Nguviu Kithiga Road- Nginda Ward | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading & Gravelling Of Nguviu Kithiga Road- Nginda Ward |  | Nginda |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 2998368 | 2998368 | 2998368 | County treasury | N/A | 2998368 | N/A | 2998368 | 100% | 2998368 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 1. Opening And Dozing Of Makima Ward Roads. | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | 1. Opening And Dozing Of Makima Ward Roads. |  | Makima |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 4988580 | 4988580 | 4988580 | County treasury | N/A | 4988580 | N/A | 4988580 | 100% | 4988580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 2.Grading And Maintenance Of Makima Roads | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | 2.Grading And Maintenance Of Makima Roads |  | Makima |  | Road | Road | Road | 2022-01-07 | 22/05/2023 | 30/6/2023 | 30/6/2023 | 4988580 | 4988580 | 4988580 | County treasury | N/A | 4988580 | N/A | 4988580 | 100% | 4988580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A |  | N/A | N/A
| Road drainage systems(kiambere ward) | Culerts, cross drains, stormwater channels | To ensure efficient removal of surface water, reduce water erosion | Sufficient runoff | Road | Road drainage systems(kiambere ward) |  | kiambere ward |  | Road | Road | Road | 2022-01-07 | 2023-07-05 | 30/6/2023 | 30/6/2023 | 3988426 | 3988426 | 3988426 | County treasury | N/A | 3988426 | N/A | 3988426 | 100% | 3988426 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Machoinne road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Machoinne road |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-07-05 | 30/6/2023 | 30/6/2023 | 1997636 | 1997636 | 1997636 | County treasury | N/A | 1997636 | N/A | 1997636 | 100% | 1997636 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Remarking of Parking Spaces , Maitenance of roads in Embu Town | Procurement, Cleaning and remarking | To improve traffic organization | Optimized use of parking facilities | Road | Remarking of Parking Spaces , Maitenance of roads in Embu Town |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-09-06 | 30/6/2023 | 30/6/2023 | 4995586 | 4995586 | 4995586 | County treasury | N/A | 4995586 | N/A | 4995586 | 100% | 4995586 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of embu town lot 2 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of embu town lot 2 |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/06/2023 | 30/6/2023 | 30/6/2023 | 4549288 | 4549288 | 4549288 | County treasury | N/A | 4549288 | N/A | 4549288 | 100% | 4549288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of embu town lot 3 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of embu town lot 3 |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/06/2023 | 30/6/2023 | 30/6/2023 | 4199316 | 4199316 | 4199316 | County treasury | N/A | 4199316 | N/A | 4199316 | 100% | 4199316 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kanja ACK church road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kanja ACK church road |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/06/2023 | 30/6/2023 | 30/6/2023 | 1298314 | 1298314 | 1298314 | County treasury | N/A | 1298314 | N/A | 1298314 | 100% | 1298314 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Chainlink fencing moi stadium | Clearing, setting out fencing line and excavation installationand fixing chainlink | To secure a designated area and enhance safetty and access control | Durable and secure environment | Road | Chainlink fencing moi stadium |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/06/2023 | 30/6/2023 | 30/6/2023 | 799987 | 799987 | 799987 | County treasury | N/A | 799987 | N/A | 799987 | 100% | 799987 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of embu town lot 4 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of embu town lot 4 |  | Embu |  | Road | Road | Road | 2022-01-07 | 22/06/2023 | 30/6/2023 | 30/6/2023 | 3797608 | 3797608 | 3797608 | County treasury | N/A | 3797608 | N/A | 3797608 | 100% | 3797608 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| : Proposed Storm Water Drainage and Iron Sheets Fence at Miraa Trading Market (Phase 2) | Excavation, construction of drains and supply and installation of durable iron sheets | To improve drainage, accessibility and safety | Upgraded drainage system | Road | : Proposed Storm Water Drainage and Iron Sheets Fence at Miraa Trading Market (Phase 2) |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-07-07 | 30/6/2023 | 30/6/2023 | 3996136 | 3996136 | 3996136 | County treasury | N/A | 3996136 | N/A | 3996136 | 100% | 3996136 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Laying Of Cabro Blocks At Miraa Trading Market | Site preparation, levelling and compaction of base | To improve surface durabality, aesthetics | Smoother movement | Road | Proposed Laying Of Cabro Blocks At Miraa Trading Market |  | Embu |  | Road | Road | Road | 2022-01-07 | 2023-07-07 | 30/6/2023 | 30/6/2023 | 3995345 | 3995345 | 3995345 | County treasury | N/A | 3995345 | N/A | 3995345 | 100% | 3995345 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Floodlights At New Embu Market In Kirimari Ward | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Intallation Of Floodlights At New Embu Market In Kirimari Ward |  | Kirimari |  | Road | Road | Road | 2022-01-07 | 2023-07-07 | 30/6/2023 | 30/6/2023 | 877555 | 877555 | 877555 | County treasury | N/A | 877555 | N/A | 877555 | 100% | 877555 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2021/2022
| Upgrading To Bitumen Standards Of Kivwe Karingari Road Phase II | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Kivwe Karingari Road Phase II |  |  |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 27583076 | 27583076 | 27583076 | County Treasury | N/A | 27583076 | N/A | 27583076 | 100% | 27583076 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Mukuuri-Kanja Road Phase 3, Upgrading To Bitumen Standards Of Ack Muthege Church To Kirimiri Coffee Factory | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Mukuuri-Kanja Road Phase 3, Upgrading To Bitumen Standards Of Ack Muthege Church To Kirimiri Coffee Factory |  | Kirimari |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 38379723 | 38379723 | 38379723 | County Treasury | N/A | 38379723 | N/A | 38379723 | 100% | 38379723 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of A9 Majimbo Junction To Kamiu Primary Phase I | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of A9 Majimbo Junction To Kamiu Primary Phase I |  | Embu |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 20901490 | 20901490 | 20901490 | County Treasury | N/A | 20901490 | N/A | 20901490 | 100% | 20901490 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Kathageri-Kigumo Road Phase 2 | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Kathageri-Kigumo Road Phase 2 |  | Embu |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 16864300 | 16864300 | 16864300 | County Treasury | N/A | 16864300 | N/A | 16864300 | 100% | 16864300 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Ishiara Town Roads Phase 2 | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Ishiara Town Roads Phase 2 |  | Embu |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 17363739 | 17363739 | 17363739 | County Treasury | N/A | 17363739 | N/A | 17363739 | 100% | 17363739 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rehabilitation Of Kibugu Road | Site assessment, vent installation, vegetative cover and landscaping | To maintain and improve the condition of existing roads | A well rehabilitated road in good condition | Road | Rehabilitation Of Kibugu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 16625193 | 16625193 | 16625193 | County Treasury | N/A | 16625193 | N/A | 16625193 | 100% | 16625193 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Mwea/Makutano Town Roads | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Mwea/Makutano Town Roads |  | Mwea |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 15470103 | 15470103 | 15470103 | County Treasury | N/A | 15470103 | N/A | 15470103 | 100% | 15470103 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Mate-Nthangaiya Road Phase 3 | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Mate-Nthangaiya Road Phase 3 |  | Embu |  | Road | Road | Road | 2021-01-07 | 18/01/2022 | 30/6/2022 | 30/06/2022 | 15864233 | 15864233 | 15864233 | County Treasury | N/A | 15864233 | N/A | 15864233 | 100% | 15864233 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Runyenjes Kigaa(phase 3) | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Runyenjes Kigaa(phase 3) |  | Runyenjes |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 15646645 | 15646645 | 15646645 | County Treasury | N/A | 15646645 | N/A | 15646645 | 100% | 15646645 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Mbiruri road off Mbiruri Catholic Church | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Mbiruri road off Mbiruri Catholic Church |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 8000000 | 8000000 | 8000000 | County Treasury | N/A | 8000000 | N/A | 8000000 | 100% | 8000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Kyeni North | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Kyeni North |  | Kyeni |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4365544 | 4365544 | 4365544 | County Treasury | N/A | 4365544 | N/A | 4365544 | 100% | 4365544 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Ruguru Ngandori | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Ruguru Ngandori |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4230752 | 4230752 | 4230752 | County Treasury | N/A | 4230752 | N/A | 4230752 | 100% | 4230752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanduri Kang’ondu Minyuamai-Main Road-Kagaari South | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kanduri Kang’ondu Minyuamai-Main Road-Kagaari South |  | Kagaari |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4759016 | 4759016 | 4759016 | County Treasury | N/A | 4759016 | N/A | 4759016 | 100% | 4759016 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Makima | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Makima |  | Makima |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4788248 | 4788248 | 4788248 | County Treasury | N/A | 4788248 | N/A | 4788248 | 100% | 4788248 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Gaturi North | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Gaturi North |  | Gaturi North |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4351624 | 4351624 | 4351624 | County Treasury | N/A | 4351624 | N/A | 4351624 | 100% | 4351624 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Kiambere | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Kiambere |  | Kiambere |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4469016 | 4469016 | 4469016 | County Treasury | N/A | 4469016 | N/A | 4469016 | 100% | 4469016 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuinjeru-Kiathari Road-Kagaari North | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbuinjeru-Kiathari Road-Kagaari North |  | Kagaari North |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4757438 | 4757438 | 4757438 | County Treasury | N/A | 4757438 | N/A | 4757438 | 100% | 4757438 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading And Murramimg Of Nembure Roads-Gaturi South | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading And Murramimg Of Nembure Roads-Gaturi South |  | Gaturi North |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4366356 | 4366356 | 4366356 | County Treasury | N/A | 4366356 | N/A | 4366356 | 100% | 4366356 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Nthawa | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Nthawa |  | Nthawa |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4485546 | 4485546 | 4485546 | County Treasury | N/A | 4485546 | N/A | 4485546 | 100% | 4485546 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Mbeti South | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Mbeti South |  | Mbeti |  |  | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4887660 | 4887660 | 4887660 | County Treasury | N/A | 4887660 | N/A | 4887660 | 100% | 4887660 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Nginda | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Nginda |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4251864 | 4251864 | 4251864 | County Treasury | N/A | 4251864 | N/A | 4251864 | 100% | 4251864 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Mbeti North | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Mbeti North |  | Mbeti North |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4235740 | 4235740 | 4235740 | County Treasury | N/A | 4235740 | N/A | 4235740 | 100% | 4235740 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Mwea | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Mwea |  | Mwea |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4430968 | 4430968 | 4430968 | County Treasury | N/A | 4430968 | N/A | 4430968 | 100% | 4430968 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Kyeni South | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Kyeni South |  | Kyeni South |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4437000 | 4437000 | 4437000 | County Treasury | N/A | 4437000 | N/A | 4437000 | 100% | 4437000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Mavuria | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Mavuria |  | Mavuria |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4788538 | 4788538 | 4788538 | County Treasury | N/A | 4788538 | N/A | 4788538 | 100% | 4788538 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Evurore | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Evurore |  | evuvori |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4589772 | 4589772 | 4589772 | County Treasury | N/A | 4589772 | N/A | 4589772 | 100% | 4589772 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Muminji | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Muminji |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2022-07-02 | 30/6/2022 | 30/06/2022 | 4788248 | 4788248 | 4788248 | County Treasury | N/A | 4788248 | N/A | 4788248 | 100% | 4788248 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Kithimu | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Kithimu |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 4397328 | 4397328 | 4397328 | County Treasury | N/A | 4397328 | N/A | 4397328 | 100% | 4397328 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Kirimari | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Kirimari |  | Kirimari |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 4235624 | 4235624 | 4235624 | County Treasury | N/A | 4235624 | N/A | 4235624 | 100% | 4235624 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gicugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gicugu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1498024 | 1498024 | 1498024 | County Treasury | N/A | 1498024 | N/A | 1498024 | 100% | 1498024 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Muembu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Muembu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 993830 | 993830 | 993830 | County Treasury | N/A | 993830 | N/A | 993830 | 100% | 993830 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakundu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gakundu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3176776 | 3176776 | 3176776 | County Treasury | N/A | 3176776 | N/A | 3176776 | 100% | 3176776 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiamatogi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiamatogi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3.566,884.00 | 3.566,884.00 | 3.566,884.00 | County Treasury | N/A | 3.566,884.00 | N/A | 3.566,884.00 | 100% | 3.566,884.00 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gicovi-Kande-Ack Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gicovi-Kande-Ack Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3.098,534.00 | 3.098,534.00 | 3.098,534.00 | County Treasury | N/A | 3.098,534.00 | N/A | 3.098,534.00 | 100% | 3.098,534.00 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithimu Market Roads | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kithimu Market Roads |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1798580 | 1798580 | 1798580 | County Treasury | N/A | 1798580 | N/A | 1798580 | 100% | 1798580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St. Anthony Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of St. Anthony Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3996896 | 3996896 | 3996896 | County Treasury | N/A | 3996896 | N/A | 3996896 | 100% | 3996896 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njagairi Kwa Warivai Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Njagairi Kwa Warivai Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1998680 | 1998680 | 1998680 | County Treasury | N/A | 1998680 | N/A | 1998680 | 100% | 1998680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiawanja Muchui b | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiawanja Muchui |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1999260 | 1999260 | 1999260 | County Treasury | N/A | 1999260 | N/A | 1999260 | 100% | 1999260 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamavindi-Karurumo Secondary Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kamavindi-Karurumo Secondary Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2988972 | 2988972 | 2988972 | County Treasury | N/A | 2988972 | N/A | 2988972 | 100% | 2988972 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kangaru Roads | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kangaru Roads |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1999341 | 1999341 | 1999341 | County Treasury | N/A | 1999341 | N/A | 1999341 | 100% | 1999341 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Iveche Loop Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Iveche Loop Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2378406 | 2378406 | 2378406 | County Treasury | N/A | 2378406 | N/A | 2378406 | 100% | 2378406 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiangoso Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiangoso Access Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3133624 | 3133624 | 3133624 | County Treasury | N/A | 3133624 | N/A | 3133624 | 100% | 3133624 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kivwe – Muriri Road, Maintenance Of Rwagori And Mwana Wa Kavaru Road (Muminji Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kivwe – Muriri Road, Maintenance Of Rwagori And Mwana Wa Kavaru Road (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2499394 | 2499394 | 2499394 | County Treasury | N/A | 2499394 | N/A | 2499394 | 100% | 2499394 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Lower Muminji Roads | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Lower Muminji Roads |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3594608 | 3594608 | 3594608 | County Treasury | N/A | 3594608 | N/A | 3594608 | 100% | 3594608 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Koi-Mugo-Sunmoon Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Koi-Mugo-Sunmoon Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3499836 | 3499836 | 3499836 | County Treasury | N/A | 3499836 | N/A | 3499836 | 100% | 3499836 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance / Opening Of Itangi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance / Opening Of Itangi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2780080 | 2780080 | 2780080 | County Treasury | N/A | 2780080 | N/A | 2780080 | 100% | 2780080 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwanake Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwanake Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2497294 | 2497294 | 2497294 | County Treasury | N/A | 2497294 | N/A | 2497294 | 100% | 2497294 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamugere Tigerpower Road Maintenace Of Muchagori Kianyangi Muva (Gaturi North Ward | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kamugere Tigerpower Road Maintenace Of Muchagori Kianyangi Muva (Gaturi North Ward |  | Gaturi North |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2998600 | 2998600 | 2998600 | County Treasury | N/A | 2998600 | N/A | 2998600 | 100% | 2998600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiringi Bishop Kamuikiarurugi (Kangara) Road. (Kithimu Ward). | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiringi Bishop Kamuikiarurugi (Kangara) Road. (Kithimu Ward). |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 4494890 | 4494890 | 4494890 | County Treasury | N/A | 4494890 | N/A | 4494890 | 100% | 2998600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthiga Kwa Irene Road (Nginda Ward). | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Muthiga Kwa Irene Road (Nginda Ward). |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2411431 | 2411431 | 2411431 | County Treasury | N/A | 2411431 | N/A | 2411431 | 100% | 2411431 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Classic Kanginga Road Maintenance Of Mutema Uffo Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Classic Kanginga Road Maintenance Of Mutema Uffo Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3495080 | 3495080 | 3495080 | County Treasury | N/A | 3495080 | N/A | 3495080 | 100% | 3495080 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening And Grading / Maintenance Of Roads In (Evurori Ward). | Surveying, road opening, grading and shaping | To open new road corridors to improve connectivity between communities | Newly opened roads providing access to previously unreachable areas | Road | Opening And Grading / Maintenance Of Roads In (Evurori Ward). |  | evuvori |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3795143 | 3795143 | 3795143 | County Treasury | N/A | 3795143 | N/A | 3795143 | 100% | 3795143 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts (Evurori Ward). | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A proper installed culvert | Road | Installation Of Culverts (Evurori Ward). |  | evuvori |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1498140 | 1498140 | 1498140 | County Treasury | N/A | 1498140 | N/A | 1498140 | 100% | 1498140 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gangara-Rukuriri Road. (Muminji Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gangara-Rukuriri Road. (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 499032 | 499032 | 499032 | County Treasury | N/A | 499032 | N/A | 499032 | 100% | 499032 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatunduri Kiringa Coffee Factory Road. (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gatunduri Kiringa Coffee Factory Road. (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1484858 | 1484858 | 1484858 | County Treasury | N/A | 1484858 | N/A | 1484858 | 100% | 1484858 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Marcarelo Township Roads. (Mbeti South Ward). | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Marcarelo Township Roads. (Mbeti South Ward). |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2435188 | 2435188 | 2435188 | County Treasury | N/A | 2435188 | N/A | 2435188 | 100% | 2435188 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kariari Junction – Kwa Njue Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kariari Junction – Kwa Njue Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 3361750 | 3361750 | 3361750 | County Treasury | N/A | 3361750 | N/A | 3361750 | 100% | 3361750 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndagari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndagari Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 2126222 | 2126222 | 2126222 | County Treasury | N/A | 2126222 | N/A | 2126222 | 100% | 2126222 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kavaruka Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kavaruka Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3447543 | 3447543 | 3447543 | County Treasury | N/A | 3447543 | N/A | 3447543 | 100% | 3447543 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Kamama Bridge (Ruguru Ngandori Ward) | Site preparation, excavation and construction | To control the flow of water and mitigate flooding | A well constructed bridge and controled water | Road | Construction Of Kamama Bridge (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 4499709 | 4499709 | 4499709 | County Treasury | N/A | 4499709 | N/A | 4499709 | 100% | 4499709 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichaki Tarmac Kwa Marigu (Kagaari South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gichaki Tarmac Kwa Marigu (Kagaari South Ward) |  | Kagaari South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3196461 | 3196461 | 3196461 | County Treasury | N/A | 3196461 | N/A | 3196461 | 100% | 3196461 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Gicegori Kwa Gicatha Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenace Of Gicegori Kwa Gicatha Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3364580 | 3364580 | 3364580 | County Treasury | N/A | 3364580 | N/A | 3364580 | 100% | 3364580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwithi Gicerori Road (Nginda Ward | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwithi Gicerori Road (Nginda Ward |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3450513 | 3450513 | 3450513 | County Treasury | N/A | 3450513 | N/A | 3450513 | 100% | 3450513 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambevo Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kambevo Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2494824 | 2494824 | 2494824 | County Treasury | N/A | 2494824 | N/A | 2494824 | 100% | 2494824 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mwalimu Kwa Njeru Bossa Elijah (Gaturi South) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Mwalimu Kwa Njeru Bossa Elijah (Gaturi South) |  | Gaturi South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2500009 | 2500009 | 2500009 | County Treasury | N/A | 2500009 | N/A | 2500009 | 100% | 2500009 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiamakumi – Bethel-Rianguu Road (Mbeti South) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiamakumi – Bethel-Rianguu Road (Mbeti South) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3748726 | 3748726 | 3748726 | County Treasury | N/A | 3748726 | N/A | 3748726 | 100% | 3748726 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Gatumu Nthano Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Gatumu Nthano Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3282046 | 3282046 | 3282046 | County Treasury | N/A | 3282046 | N/A | 3282046 | 100% | 3282046 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimangaru Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kimangaru Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3350950 | 3350950 | 3350950 | County Treasury | N/A | 3350950 | N/A | 3350950 | 100% | 3350950 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Bishop Kathii Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Bishop Kathii Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3209007 | 3209007 | 3209007 | County Treasury | N/A | 3209007 | N/A | 3209007 | 100% | 3209007 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Bishop Muriithi Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Bishop Muriithi Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1398612 | 1398612 | 1398612 | County Treasury | N/A | 1398612 | N/A | 1398612 | 100% | 1398612 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatumu – Kismayu Road (Mbeti South) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gatumu – Kismayu Road (Mbeti South) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3776531 | 3776531 | 3776531 | County Treasury | N/A | 3776531 | N/A | 3776531 | 100% | 3776531 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatothia – Ngiiri Road, Murraming And Culverts At Micegethiu Road (Muminji Ward) | Debris clearing, excavation, murraming and construction of culverts | To improve the quality of the road and construct a all-weathered road | A fully functional road in good condition | Road | Maintenance Of Gatothia – Ngiiri Road, Murraming And Culverts At Micegethiu Road (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1997984 | 1997984 | 1997984 | County Treasury | N/A | 1997984 | N/A | 1997984 | 100% | 1997984 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamuthatha Kwa Mathara Kanindi Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kamuthatha Kwa Mathara Kanindi Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2796644 | 2796644 | 2796644 | County Treasury | N/A | 2796644 | N/A | 2796644 | 100% | 2796644 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Githumbi Fr. Macharia Mwondo Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Githumbi Fr. Macharia Mwondo Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2498814 | 2498814 | 2498814 | County Treasury | N/A | 2498814 | N/A | 2498814 | 100% | 2498814 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Catholic Church Road (Kirimari Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Catholic Church Road (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 996469 | 996469 | 996469 | County Treasury | N/A | 996469 | N/A | 996469 | 100% | 996469 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makimei Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Makimei Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2475440 | 2475440 | 2475440 | County Treasury | N/A | 2475440 | N/A | 2475440 | 100% | 2475440 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kasarani Rupingazi Road (Mbeti North) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kasarani Rupingazi Road (Mbeti North) |  | Mbeti North |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1986987 | 1986987 | 1986987 | County Treasury | N/A | 1986987 | N/A | 1986987 | 100% | 1986987 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening Of Ishmael-Mavirari – Kwa Nthiga (Mbeti South Ward) | Site assessment, clearing and constrution | open new road corridors connecting new towns | A new road connecting new town | Road | Opening Of Ishmael-Mavirari – Kwa Nthiga (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1986094 | 1986094 | 1986094 | County Treasury | N/A | 1986094 | N/A | 1986094 | 100% | 1986094 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngaari-Kiangi-Nduuri Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ngaari-Kiangi-Nduuri Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2978509 | 2978509 | 2978509 | County Treasury | N/A | 2978509 | N/A | 2978509 | 100% | 2978509 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening Of Mbita South Location (Mbeti South) | Site assessment, clearing and constrution | open new road corridors connecting new towns | A new road connecting new town | Road | Opening Of Mbita South Location (Mbeti South) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1999376 | 1999376 | 1999376 | County Treasury | N/A | 1999376 | N/A | 1999376 | 100% | 1999376 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Redeemed Kamangara Kwa Maina Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Redeemed Kamangara Kwa Maina Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2998020 | 2998020 | 2998020 | County Treasury | N/A | 2998020 | N/A | 2998020 | 100% | 2998020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Allomano Road (Kithimu Ward | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Allomano Road (Kithimu Ward |  | Kithimu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2444828 | 2444828 | 2444828 | County Treasury | N/A | 2444828 | N/A | 2444828 | 100% | 2444828 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigumo Kiriari Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kigumo Kiriari Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1584618 | 1584618 | 1584618 | County Treasury | N/A | 1584618 | N/A | 1584618 | 100% | 1584618 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathima Ciiri Road (Gaturi South Ward | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathima Ciiri Road (Gaturi South Ward |  | Gaturi South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2996872 | 2996872 | 2996872 | County Treasury | N/A | 2996872 | N/A | 2996872 | 100% | 2996872 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ketheru Nembure Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ketheru Nembure Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2995178 | 2995178 | 2995178 | County Treasury | N/A | 2995178 | N/A | 2995178 | 100% | 2995178 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Mortuary Gakwegori Road (Mbeti North Ward) | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading And Murraming Of Mortuary Gakwegori Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 999050 | 999050 | 999050 | County Treasury | N/A | 999050 | N/A | 999050 | 100% | 999050 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Kyeni South Roads (Kyeni South Ward) | Site preparation and gravelling | To improve road accessibility and reduce travel time | A well-gravelled road in good contion | Road | Gravelling Of Kyeni South Roads (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3467862 | 3467862 | 3467862 | County Treasury | N/A | 3467862 | N/A | 3467862 | 100% | 3467862 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening, Grading And Murraming Of Gicuvirori Road | Site survey, clearing and opening, grading and murraming | To provide an all-weather road surface suitable for motorized and non-motorized transport | Improved accessibility and transportation efficiency | Road | Opening, Grading And Murraming Of Gicuvirori Road |  | Embu |  | Road | Road |  | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1182104 | 1182104 | 1182104 | County Treasury | N/A | 1182104 | N/A | 1182104 | 100% | 1182104 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Mugoya Loop Road | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading And Murraming Of Mugoya Loop Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1488744 | 1488744 | 1488744 | County Treasury | N/A | 1488744 | N/A | 1488744 | 100% | 1488744 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Itabua Nduva Loop Roads | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading And Murraming Of Itabua Nduva Loop Roads |  | Embu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1186390 | 1186390 | 1186390 | County Treasury | N/A | 1186390 | N/A | 1186390 | 100% | 1186390 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbukori Road (Gaturi South) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbukori Road (Gaturi South) |  | Gaturi South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1999202 | 1999202 | 1999202 | County Treasury | N/A | 1999202 | N/A | 1999202 | 100% | 1999202 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mindari Njagairi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mindari Njagairi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1997288 | 1997288 | 1997288 | County Treasury | N/A | 1997288 | N/A | 1997288 | 100% | 1997288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading Of Junction-Kamuthigo Road (Evurore Ward) | Site preparation, grading | To regrade and smoothen existing road surface for improved riding quality | Regraded and compacted road surface | Road | Grading Of Junction-Kamuthigo Road (Evurore Ward) |  | evuvori |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1954948 | 1954948 | 1954948 | County Treasury | N/A | 1954948 | N/A | 1954948 | 100% | 1954948 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kandete Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kandete Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1992532 | 1992532 | 1992532 | County Treasury | N/A | 1992532 | N/A | 1992532 | 100% | 1992532 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming And Grading Of Gitogoro-Gitumbi Ack-Kianjokoma Road (Gaturi North Ward) | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Murraming And Grading Of Gitogoro-Gitumbi Ack-Kianjokoma Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3498478 | 3498478 | 3498478 | County Treasury | N/A | 3498478 | N/A | 3498478 | 100% | 3498478 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming And Grading Of Kiegucu-Kiriri-Itonguri Road (Gaturi North Ward) | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Murraming And Grading Of Kiegucu-Kiriri-Itonguri Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2998426 | 2998426 | 2998426 | County Treasury | N/A | 2998426 | N/A | 2998426 | 100% | 2998426 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading And Murraming Of Koi Mugo Roads Kirimari (Kirimari Ward) | Site preparation, grading works, murraming | Improved road surface and year-round accessility | Improved and well-graded murram road | Road | Grading And Murraming Of Koi Mugo Roads Kirimari (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1998796 | 1998796 | 1998796 | County Treasury | N/A | 1998796 | N/A | 1998796 | 100% | 1998796 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ruma Kangichu Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ruma Kangichu Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1299154 | 1299154 | 1299154 | County Treasury | N/A | 1299154 | N/A | 1299154 | 100% | 1299154 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing And Maintenance Of Roads (Nthawa Ward) | Site inspection, clearing, dozing and reshaping | To maintain and level existing roads for improved surface smoothness and drainage | A well-maintained and leveled road | Road | Dozing And Maintenance Of Roads (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 4898680 | 4898680 | 4898680 | County Treasury | N/A | 4898680 | N/A | 4898680 | 100% | 4898680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nyaga Kagumori Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Nyaga Kagumori Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 1687179 | 1687179 | 1687179 | County Treasury | N/A | 1687179 | N/A | 1687179 | 100% | 1687179 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuvi Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbuvi Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 2498930 | 2498930 | 2498930 | County Treasury | N/A | 2498930 | N/A | 2498930 | 100% | 2498930 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwalimu – Rupingazi Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwalimu – Rupingazi Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3409971 | 3409971 | 3409971 | County Treasury | N/A | 3409971 | N/A | 3409971 | 100% | 3409971 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Roads In Mbeti South (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Roads In Mbeti South (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2021-08-12 | 30/6/2022 | 30/06/2022 | 3998288 | 3998288 | 3998288 | County Treasury | N/A | 3998288 | N/A | 3998288 | 100% | 3998288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kaseve-Masimba –Lulwa Road, Maintenance Of Wachoro Secondary – Karuku Market | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kaseve-Masimba –Lulwa Road, Maintenance Of Wachoro Secondary – Karuku Market |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2183311 | 2183311 | 2183311 | County Treasury | N/A | 2183311 | N/A | 2183311 | 100% | 2183311 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbiti Gachuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbiti Gachuki Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 3521215 | 3521215 | 3521215 | County Treasury | N/A | 3521215 | N/A | 3521215 | 100% | 3521215 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads In Mavuria Ward | Site preparation, grading | To ensure that the roads are in good condition for motoring | A well-graded road | Road | Grading Of Roads In Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1997520 | 1997520 | 1997520 | County Treasury | N/A | 1997520 | N/A | 1997520 | 100% | 1997520 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening/Maintenance Of Roads In Mavuria Ward | Site assessment, bush clearing, cleaning | To maintain and improve the condition of existing roads | A well maintained road | Road | Opening/Maintenance Of Roads In Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1996940 | 1996940 | 1996940 | County Treasury | N/A | 1996940 | N/A | 1996940 | 100% | 1996940 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwalimu Njiru Kiruari/Ceaser Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwalimu Njiru Kiruari/Ceaser Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1399424 | 1399424 | 1399424 | County Treasury | N/A | 1399424 | N/A | 1399424 | 100% | 1399424 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening And Grading Of Mwangaza Nguyari Road | Surveying, road opening, grading and shaping | To open new road corridors to improve connectivity between communities | Newly opened roads providing access to previously unreachable areas | Road | Opening And Grading Of Mwangaza Nguyari Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1996986 | 1996986 | 1996986 | County Treasury | N/A | 1996986 | N/A | 1996986 | 100% | 1996986 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening/Maintenance Of Roads In Kiambere | Site assessment, bush clearing, cleaning | To maintain and improve the condition of existing roads | A well maintained road | Road | Opening/Maintenance Of Roads In Kiambere |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2086057 | 2086057 | 2086057 | County Treasury | N/A | 2086057 | N/A | 2086057 | 100% | 2086057 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Njiru – Thuci Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Njiru – Thuci Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2989482 | 2989482 | 2989482 | County Treasury | N/A | 2989482 | N/A | 2989482 | 100% | 2989482 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jeremiah Nyaga Gakwegori | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Jeremiah Nyaga Gakwegori |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1494486 | 1494486 | 1494486 | County Treasury | N/A | 1494486 | N/A | 1494486 | 100% | 1494486 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mivutiri Gatumbi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mivutiri Gatumbi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1990792 | 1990792 | 1990792 | County Treasury | N/A | 1990792 | N/A | 1990792 | 100% | 1990792 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening/Maintenance Of Roads In Makima Ward | Site assessment, bush clearing, cleaning | To maintain and improve the condition of existing roads | A well maintained road | Road | Opening/Maintenance Of Roads In Makima Ward |  | Makima |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 3978568 | 3978568 | 3978568 | County Treasury | N/A | 3978568 | N/A | 3978568 | 100% | 3978568 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St.Kizito Kinyaga Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of St.Kizito Kinyaga Primary School Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1298388 | 1298388 | 1298388 | County Treasury | N/A | 1298388 | N/A | 1298388 | 100% | 1298388 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiadongo Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiadongo Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-02-02 | 30/6/2022 | 30/06/2022 | 1978844 | 1978844 | 1978844 | County Treasury | N/A | 1978844 | N/A | 1978844 | 100% | 1978844 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Upper Ntheuni Drift – Mwea Ward | Site preparation, drilling, construction | To construct a stable, safe, and properly supported drift of specified dimensions | A fully excavated and supported drift | Road | Construction Of Upper Ntheuni Drift – Mwea Ward |  | Mwea |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1199440 | 1199440 | 1199440 | County Treasury | N/A | 1199440 | N/A | 1199440 | 100% | 1199440 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitaraka – Twenze Road, Maintenance Of Kwa Kanawe –Kaseveni Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gitaraka – Twenze Road, Maintenance Of Kwa Kanawe –Kaseveni Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1775554 | 1775554 | 1775554 | County Treasury | N/A | 1775554 | N/A | 1775554 | 100% | 1775554 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts – Evurore | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A well installed culvert | Road | Installation Of Culverts – Evurore |  | evuvori |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 992612 | 992612 | 992612 | County Treasury | N/A | 992612 | N/A | 992612 | 100% | 992612 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Consultancy Services On Road Survey For Makima Ward | Procurement, survey | To ensure that the new road site is well examined | A full documented report on the site | Road | Consultancy Services On Road Survey For Makima Ward |  | Makima |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1490000 | 1490000 | 1490000 | County Treasury | N/A | 1490000 | N/A | 1490000 | 100% | 1490000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakwegori Kangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gakwegori Kangaru Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1493581 | 1493581 | 1493581 | County Treasury | N/A | 1493581 | N/A | 1493581 | 100% | 1493581 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Kathesu-Ndudani Bridge (Repair Of Drift) – Makima Ward | debris clearing, excavation, and construction | To ensure that the roads are safe to cross using drifts and bridges | A well constructed bridge and controled water | Road | Construction Of Kathesu-Ndudani Bridge (Repair Of Drift) – Makima Ward |  | Makima |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2316972 | 2316972 | 2316972 | County Treasury | N/A | 2316972 | N/A | 2316972 | 100% | 2316972 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Mango’te Drift | Site preparation, drilling, construction | To construct a stable, safe, and properly supported drift of specified dimensions | A fully excavated and supported drift | Road | Construction Of Mango’te Drift |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1384600 | 1384600 | 1384600 | County Treasury | N/A | 1384600 | N/A | 1384600 | 100% | 1384600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Malikini – Kasioni Road. Maintenance Of Ngandi – Mbonzuki – Muthyonzya Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Malikini – Kasioni Road. Maintenance Of Ngandi – Mbonzuki – Muthyonzya Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2799590 | 2799590 | 2799590 | County Treasury | N/A | 2799590 | N/A | 2799590 | 100% | 2799590 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimbu Kwa Sub Area Road (Runyenjes Central) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kimbu Kwa Sub Area Road (Runyenjes Central) |  | Runyenjes |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2095693 | 2095693 | 2095693 | County Treasury | N/A | 2095693 | N/A | 2095693 | 100% | 2095693 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngomi Road (Kyeni South) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ngomi Road (Kyeni South) |  | Kyeni South |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1986947 | 1986947 | 1986947 | County Treasury | N/A | 1986947 | N/A | 1986947 | 100% | 1986947 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Munyutu Culverts (Kagaari North) | Site preparation, drilling, construction | To construct a stable and a well supported bridge | A well supported bridge which call sustain all-weather seasons | Road | Construction Of Munyutu Culverts (Kagaari North) |  | Kagaari North |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 4499657 | 4499657 | 4499657 | County Treasury | N/A | 4499657 | N/A | 4499657 | 100% | 4499657 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiang’ombe Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiang’ombe Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2879155 | 2879155 | 2879155 | County Treasury | N/A | 2879155 | N/A | 2879155 | 100% | 2879155 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Rupinganzi South Ngariama Foot Bridge – Mbeti South | Site preparation, drilling, construction | To construct a stable, safe, and properly supported bridge of specified dimensions | A well excavated bridge | Road | Construction Of Rupinganzi South Ngariama Foot Bridge – Mbeti South |  | Mbeti South |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 3287562 | 3287562 | 3287562 | County Treasury | N/A | 3287562 | N/A | 3287562 | 100% | 3287562 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kangari Mbiruri Road (Runyenjes Central) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kangari Mbiruri Road (Runyenjes Central) |  | Runyenjes |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1990281 | 1990281 | 1990281 | County Treasury | N/A | 1990281 | N/A | 1990281 | 100% | 1990281 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads In Runyenjes Central | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Various Roads In Runyenjes Central |  | Runyenjes |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 4999542 | 4999542 | 4999542 | County Treasury | N/A | 4999542 | N/A | 4999542 | 100% | 4999542 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Muembu Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Muembu Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 986493 | 986493 | 986493 | County Treasury | N/A | 986493 | N/A | 986493 | 100% | 986493 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Machaga Road (Nginda Ward | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Machaga Road (Nginda Ward |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 2489302 | 2489302 | 2489302 | County Treasury | N/A | 2489302 | N/A | 2489302 | 100% | 2489302 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Murova Njeruri Road (Runyenjes Central | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Murova Njeruri Road (Runyenjes Central |  |  |  | Road | Road | Road | 2021-01-07 | 2022-09-02 | 30/6/2022 | 30/06/2022 | 1985427 | 1985427 | 1985427 | County Treasury | N/A | 1985427 | N/A | 1985427 | 100% | 1985427 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigaa-Gicagi Road, Kirigori Road And Karuriri-Mutitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kigaa-Gicagi Road, Kirigori Road And Karuriri-Mutitu Road |  | Runyenjes |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 4074964 | 4074964 | 4074964 | County Treasury | N/A | 4074964 | N/A | 4074964 | 100% | 4074964 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbiruri Catholic Church To Kathuriri Shopping Centre Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbiruri Catholic Church To Kathuriri Shopping Centre Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 1999144 | 1999144 | 1999144 | County Treasury | N/A | 1999144 | N/A | 1999144 | 100% | 1999144 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing Of Kagaari South Roads | Cutting, removal of excess soil, | To restore the road to a smooth and uniform profile | A smooth, drivable road surface with improved alignment | Road | Dozing Of Kagaari South Roads |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 2996860 | 2996860 | 2996860 | County Treasury | N/A | 2996860 | N/A | 2996860 | 100% | 2996860 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutunduri Nickomaria School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mutunduri Nickomaria School Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 1998100 | 1998100 | 1998100 | County Treasury | N/A | 1998100 | N/A | 1998100 | 100% | 1998100 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithunguthia Market Kwa Chief Road, Installation Of Culverts At Rukanga, Maintenance Of Tenri Karuga E.A.P.C Road | Clearing debris, installation of culverts | To rehabilitate and maintain existing culverts to restore full functionality | Fully functional culverts capable of handling designed stormwater flow | Road | Maintenance Of Kithunguthia Market Kwa Chief Road, Installation Of Culverts At Rukanga, Maintenance Of Tenri Karuga E.A.P.C Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 3895790 | 3895790 | 3895790 | County Treasury | N/A | 3895790 | N/A | 3895790 | 100% | 3895790 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Slip Road Connecting A9 At Issac Hotel To Kibugu Road | Cleaning, drainage maintenance and repair of damaged areas | To improve the overall surface condition and drivability of the road | A smooth, drivable road surface with improved alignment | Road | Maintenance Of Slip Road Connecting A9 At Issac Hotel To Kibugu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 1976918 | 1976918 | 1976918 | County Treasury | N/A | 1976918 | N/A | 1976918 | 100% | 1976918 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tarmac Kwa Subchief Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tarmac Kwa Subchief Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 3977385 | 3977385 | 3977385 | County Treasury | N/A | 3977385 | N/A | 3977385 | 100% | 3977385 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gicovi Councillor Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gicovi Councillor Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 498800 | 498800 | 498800 | County Treasury | N/A | 498800 | N/A | 498800 | 100% | 498800 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Kabogo Road, Installation Of Culverts At Nguruka, Maintenance Of Kathugu Road | Clearing debris, installation of culverts | To rehabilitate and maintain existing culverts to restore full functionality | Fully functional culverts capable of handling designed stormwater flow | Road | Maintenance Of Kwa Kabogo Road, Installation Of Culverts At Nguruka, Maintenance Of Kathugu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 3895396 | 3895396 | 3895396 | County Treasury | N/A | 3895396 | N/A | 3895396 | 100% | 3895396 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndiuri Muganjuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndiuri Muganjuki Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 17/2/2022 | 30/6/2022 | 30/06/2022 | 1998680 | 1998680 | 1998680 | County Treasury | N/A | 1998680 | N/A | 1998680 | 100% | 1998680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kevote-Nyange – Karue Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kevote-Nyange – Karue Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 2094612 | 2094612 | 2094612 | County Treasury | N/A | 2094612 | N/A | 2094612 | 100% | 2094612 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Maintenance Of Roads In Muminji Ward | Cutting high spots, grading, and clearing roadside vegetationgs | To restore the road surface to uniform, smooth, and safe condition | Smooth, stable, well-drained road surface | Road | Grading/Maintenance Of Roads In Muminji Ward |  | Muminji |  | Road | Road | Road | 2021-01-07 | 2022-09-03 | 30/6/2022 | 30/06/2022 | 1597900 | 1597900 | 1597900 | County Treasury | N/A | 1597900 | N/A | 1597900 | 100% | 1597900 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Maintenance Of Roads Phase 2 In Mavuria Ward | Cutting high spots, grading, and clearing roadside vegetationgs | To restore the road surface to uniform, smooth, and safe condition | Smooth, stable, well-drained road surface | Road | Grading/Maintenance Of Roads Phase 2 In Mavuria Ward |  | Mavuria |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1986848 | 1986848 | 1986848 | County Treasury | N/A | 1986848 | N/A | 1986848 | 100% | 1986848 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts At Mathai sky Girls Road, Installation Of Culverts At Gwa Sofia Kamburu Road, Installation Of Culverts At Kambora Road | Site preparation, culverts, headwalls and wing walls construction | To improve road drainage and prevent ccumulation and flooding | A well installed culvert | Road | Installation Of Culverts At Mathai sky Girls Road, Installation Of Culverts At Gwa Sofia Kamburu Road, Installation Of Culverts At Kambora Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 2696420 | 2696420 | 2696420 | County Treasury | N/A | 2696420 | N/A | 2696420 | 100% | 2696420 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kavutiri – Kavari Gitongoro Road, Maintenance Of Gatura Gituri Kianjuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kavutiri – Kavari Gitongoro Road, Maintenance Of Gatura Gituri Kianjuki Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 4497320 | 4497320 | 4497320 | County Treasury | N/A | 4497320 | N/A | 4497320 | 100% | 4497320 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwanzo Market – Mwea Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwanzo Market – Mwea Market Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 996923 | 996923 | 996923 | County Treasury | N/A | 996923 | N/A | 996923 | 100% | 996923 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Maintenance Of Selected Roads In Makima Ward | Cutting high spots, grading, and clearing roadside vegetationgs | To restore the road surface to uniform, smooth, and safe condition | Smooth, stable, well-drained road surface | Road | Grading/Maintenance Of Selected Roads In Makima Ward |  | Makima |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1994852 | 1994852 | 1994852 | County Treasury | N/A | 1994852 | N/A | 1994852 | 100% | 1994852 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Catholic Mugoya Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Catholic Mugoya Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1492004 | 1492004 | 1492004 | County Treasury | N/A | 1492004 | N/A | 1492004 | 100% | 1492004 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndamunge Director Road, Maintenance Of Irangi Utukuvi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndamunge Director Road, Maintenance Of Irangi Utukuvi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1993077 | 1993077 | 1993077 | County Treasury | N/A | 1993077 | N/A | 1993077 | 100% | 1993077 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening/Maintenance Of Roads Phase 2 N Mavuia Ward | Clearing vegetation, grading, repair of patholes | To clear and open the road corridor for unrestricted access | A fully opened and accessible roadway suitable for vehicle movement | Road | Opening/Maintenance Of Roads Phase 2 N Mavuia Ward |  | Mavuria |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1996940 | 1996940 | 1996940 | County Treasury | N/A | 1996940 | N/A | 1996940 | 100% | 1996940 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Igabitika Ena Road, Maintenance Of Ack Nginda Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Igabitika Ena Road, Maintenance Of Ack Nginda Road |  | Nginda |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 3991015 | 3991015 | 3991015 | County Treasury | N/A | 3991015 | N/A | 3991015 | 100% | 3991015 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichiche Gichera Gitungu Road, Maintenance Of Gicagi Kiaragana Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gichiche Gichera Gitungu Road, Maintenance Of Gicagi Kiaragana Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 4486880 | 4486880 | 4486880 | County Treasury | N/A | 4486880 | N/A | 4486880 | 100% | 4486880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makengi Nguire Gichagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Makengi Nguire Gichagi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-04-03 | 30/6/2022 | 30/06/2022 | 1996360 | 1996360 | 1996360 | County Treasury | N/A | 1996360 | N/A | 1996360 | 100% | 1996360 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiuga Coffee Factory Road, Maintenance Of Ena Mutitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiuga Coffee Factory Road, Maintenance Of Ena Mutitu Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 3898354 | 3898354 | 3898354 | County Treasury | N/A | 3898354 | N/A | 3898354 | 100% | 3898354 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gwa Njeru Wambui | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gwa Njeru Wambui |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2795136 | 2795136 | 2795136 | County Treasury | N/A | 2795136 | N/A | 2795136 | 100% | 2795136 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mainteance Of Kanguri Gekawa Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mainteance Of Kanguri Gekawa Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2997324 | 2997324 | 2997324 | County Treasury | N/A | 2997324 | N/A | 2997324 | 100% | 2997324 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiangondi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiangondi Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 998180 | 998180 | 998180 | County Treasury | N/A | 998180 | N/A | 998180 | 100% | 998180 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mainteance Of Gakui Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mainteance Of Gakui Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 3795520 | 3795520 | 3795520 | County Treasury | N/A | 3795520 | N/A | 3795520 | 100% | 3795520 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kavaruko Kwa Waweru | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kavaruko Kwa Waweru |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2998600 | 2998600 | 2998600 | County Treasury | N/A | 2998600 | N/A | 2998600 | 100% | 2998600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbiruri Catholic Church To Kathuri Shopping Centre Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mbiruri Catholic Church To Kathuri Shopping Centre Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 1996638 | 1996638 | 1996638 | County Treasury | N/A | 1996638 | N/A | 1996638 | 100% | 1996638 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mainteance Of Kiambogo Kathangari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mainteance Of Kiambogo Kathangari Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2872006 | 2872006 | 2872006 | County Treasury | N/A | 2872006 | N/A | 2872006 | 100% | 2872006 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mukangu Kiriari (Village) Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mukangu Kiriari (Village) Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 3090240 | 3090240 | 3090240 | County Treasury | N/A | 3090240 | N/A | 3090240 | 100% | 3090240 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tarmac To Kariavu Junction | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tarmac To Kariavu Junction |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 1973044 | 1973044 | 1973044 | County Treasury | N/A | 1973044 | N/A | 1973044 | 100% | 1973044 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kang’aru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kang’aru Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2798268 | 2798268 | 2798268 | County Treasury | N/A | 2798268 | N/A | 2798268 | 100% | 2798268 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathuniri Primary Forest Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathuniri Primary Forest Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2697000 | 2697000 | 2697000 | County Treasury | N/A | 2697000 | N/A | 2697000 | 100% | 2697000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiawanja Acess Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiawanja Acess Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-05-04 | 30/6/2022 | 30/06/2022 | 2997115 | 2997115 | 2997115 | County Treasury | N/A | 2997115 | N/A | 2997115 | 100% | 2997115 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mivukori Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mivukori Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-12-05 | 30/6/2022 | 30/06/2022 | 2496088 | 2496088 | 2496088 | County Treasury | N/A | 2496088 | N/A | 2496088 | 100% | 2496088 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karambari-Gitua Road And Maintenance Of Mbarwari-Kandoma-Kivwe And Kivutiri Roads | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karambari-Gitua Road And Maintenance Of Mbarwari-Kandoma-Kivwe And Kivutiri Roads |  | Embu |  | Road | Road | Road | 2021-01-07 | 2022-12-05 | 30/6/2022 | 30/06/2022 | 1597900 | 1597900 | 1597900 | County Treasury | N/A | 1597900 | N/A | 1597900 | 100% | 1597900 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kyeni Central Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kyeni Central Road |  | Kyeni Central |  | Road | Road | Road | 2021-01-07 | 2022-12-05 | 30/6/2022 | 30/06/2022 | 1998312 | 1998312 | 1998312 | County Treasury | N/A | 1998312 | N/A | 1998312 | 100% | 1998312 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening And Grading Of Kilia-Masinga Dam Road And Opening And Grading Of Iria Itune-Warui Nguti Road | Clearing vegetation, grading, repair of patholes | To clear and open road alignenent for unobstructed access | A fully opened and accessible roadway suitable for vehicle movement | Road | Opening And Grading Of Kilia-Masinga Dam Road And Opening And Grading Of Iria Itune-Warui Nguti Road |  | Embu |  | Road | Road | Road | 2021-01-07 | 27/5/2022 | 30/6/2022 | 30/06/2022 | 2994389 | 2994389 | 2994389 | County Treasury | N/A | 2994389 | N/A | 2994389 | 100% | 2994389 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2020/2021
| Maintenance Of Mbui Njeru Kandongo Road E4207 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbui Njeru Kandongo Road E4207 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5986992 | 5986992 | 5986992 | County treasury | N/A | 5986992 | N/A | 5986992 | 100% | 5986992 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurumo - Kaveti- Kathunguri Murari Road G48682 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurumo - Kaveti- Kathunguri Murari Road G48682 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 6124568 | 6124568 | 6124568 | County treasury | N/A | 6124568 | N/A | 6124568 | 100% | 6124568 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Keria-Gica Road (G48614) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Keria-Gica Road (G48614) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 6633460 | 6633460 | 6633460 | County treasury | N/A | 6633460 | N/A | 6633460 | 100% | 6633460 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Munathiri – Gataka Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Munathiri – Gataka Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5970868 | 5970868 | 5970868 | County treasury | N/A | 5970868 | N/A | 5970868 | 100% | 5970868 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutuobare Market - Shauri - Riacina Primary School -Mutuobare Secondary School Road E4183 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutuobare Market - Shauri - Riacina Primary School -Mutuobare Secondary School Road E4183 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 6257620 | 6257620 | 6257620 | County treasury | N/A | 6257620 | N/A | 6257620 | 100% | 6257620 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamumu -Uvarire - Kuui - Kune Road (G48183) - 15.2km | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamumu -Uvarire - Kuui - Kune Road (G48183) - 15.2km |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5698790 | 5698790 | 5698790 | County treasury | N/A | 5698790 | N/A | 5698790 | 100% | 5698790 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Siakago-Makunguru- Gitivuri- Kanthenge – Witwa - Maathai Kamunge Rukira Road G48133 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Siakago-Makunguru- Gitivuri- Kanthenge – Witwa - Maathai Kamunge Rukira Road G48133 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 4558800 | 4558800 | 4558800 | County treasury | N/A | 4558800 | N/A | 4558800 | 100% | 4558800 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyariri - Muraru Road G48053 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanyariri - Muraru Road G48053 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5959616 | 5959616 | 5959616 | County treasury | N/A | 5959616 | N/A | 5959616 | 100% | 5959616 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamukwego-Kwamutheri-Ack Gatituri-Karurina-Munyi Karukungu Loop | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamukwego-Kwamutheri-Ack Gatituri-Karurina-Munyi Karukungu Loop |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5951616 | 5951616 | 5951616 | County treasury | N/A | 5951616 | N/A | 5951616 | 100% | 5951616 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuvori - Karau - Kiambiti - Kiaritha - Gitare - Mususari Road (G 48613, G 48624, G 48625, G 48627) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbuvori - Karau - Kiambiti - Kiaritha - Gitare - Mususari Road (G 48613, G 48624, G 48625, G 48627) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 6529640 | 6529640 | 6529640 | County treasury | N/A | 6529640 | N/A | 6529640 | 100% | 6529640 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Micakarandari-Dubai-Runganga Road (F4105, G48490, G48478, G48449 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Micakarandari-Dubai-Runganga Road (F4105, G48490, G48478, G48449 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5958398 | 5958398 | 5958398 | County treasury | N/A | 5958398 | N/A | 5958398 | 100% | 5958398 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gategi - Kaseve - Kathiani Mbonzuki Road (D1223, G47761) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gategi - Kaseve - Kathiani Mbonzuki Road (D1223, G47761) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5828768 | 5828768 | 5828768 | County treasury | N/A | 5828768 | N/A | 5828768 | 100% | 5828768 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kang'ombe Kwa Ucuru Road (P20) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kang'ombe Kwa Ucuru Road (P20) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5423290 | 5423290 | 5423290 | County treasury | N/A | 5423290 | N/A | 5423290 | 100% | 5423290 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Igumo Primary-Rukira-Mvangua-Kauriro Road (F4304, F4103) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Igumo Primary-Rukira-Mvangua-Kauriro Road (F4304, F4103) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5800322 | 5800322 | 5800322 | County treasury | N/A | 5800322 | N/A | 5800322 | 100% | 5800322 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangari-Kithungururu-Scheme-Kairigi-Kangaru Road (P202_Embu, P196_Embu, P197_Embu, P199_Embu) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathangari-Kithungururu-Scheme-Kairigi-Kangaru Road (P202_Embu, P196_Embu, P197_Embu, P199_Embu) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5907300 | 5907300 | 5907300 | County treasury | N/A | 5907300 | N/A | 5907300 | 100% | 5907300 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Musyoka Market - Muthilu Market - Kathiani Market Road G47813 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Musyoka Market - Muthilu Market - Kathiani Market Road G47813 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5998384 | 5998384 | 5998384 | County treasury | N/A | 5998384 | N/A | 5998384 | 100% | 5998384 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karundori - Kavumburi Road & Rukuriri Nthumbiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karundori - Kavumburi Road & Rukuriri Nthumbiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-03-26 | 30/6/2021 | 30/6/2021 | 5532330 | 5532330 | 5532330 | County treasury | N/A | 5532330 | N/A | 5532330 | 100% | 5532330 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanjatiri Maturiri Thau Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanjatiri Maturiri Thau Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-01-29 | 30/6/2021 | 30/6/2021 | 5931660 | 5931660 | 5931660 | County treasury | N/A | 5931660 | N/A | 5931660 | 100% | 5931660 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatakari-Gangara-Kivue Road (F4097) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatakari-Gangara-Kivue Road (F4097) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 6303092 | 6303092 | 6303092 | County treasury | N/A | 6303092 | N/A | 6303092 | 100% | 6303092 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Governor’s Residence Embu County | Procurement, design , fountation laying and construction | To provide secure, functional and dignified facility | A well established morden, purpose-built residential complex | Road | Proposed Construction Of Governor’s Residence Embu County |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 49703439 | 49703439 | 49703439 | County treasury | N/A | 49703439 | N/A | 49703439 | 100% | 49703439 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Kathageri to Kigumo road (Phase I) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Kathageri to Kigumo road (Phase I) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 24491022 | 24491022 | 24491022 | County treasury | N/A | 24491022 | N/A | 24491022 | 100% | 24491022 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Stamdards of Muukuri Kirimiri road (kagaari North) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Stamdards of Muukuri Kirimiri road (kagaari North) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 23421814 | 23421814 | 23421814 | County treasury | N/A | 23421814 | N/A | 23421814 | 100% | 23421814 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Runyenjes Kigaa road (Phase 2) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Runyenjes Kigaa road (Phase 2) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 24732865 | 24732865 | 24732865 | County treasury | N/A | 24732865 | N/A | 24732865 | 100% | 24732865 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Ishiara Karerema road (Evurore) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Ishiara Karerema road (Evurore) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 24471641 | 24471641 | 24471641 | County treasury | N/A | 24471641 | N/A | 24471641 | 100% | 24471641 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Mukuuri Kanja road (Phase 2) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Mukuuri Kanja road (Phase 2) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 31225649 | 31225649 | 31225649 | County treasury | N/A | 31225649 | N/A | 31225649 | 100% | 31225649 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of A9 to Mufu road (Phase I) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of A9 to Mufu road (Phase I) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 23279164 | 23279164 | 23279164 | County treasury | N/A | 23279164 | N/A | 23279164 | 100% | 23279164 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Rwika-Jeremiah Nyaga road Phase 2 | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Rwika-Jeremiah Nyaga road Phase 2 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-04-29 | 30/6/2021 | 30/6/2021 | 25840335 | 25840335 | 25840335 | County treasury | N/A | 25840335 | N/A | 25840335 | 100% | 25840335 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Kivwe Karingari road (Phase I) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Kivwe Karingari road (Phase I) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-10 | 30/6/2021 | 30/6/2021 | 25197645 | 25197645 | 25197645 | County treasury | N/A | 25197645 | N/A | 25197645 | 100% | 25197645 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading to Bitumen Standards of Kivwe Kithimu road (Phase II) | Clearing, road formation, construction of pavement layers, and drainage works | To improve road safety, durability, and accessibility | Upgraded road to the morden constructions | Road | Upgrading to Bitumen Standards of Kivwe Kithimu road (Phase II) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 25908845 | 25908845 | 25908845 | County treasury | N/A | 25908845 | N/A | 25908845 | 100% | 25908845 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kavari, Gichugu, Kathangari road F4119 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kavari, Gichugu, Kathangari road F4119 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 5725354 | 5725354 | 5725354 | County treasury | N/A | 5725354 | N/A | 5725354 | 100% | 5725354 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jesi – Mathamjuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Jesi – Mathamjuki Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2693752 | 2693752 | 2693752 | County treasury | N/A | 2693752 | N/A | 2693752 | 100% | 2693752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gwa Toitoi – Nju Kavutii Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gwa Toitoi – Nju Kavutii Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2287694 | 2287694 | 2287694 | County treasury | N/A | 2287694 | N/A | 2287694 | 100% | 2287694 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Miliman Kwa Waweru – Full Gospel Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Miliman Kwa Waweru – Full Gospel Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3594468 | 3594468 | 3594468 | County treasury | N/A | 3594468 | N/A | 3594468 | 100% | 3594468 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Wambui Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Wambui Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3390738 | 3390738 | 3390738 | County treasury | N/A | 3390738 | N/A | 3390738 | 100% | 3390738 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 797500 | 797500 | 797500 | County treasury | N/A | 797500 | N/A | 797500 | 100% | 797500 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kyethiga Ntharawe Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kyethiga Ntharawe Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2993902 | 2993902 | 2993902 | County treasury | N/A | 2993902 | N/A | 2993902 | 100% | 2993902 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamuthatha Police Post Karindi – Wakioni Chief Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kamuthatha Police Post Karindi – Wakioni Chief Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 999004 | 999004 | 999004 | County treasury | N/A | 999004 | N/A | 999004 | 100% | 999004 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Elijah Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintance Of Elijah Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2997684 | 2997684 | 2997684 | County treasury | N/A | 2997684 | N/A | 2997684 | 100% | 2997684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gwa Tujenge Iganjagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gwa Tujenge Iganjagi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1399789 | 1399789 | 1399789 | County treasury | N/A | 1399789 | N/A | 1399789 | 100% | 1399789 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathuu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathuu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3333399 | 3333399 | 3333399 | County treasury | N/A | 3333399 | N/A | 3333399 | 100% | 3333399 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widening Maintenance Of Mondu Mutethania Kangaru Road | Bush clearing, widening, pavement repairs | To improve road capacity, safety and overall serviceability | Reduced maintenance cost and a widened road | Road | Widening Maintenance Of Mondu Mutethania Kangaru Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2499081 | 2499081 | 2499081 | County treasury | N/A | 2499081 | N/A | 2499081 | 100% | 2499081 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gacagori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gacagori Road |  |  |  | Road | Road |  | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2496552 | 2496552 | 2496552 | County treasury | N/A | 2496552 | N/A | 2496552 | 100% | 2496552 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Kau Cicuit Roads, Kamutungi Allamano Bypass Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Kau Cicuit Roads, Kamutungi Allamano Bypass Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3798884 | 3798884 | 3798884 | County treasury | N/A | 3798884 | N/A | 3798884 | 100% | 3798884 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rukira Kinyororo Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rukira Kinyororo Access Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2097396 | 2097396 | 2097396 | County treasury | N/A | 2097396 | N/A | 2097396 | 100% | 2097396 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading, Murraming And Installation Of Culverts Of Nemburi Gikangatu ,Kathanuroad | Grading, shaping of road formation, clearing and culvert installation | To improve road passability, durability and drainage system | A all-weather accessible road estabilshed | Road | Grading, Murraming And Installation Of Culverts Of Nemburi Gikangatu ,Kathanuroad |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2997892 | 2997892 | 2997892 | County treasury | N/A | 2997892 | N/A | 2997892 | 100% | 2997892 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Karue Kwa Marigu,Kathee Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Karue Kwa Marigu,Kathee Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2977256 | 2977256 | 2977256 | County treasury | N/A | 2977256 | N/A | 2977256 | 100% | 2977256 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rututu, Kiangwaci Karurina Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rututu, Kiangwaci Karurina Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2964008 | 2964008 | 2964008 | County treasury | N/A | 2964008 | N/A | 2964008 | 100% | 2964008 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance And Installation Of Culverts Of Kithimu Market – Gicagi Road, Maintenance Installation Of Culverts Of Kithegi Giekawa Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance And Installation Of Culverts Of Kithimu Market – Gicagi Road, Maintenance Installation Of Culverts Of Kithegi Giekawa Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3998630 | 3998630 | 3998630 | County treasury | N/A | 3998630 | N/A | 3998630 | 100% | 3998630 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Miyuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Miyuriri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2498930 | 2498930 | 2498930 | County treasury | N/A | 2498930 | N/A | 2498930 | 100% | 2498930 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathururu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathururu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2499290 | 2499290 | 2499290 | County treasury | N/A | 2499290 | N/A | 2499290 | 100% | 2499290 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kangichu , Luwaka Forest Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kangichu , Luwaka Forest Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2995874 | 2995874 | 2995874 | County treasury | N/A | 2995874 | N/A | 2995874 | 100% | 2995874 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiathwanga-Karwagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiathwanga-Karwagi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3994657 | 3994657 | 3994657 | County treasury | N/A | 3994657 | N/A | 3994657 | 100% | 3994657 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mkadamia Maendelea Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mkadamia Maendelea Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1997938 | 1997938 | 1997938 | County treasury | N/A | 1997938 | N/A | 1997938 | 100% | 1997938 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts On Various Roads | Procurement, culvert delivery and installation | To improve water drainage systems on the roads | Durable and erosion free roads | Road | Installation Of Culverts On Various Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 993656 | 993656 | 993656 | County treasury | N/A | 993656 | N/A | 993656 | 100% | 993656 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kairuri Bank Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kairuri Bank Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 998122 | 998122 | 998122 | County treasury | N/A | 998122 | N/A | 998122 | 100% | 998122 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriari Market | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiriari Market |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1996998 | 1996998 | 1996998 | County treasury | N/A | 1996998 | N/A | 1996998 | 100% | 1996998 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Matiru Kigari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Matiru Kigari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2998345 | 2998345 | 2998345 | County treasury | N/A | 2998345 | N/A | 2998345 | 100% | 2998345 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiamutubari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiamutubari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 999282 | 999282 | 999282 | County treasury | N/A | 999282 | N/A | 999282 | 100% | 999282 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirigi Kwa Bishop Pag Road, Kamviu Kiarugiri | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirigi Kwa Bishop Pag Road, Kamviu Kiarugiri |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 4498398 | 4498398 | 4498398 | County treasury | N/A | 4498398 | N/A | 4498398 | 100% | 4498398 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngaratiri Factory Road,Maintenance Of Kiamigumo Kirimiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngaratiri Factory Road,Maintenance Of Kiamigumo Kirimiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2952014 | 2952014 | 2952014 | County treasury | N/A | 2952014 | N/A | 2952014 | 100% | 2952014 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karima Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karima Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 997438 | 997438 | 997438 | County treasury | N/A | 997438 | N/A | 997438 | 100% | 997438 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakinduri Kathande Road, Maintenance Of Kiandakia Ithanje, Josefu Miandari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gakinduri Kathande Road, Maintenance Of Kiandakia Ithanje, Josefu Miandari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2978915 | 2978915 | 2978915 | County treasury | N/A | 2978915 | N/A | 2978915 | 100% | 2978915 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nica Iriangi Road, Maintenance Of Nduuro Kanja Road, Maintenance Of Kithuguya Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nica Iriangi Road, Maintenance Of Nduuro Kanja Road, Maintenance Of Kithuguya Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2981977 | 2981977 | 2981977 | County treasury | N/A | 2981977 | N/A | 2981977 | 100% | 2981977 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nthunguri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nthunguri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2997614 | 2997614 | 2997614 | County treasury | N/A | 2997614 | N/A | 2997614 | 100% | 2997614 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Full Gospel Gwa Karobo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Full Gospel Gwa Karobo Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2994679 | 2994679 | 2994679 | County treasury | N/A | 2994679 | N/A | 2994679 | 100% | 2994679 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njagairi Kwa Warivai Road, Maintenance Of Minandari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njagairi Kwa Warivai Road, Maintenance Of Minandari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3557674 | 3557674 | 3557674 | County treasury | N/A | 3557674 | N/A | 3557674 | 100% | 3557674 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Kathuthi – Kwa Ndwiga Njeru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Kathuthi – Kwa Ndwiga Njeru Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3590954 | 3590954 | 3590954 | County treasury | N/A | 3590954 | N/A | 3590954 | 100% | 3590954 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichichie – Gatitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichichie – Gatitu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1991662 | 1991662 | 1991662 | County treasury | N/A | 1991662 | N/A | 1991662 | 100% | 1991662 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gaciari B Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gaciari B Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1935576 | 1935576 | 1935576 | County treasury | N/A | 1935576 | N/A | 1935576 | 100% | 1935576 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngarari – Kang’ethia Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngarari – Kang’ethia Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3498258 | 3498258 | 3498258 | County treasury | N/A | 3498258 | N/A | 3498258 | 100% | 3498258 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndururi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ndururi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2123809 | 2123809 | 2123809 | County treasury | N/A | 2123809 | N/A | 2123809 | 100% | 2123809 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njagairi – Kwa Suta Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njagairi – Kwa Suta Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2109286 | 2109286 | 2109286 | County treasury | N/A | 2109286 | N/A | 2109286 | 100% | 2109286 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Irati Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Irati Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1948684 | 1948684 | 1948684 | County treasury | N/A | 1948684 | N/A | 1948684 | 100% | 1948684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kianjuri – Kiandari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kianjuri – Kiandari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2987174 | 2987174 | 2987174 | County treasury | N/A | 2987174 | N/A | 2987174 | 100% | 2987174 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ithuiro Kasarani Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ithuiro Kasarani Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 3397246 | 3397246 | 3397246 | County treasury | N/A | 3397246 | N/A | 3397246 | 100% | 3397246 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Munyutu Morris Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Munyutu Morris Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2793408 | 2793408 | 2793408 | County treasury | N/A | 2793408 | N/A | 2793408 | 100% | 2793408 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamwarime – Jugo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamwarime – Jugo Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1790530 | 1790530 | 1790530 | County treasury | N/A | 1790530 | N/A | 1790530 | 100% | 1790530 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njeruri Kiruari Road, Maintenance Of Makutano Kirege Road , Maintenance Of Kiaragana -Kaveti Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njeruri Kiruari Road, Maintenance Of Makutano Kirege Road , Maintenance Of Kiaragana -Kaveti Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2998530 | 2998530 | 2998530 | County treasury | N/A | 2998530 | N/A | 2998530 | 100% | 2998530 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njeruri – Mivutiri Road, Maintenance Of Mufu – Gatumbi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njeruri – Mivutiri Road, Maintenance Of Mufu – Gatumbi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1990456 | 1990456 | 1990456 | County treasury | N/A | 1990456 | N/A | 1990456 | 100% | 1990456 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Dipure Gatunduri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Dipure Gatunduri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1499184 | 1499184 | 1499184 | County treasury | N/A | 1499184 | N/A | 1499184 | 100% | 1499184 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gikirima Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gikirima Factory Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 1499764 | 1499764 | 1499764 | County treasury | N/A | 1499764 | N/A | 1499764 | 100% | 1499764 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Ofcamp Dundaroad | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Ofcamp Dundaroad |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2994865 | 2994865 | 2994865 | County treasury | N/A | 2994865 | N/A | 2994865 | 100% | 2994865 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchagori -Gituri Kirangiri Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muchagori -Gituri Kirangiri Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-05-31 | 30/6/2021 | 30/6/2021 | 2598359 | 2598359 | 2598359 | County treasury | N/A | 2598359 | N/A | 2598359 | 100% | 2598359 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kagumori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kagumori Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1999550 | 1999550 | 1999550 | County treasury | N/A | 1999550 | N/A | 1999550 | 100% | 1999550 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuyari-Kiamatuto Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbuyari-Kiamatuto Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1069195 | 1069195 | 1069195 | County treasury | N/A | 1069195 | N/A | 1069195 | 100% | 1069195 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Igumo Gwa Kimenye Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Igumo Gwa Kimenye Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1999852 | 1999852 | 1999852 | County treasury | N/A | 1999852 | N/A | 1999852 | 100% | 1999852 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gaciari A Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gaciari A Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1497374 | 1497374 | 1497374 | County treasury | N/A | 1497374 | N/A | 1497374 | 100% | 1497374 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mariari Primary – Muramba Mavuthu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mariari Primary – Muramba Mavuthu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1981916 | 1981916 | 1981916 | County treasury | N/A | 1981916 | N/A | 1981916 | 100% | 1981916 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichugu Jaft, Maintenance Mutira Road, Mainatance Of Muthageri Kavutiri Primary Opening Of Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichugu Jaft, Maintenance Mutira Road, Mainatance Of Muthageri Kavutiri Primary Opening Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 4497587 | 4497587 | 4497587 | County treasury | N/A | 4497587 | N/A | 4497587 | 100% | 4497587 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads | Clearing, road formation, construction of pavement layers, and drainage works | To restore the road surface and improve riding quality | Reliable access for residents and service providers | Road | Grading Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2998600 | 2998600 | 2998600 | County treasury | N/A | 2998600 | N/A | 2998600 | 100% | 2998600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of County Road-Ciamuvui Junction Mavirari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of County Road-Ciamuvui Junction Mavirari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2496900 | 2496900 | 2496900 | County treasury | N/A | 2496900 | N/A | 2496900 | 100% | 2496900 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening And Grading Of Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening And Grading Of Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2992174 | 2992174 | 2992174 | County treasury | N/A | 2992174 | N/A | 2992174 | 100% | 2992174 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Syomathi – Thiba Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Syomathi – Thiba Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3194872 | 3194872 | 3194872 | County treasury | N/A | 3194872 | N/A | 3194872 | 100% | 3194872 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Itonguri Kirigiri Ikunguru Road, Ruvutiri B Road, Muthanderi – Karue Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Itonguri Kirigiri Ikunguru Road, Ruvutiri B Road, Muthanderi – Karue Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2997602 | 2997602 | 2997602 | County treasury | N/A | 2997602 | N/A | 2997602 | 100% | 2997602 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Selected Roads In | Clearing, road formation, construction of pavement layers, and drainage works | To improve road surface condition, durability and all-weather accessibility | Reliable access to farms, schools, health facilities, and residential areas | Road | Gravelling Of Selected Roads In |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3999216 | 3999216 | 3999216 | County treasury | N/A | 3999216 | N/A | 3999216 | 100% | 3999216 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngimari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngimari Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1995710 | 1995710 | 1995710 | County treasury | N/A | 1995710 | N/A | 1995710 | 100% | 1995710 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kivwe Miriruri And Kivwe Gwagukenga Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kivwe Miriruri And Kivwe Gwagukenga Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1493210 | 1493210 | 1493210 | County treasury | N/A | 1493210 | N/A | 1493210 | 100% | 1493210 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nguthi Road And Construction Of Karie Kathari Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nguthi Road And Construction Of Karie Kathari Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1997056 | 1997056 | 1997056 | County treasury | N/A | 1997056 | N/A | 1997056 | 100% | 1997056 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Methano Nduva Ack Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Methano Nduva Ack Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1997404 | 1997404 | 1997404 | County treasury | N/A | 1997404 | N/A | 1997404 | 100% | 1997404 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Various Roads In | Clearing, grading and reshaping, spot improvement of weak sections | To restore surface condition and improve riding quality | Reliable access for residents and service providers | Road | Grading Of Various Roads In |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2495160 | 2495160 | 2495160 | County treasury | N/A | 2495160 | N/A | 2495160 | 100% | 2495160 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Murumiri Hospice Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Murumiri Hospice Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1994040 | 1994040 | 1994040 | County treasury | N/A | 1994040 | N/A | 1994040 | 100% | 1994040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | All-weather accessible and durable road | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 999862 | 999862 | 999862 | County treasury | N/A | 999862 | N/A | 999862 | 100% | 999862 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2993902 | 2993902 | 2993902 | County treasury | N/A | 2993902 | N/A | 2993902 | 100% | 2993902 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Majimbo Loop Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Majimbo Loop Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2990480 | 2990480 | 2990480 | County treasury | N/A | 2990480 | N/A | 2990480 | 100% | 2990480 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitaungu Road ( | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gitaungu Road ( |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 999746 | 999746 | 999746 | County treasury | N/A | 999746 | N/A | 999746 | 100% | 999746 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanvara Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanvara Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3476706 | 3476706 | 3476706 | County treasury | N/A | 3476706 | N/A | 3476706 | 100% | 3476706 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St John’s Karumiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of St John’s Karumiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 995860 | 995860 | 995860 | County treasury | N/A | 995860 | N/A | 995860 | 100% | 995860 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Havard Mwana Wa Gitii Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Havard Mwana Wa Gitii Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3484507 | 3484507 | 3484507 | County treasury | N/A | 3484507 | N/A | 3484507 | 100% | 3484507 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kauga B Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kauga B Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2540400 | 2540400 | 2540400 | County treasury | N/A | 2540400 | N/A | 2540400 | 100% | 2540400 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rukungu-Mwondu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rukungu-Mwondu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1993344 | 1993344 | 1993344 | County treasury | N/A | 1993344 | N/A | 1993344 | 100% | 1993344 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Dallas-Old Stadium-Rupingazi Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Dallas-Old Stadium-Rupingazi Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2999871 | 2999871 | 2999871 | County treasury | N/A | 2999871 | N/A | 2999871 | 100% | 2999871 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithunguthia-Gituri B Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kithunguthia-Gituri B Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 999201 | 999201 | 999201 | County treasury | N/A | 999201 | N/A | 999201 | 100% | 999201 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads In | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads In |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2929708 | 2929708 | 2929708 | County treasury | N/A | 2929708 | N/A | 2929708 | 100% | 2929708 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Itiira-Kathutheri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Itiira-Kathutheri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 997136 | 997136 | 997136 | County treasury | N/A | 997136 | N/A | 997136 | 100% | 997136 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads In Kiambere | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Roads In Kiambere |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1995722 | 1995722 | 1995722 | County treasury | N/A | 1995722 | N/A | 1995722 | 100% | 1995722 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Various Access Roads | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling Of Various Access Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1996743 | 1996743 | 1996743 | County treasury | N/A | 1996743 | N/A | 1996743 | 100% | 1996743 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kibera Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kibera Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2278008 | 2278008 | 2278008 | County treasury | N/A | 2278008 | N/A | 2278008 | 100% | 2278008 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakurungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gakurungu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2013963 | 2013963 | 2013963 | County treasury | N/A | 2013963 | N/A | 2013963 | 100% | 2013963 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Spring Valley-St Michael To Ap Line ( | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Spring Valley-St Michael To Ap Line ( |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2999940 | 2999940 | 2999940 | County treasury | N/A | 2999940 | N/A | 2999940 | 100% | 2999940 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Gachoka-Zebra-Rwika Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Gachoka-Zebra-Rwika Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3296952 | 3296952 | 3296952 | County treasury | N/A | 3296952 | N/A | 3296952 | 100% | 3296952 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kararitiri Emau Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kararitiri Emau Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2999816 | 2999816 | 2999816 | County treasury | N/A | 2999816 | N/A | 2999816 | 100% | 2999816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening/Widening Of Roads In | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening/Widening Of Roads In |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3499991 | 3499991 | 3499991 | County treasury | N/A | 3499991 | N/A | 3499991 | 100% | 3499991 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 3990040 | 3990040 | 3990040 | County treasury | N/A | 3990040 | N/A | 3990040 | 100% | 3990040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1999492 | 1999492 | 1999492 | County treasury | N/A | 1999492 | N/A | 1999492 | 100% | 1999492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Runyaga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Runyaga Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1498836 | 1498836 | 1498836 | County treasury | N/A | 1498836 | N/A | 1498836 | 100% | 1498836 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1995200 | 1995200 | 1995200 | County treasury | N/A | 1995200 | N/A | 1995200 | 100% | 1995200 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichegori –Baptist Church Ngenge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichegori –Baptist Church Ngenge Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 895798 | 895798 | 895798 | County treasury | N/A | 895798 | N/A | 895798 | 100% | 895798 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Asorted Sizes Of Culverts On Selected Roads | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Asorted Sizes Of Culverts On Selected Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1999376 | 1999376 | 1999376 | County treasury | N/A | 1999376 | N/A | 1999376 | 100% | 1999376 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gisamba Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gisamba Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 1989168 | 1989168 | 1989168 | County treasury | N/A | 1989168 | N/A | 1989168 | 100% | 1989168 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Wango Kwa Kimilu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Wango Kwa Kimilu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2495131 | 2495131 | 2495131 | County treasury | N/A | 2495131 | N/A | 2495131 | 100% | 2495131 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Frangesco Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Frangesco Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-07 | 30/6/2021 | 30/6/2021 | 2488316 | 2488316 | 2488316 | County treasury | N/A | 2488316 | N/A | 2488316 | 100% | 2488316 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Makutano Kamviu Manyatta Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Makutano Kamviu Manyatta Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-14 | 30/6/2021 | 30/6/2021 | 3497452 | 3497452 | 3497452 | County treasury | N/A | 3497452 | N/A | 3497452 | 100% | 3497452 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintennace of Kawanjara Kithunguthia Road(AGPO Women) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintennace of Kawanjara Kithunguthia Road(AGPO Women) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-14 | 30/6/2021 | 30/6/2021 | 3393580 | 3393580 | 3393580 | County treasury | N/A | 3393580 | N/A | 3393580 | 100% | 3393580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Nduuri Gacagori Road (AGPO Youth) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Nduuri Gacagori Road (AGPO Youth) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-14 | 30/6/2021 | 30/6/2021 | 3198468 | 3198468 | 3198468 | County treasury | N/A | 3198468 | N/A | 3198468 | 100% | 3198468 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kigaa Muthuari Road (AGPO Youth) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kigaa Muthuari Road (AGPO Youth) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-14 | 30/6/2021 | 30/6/2021 | 3199674 | 3199674 | 3199674 | County treasury | N/A | 3199674 | N/A | 3199674 | 100% | 3199674 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamiugu Kevote Road (AGPO Youth) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamiugu Kevote Road (AGPO Youth) |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-14 | 30/6/2021 | 30/6/2021 | 3499662 | 3499662 | 3499662 | County treasury | N/A | 3499662 | N/A | 3499662 | 100% | 3499662 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyakiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanyakiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1996766 | 1996766 | 1996766 | County treasury | N/A | 1996766 | N/A | 1996766 | 100% | 1996766 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Managia Ndumari Road, Kwa Elisha Gaturi Road, Senior Chief Road, Kwa Gatungu Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Managia Ndumari Road, Kwa Elisha Gaturi Road, Senior Chief Road, Kwa Gatungu Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 3255876 | 3255876 | 3255876 | County treasury | N/A | 3255876 | N/A | 3255876 | 100% | 3255876 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbondoni – Mwalimu Njue- Ndunduni Road –Makima | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbondoni – Mwalimu Njue- Ndunduni Road –Makima |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1498256 | 1498256 | 1498256 | County treasury | N/A | 1498256 | N/A | 1498256 | 100% | 1498256 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation And Repair Of Various Culverts Makima | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation And Repair Of Various Culverts Makima |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 2497132 | 2497132 | 2497132 | County treasury | N/A | 2497132 | N/A | 2497132 | 100% | 2497132 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Musingini Malikini Kilia Ngomola Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Musingini Malikini Kilia Ngomola Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 2996326 | 2996326 | 2996326 | County treasury | N/A | 2996326 | N/A | 2996326 | 100% | 2996326 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Cieria Ndivuri & Grading And Intallation Of Culverts Of Ndiuri Road | Clearing, excavation and earthworks | Opening new road corridors and to improve road accessibility and drainage | A functional, well-drained and durable road | Road | Opening Of Cieria Ndivuri & Grading And Intallation Of Culverts Of Ndiuri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1498233 | 1498233 | 1498233 | County treasury | N/A | 1498233 | N/A | 1498233 | 100% | 1498233 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigangari Road, Coffee Factory Road, Ngomani Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kigangari Road, Coffee Factory Road, Ngomani Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 4695112 | 4695112 | 4695112 | County treasury | N/A | 4695112 | N/A | 4695112 | 100% | 4695112 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Various Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Various Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 2985724 | 2985724 | 2985724 | County treasury | N/A | 2985724 | N/A | 2985724 | 100% | 2985724 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurumo Kandete Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurumo Kandete Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1999255 | 1999255 | 1999255 | County treasury | N/A | 1999255 | N/A | 1999255 | 100% | 1999255 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Kyeni East Location Roads | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling Of Kyeni East Location Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 2495102 | 2495102 | 2495102 | County treasury | N/A | 2495102 | N/A | 2495102 | 100% | 2495102 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Rehabilitation Of Gakungugu Foot Bridge | Assessment, removal and repair of structural elements | To restore the integrity of the structure and safety | A safe, durable and reliable crossing for pedestrians | Road | Rehabilitation Of Gakungugu Foot Bridge |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1498662 | 1498662 | 1498662 | County treasury | N/A | 1498662 | N/A | 1498662 | 100% | 1498662 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 802720 | 802720 | 802720 | County treasury | N/A | 802720 | N/A | 802720 | 100% | 802720 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kevote- Gicagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kevote- Gicagi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 999201 | 999201 | 999201 | County treasury | N/A | 999201 | N/A | 999201 | 100% | 999201 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitaraka Wango Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gitaraka Wango Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1094916 | 1094916 | 1094916 | County treasury | N/A | 1094916 | N/A | 1094916 | 100% | 1094916 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamunyagia – Mwea Makima | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamunyagia – Mwea Makima |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1289688 | 1289688 | 1289688 | County treasury | N/A | 1289688 | N/A | 1289688 | 100% | 1289688 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirigi Road, Maintenance Of Ivari B Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirigi Road, Maintenance Of Ivari B Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 3497412 | 3497412 | 3497412 | County treasury | N/A | 3497412 | N/A | 3497412 | 100% | 3497412 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening And Maintenance Of Katwanyaga- Kavengrle Road – | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening And Maintenance Of Katwanyaga- Kavengrle Road – |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1991627 | 1991627 | 1991627 | County treasury | N/A | 1991627 | N/A | 1991627 | 100% | 1991627 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 3995620 | 3995620 | 3995620 | County treasury | N/A | 3995620 | N/A | 3995620 | 100% | 3995620 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Various Roads | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts In Various Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 985218 | 985218 | 985218 | County treasury | N/A | 985218 | N/A | 985218 | 100% | 985218 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimangaru Access Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kimangaru Access Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 3887102 | 3887102 | 3887102 | County treasury | N/A | 3887102 | N/A | 3887102 | 100% | 3887102 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Mururi Kuui Drift | Excavation, clearance and construction | To ensure safe passage of traffic and resistance to flooding effects | A durable and reliable crossing access to connectivity | Road | Construction Of Mururi Kuui Drift |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1384193 | 1384193 | 1384193 | County treasury | N/A | 1384193 | N/A | 1384193 | 100% | 1384193 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Syongua Ngandi Gatuiri Maviani To Ngandi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Syongua Ngandi Gatuiri Maviani To Ngandi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 2986536 | 2986536 | 2986536 | County treasury | N/A | 2986536 | N/A | 2986536 | 100% | 2986536 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigaa Gicagi/Gacuki Road, Gitare Kiaragana, Kang’ondu B Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kigaa Gicagi/Gacuki Road, Gitare Kiaragana, Kang’ondu B Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 3998807 | 3998807 | 3998807 | County treasury | N/A | 3998807 | N/A | 3998807 | 100% | 3998807 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1997752 | 1997752 | 1997752 | County treasury | N/A | 1997752 | N/A | 1997752 | 100% | 1997752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts At Kamarindo Drift | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts At Kamarindo Drift |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1999910 | 1999910 | 1999910 | County treasury | N/A | 1999910 | N/A | 1999910 | 100% | 1999910 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gisamba Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gisamba Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-18 | 30/6/2021 | 30/6/2021 | 1989168 | 1989168 | 1989168 | County treasury | N/A | 1989168 | N/A | 1989168 | 100% | 1989168 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Kyeni Central Road | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling Of Kyeni Central Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 2497213 | 2497213 | 2497213 | County treasury | N/A | 2497213 | N/A | 2497213 | 100% | 2497213 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St Teresaroad | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of St Teresaroad |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 2991466 | 2991466 | 2991466 | County treasury | N/A | 2991466 | N/A | 2991466 | 100% | 2991466 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Beat To Karuga Mutitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Beat To Karuga Mutitu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3998798 | 3998798 | 3998798 | County treasury | N/A | 3998798 | N/A | 3998798 | 100% | 3998798 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Musafiri Tito Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Musafiri Tito Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3232000 | 3232000 | 3232000 | County treasury | N/A | 3232000 | N/A | 3232000 | 100% | 3232000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Ngondi Full Gospel Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Ngondi Full Gospel Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3102002 | 3102002 | 3102002 | County treasury | N/A | 3102002 | N/A | 3102002 | 100% | 3102002 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuvori Kamavindi Road( | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbuvori Kamavindi Road( |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3482564 | 3482564 | 3482564 | County treasury | N/A | 3482564 | N/A | 3482564 | 100% | 3482564 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Fausi Semeji Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Fausi Semeji Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3306000 | 3306000 | 3306000 | County treasury | N/A | 3306000 | N/A | 3306000 | 100% | 3306000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karumiri Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karumiri Access Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3440468 | 3440468 | 3440468 | County treasury | N/A | 3440468 | N/A | 3440468 | 100% | 3440468 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Ndwiga Gutonya Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Ndwiga Gutonya Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3471323 | 3471323 | 3471323 | County treasury | N/A | 3471323 | N/A | 3471323 | 100% | 3471323 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutethania Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutethania Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3214476 | 3214476 | 3214476 | County treasury | N/A | 3214476 | N/A | 3214476 | 100% | 3214476 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakambura Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gakambura Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 1993228 | 1993228 | 1993228 | County treasury | N/A | 1993228 | N/A | 1993228 | 100% | 1993228 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ack St.Paul Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ack St.Paul Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3490382 | 3490382 | 3490382 | County treasury | N/A | 3490382 | N/A | 3490382 | 100% | 3490382 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Njaga –Munyi Karukungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Njaga –Munyi Karukungu Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3960463 | 3960463 | 3960463 | County treasury | N/A | 3960463 | N/A | 3960463 | 100% | 3960463 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Gachogo Njiru Matua Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Gachogo Njiru Matua Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3492876 | 3492876 | 3492876 | County treasury | N/A | 3492876 | N/A | 3492876 | 100% | 3492876 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widenig/Grading/Murraming Of Matangiri/Ithara/Gicuvirori Roads | Clearing, excavation, levelling and grading | To improve capacity, riding quality and al-weather accessibity | A stable, well-drained road | Road | Widenig/Grading/Murraming Of Matangiri/Ithara/Gicuvirori Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 2989146 | 2989146 | 2989146 | County treasury | N/A | 2989146 | N/A | 2989146 | 100% | 2989146 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nduva Gichegeri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nduva Gichegeri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 1099460 | 1099460 | 1099460 | County treasury | N/A | 1099460 | N/A | 1099460 | 100% | 1099460 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mirangari Main Tarmac Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mirangari Main Tarmac Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-23 | 30/6/2021 | 30/6/2021 | 3191415 | 3191415 | 3191415 | County treasury | N/A | 3191415 | N/A | 3191415 | 100% | 3191415 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamande Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kamande Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2486460 | 2486460 | 2486460 | County treasury | N/A | 2486460 | N/A | 2486460 | 100% | 2486460 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Wachira Kithiga Road ( | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Wachira Kithiga Road ( |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2881266 | 2881266 | 2881266 | County treasury | N/A | 2881266 | N/A | 2881266 | 100% | 2881266 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Spot Murraming Of Irumiri Road | Identification, removal and replacement of unsuitable material | To restore the road surface and ensuring effective drainage | More durable and improved drainage suface | Road | Spot Murraming Of Irumiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 1999376 | 1999376 | 1999376 | County treasury | N/A | 1999376 | N/A | 1999376 | 100% | 1999376 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ithaara –Yayeri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ithaara –Yayeri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 3997708 | 3997708 | 3997708 | County treasury | N/A | 3997708 | N/A | 3997708 | 100% | 3997708 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murraming Of Njukiri Road | Identification, removal and replacement of unsuitable material | To restore the road surface and ensuring effective drainage | More durable and improved drainage suface | Road | Murraming Of Njukiri Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 1486250 | 1486250 | 1486250 | County treasury | N/A | 1486250 | N/A | 1486250 | 100% | 1486250 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muraru – Bypass Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muraru – Bypass Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2992684 | 2992684 | 2992684 | County treasury | N/A | 2992684 | N/A | 2992684 | 100% | 2992684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Musingini Malikini Kilia Ngomola Road. | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Musingini Malikini Kilia Ngomola Road. |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2921320 | 2921320 | 2921320 | County treasury | N/A | 2921320 | N/A | 2921320 | 100% | 2921320 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rwika Market To Rianjeru Tarmac Junction | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rwika Market To Rianjeru Tarmac Junction |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2498130 | 2498130 | 2498130 | County treasury | N/A | 2498130 | N/A | 2498130 | 100% | 2498130 | N/A | N/A | Completed | 1005 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchangi Chege Njeru Mutemi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muchangi Chege Njeru Mutemi Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 3191682 | 3191682 | 3191682 | County treasury | N/A | 3191682 | N/A | 3191682 | 100% | 3191682 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Catholic Kanthamba, Kivoo Masister Gachage – Tarmac Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Catholic Kanthamba, Kivoo Masister Gachage – Tarmac Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 3595432 | 3595432 | 3595432 | County treasury | N/A | 3595432 | N/A | 3595432 | 100% | 3595432 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatete Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatete Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2110000 | 2110000 | 2110000 | County treasury | N/A | 2110000 | N/A | 2110000 | 100% | 2110000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gpa Ngarira Kauvaciri, Maintenance Of Roads In Mavuria | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gpa Ngarira Kauvaciri, Maintenance Of Roads In Mavuria |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2299143 | 2299143 | 2299143 | County treasury | N/A | 2299143 | N/A | 2299143 | 100% | 2299143 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| Maintenance Of Mukangu – Gakindu – Kiriari – Gatoori | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mukangu – Gakindu – Kiriari – Gatoori |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2493234 | 2493234 | 2493234 | County treasury | N/A | 2493234 | N/A | 2493234 | 100% | 2493234 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Munene Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Munene Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 2887448 | 2887448 | 2887448 | County treasury | N/A | 2887448 | N/A | 2887448 | 100% | 2887448 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads, Hire Of Dozing Machines |  |  |  | Road | Opening Of Roads, Hire Of Dozing Machines |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 3497980 | 3497980 | 3497980 | County treasury | N/A | 3497980 | N/A | 3497980 | 100% | 3497980 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Road | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 1999840 | 1999840 | 1999840 | County treasury | N/A | 1999840 | N/A | 1999840 | 100% | 1999840 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Kiritiri Drift | Excavation, clearance and construction | To ensure safe passage of traffic and resistance to flooding effects | A durable and reliable crossing access to connectivity | Road | Construction Of Kiritiri Drift |  |  |  | Road | Road | Road | 2020-01-07 | 2021-06-24 | 30/6/2021 | 30/6/2021 | 999746 | 999746 | 999746 | County treasury | N/A | 999746 | N/A | 999746 | 100% | 999746 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Renovation Of Former County Treasurer House | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | A durable and reliable crossing access to connectivity | Road | Renovation Of Former County Treasurer House |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 3999993 | 3999993 | 3999993 | County treasury | N/A | 3999993 | N/A | 3999993 | 100% | 3999993 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Iriari Gichogeni Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Iriari Gichogeni Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2997570 | 2997570 | 2997570 | County treasury | N/A | 2997570 | N/A | 2997570 | 100% | 2997570 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Zoori – Ngerwe | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Zoori – Ngerwe |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2195022 | 2195022 | 2195022 | County treasury | N/A | 2195022 | N/A | 2195022 | 100% | 2195022 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngambari Ntharawe & Catholic Issaco Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngambari Ntharawe & Catholic Issaco Roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2999760 | 2999760 | 2999760 | County treasury | N/A | 2999760 | N/A | 2999760 | 100% | 2999760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murraming And Grading Of Muraru Market Sheds | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | A durable and reliable crossing access to connectivity | Road | Murraming And Grading Of Muraru Market Sheds |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2197434 | 2197434 | 2197434 | County treasury | N/A | 2197434 | N/A | 2197434 | 100% | 2197434 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbonzuki Musingini Road, Maintenance Of Malikini Kisio ni Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbonzuki Musingini Road, Maintenance Of Malikini Kisio ni Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2199592 | 2199592 | 2199592 | County treasury | N/A | 2199592 | N/A | 2199592 | 100% | 2199592 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangariri Kyeni Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathangariri Kyeni Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 1999040 | 1999040 | 1999040 | County treasury | N/A | 1999040 | N/A | 1999040 | 100% | 1999040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Ciku Njuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Ciku Njuki Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 3367132 | 3367132 | 3367132 | County treasury | N/A | 3367132 | N/A | 3367132 | 100% | 3367132 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamugere | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamugere |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 999201 | 999201 | 999201 | County treasury | N/A | 999201 | N/A | 999201 | 100% | 999201 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murraming Of Gategi Market Sheds | Identification, removal and replacement of unsuitable material | To prevent further deterioration of road assets though timely interventions | More durable and improved drainage suface | Road | Murraming Of Gategi Market Sheds |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 399968 | 399968 | 399968 | County treasury | N/A | 399968 | N/A | 399968 | 100% | 399968 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kianjokoma Kathimba Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kianjokoma Kathimba Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 999201 | 999201 | 999201 | County treasury | N/A | 999201 | N/A | 999201 | 100% | 999201 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ngarira Drift Phase 1 | Excavation, clearance and construction | To ensure safe passage of traffic and resistance to flooding effects | A durable and reliable crossing access to connectivity | Road | Construction Of Ngarira Drift Phase 1 |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 1999898 | 1999898 | 1999898 | County treasury | N/A | 1999898 | N/A | 1999898 | 100% | 1999898 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Sunrise – Kiwanuka Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Sunrise – Kiwanuka Road |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 1647200 | 1647200 | 1647200 | County treasury | N/A | 1647200 | N/A | 1647200 | 100% | 1647200 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading and sport improvement of Kamweli road, Grading, Murraming of PI-Wanding road, Grading and Murraming of PI Market roads | Clearing, earthworks, levelling and compaction | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Grading and sport improvement of Kamweli road, Grading, Murraming of PI-Wanding road, Grading and Murraming of PI Market roads |  |  |  | Road | Road | Road | 2020-01-07 | 2021-07-05 | 30/6/2021 | 30/6/2021 | 2999535 | 2999535 | 2999535 | County treasury | N/A | 2999535 | N/A | 2999535 | 100% | 2999535 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2019/2020
| Upgrading Of Rwika – Jeremiah Nyaga Technical Road To Bitumen Standards | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Rwika – Jeremiah Nyaga Technical Road To Bitumen Standards |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 34287825 | 34287825 | 34287825 | County Treasury | N/A | 34287825 | N/A | 34287825 | 100% | 34287825 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Kivwe – Kithimu Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Kivwe – Kithimu Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 34472871 | 34472871 | 34472871 | County Treasury | N/A | 34472871 | N/A | 34472871 | 100% | 34472871 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Muchangori Market Loop Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Muchangori Market Loop Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 8990423 | 8990423 | 8990423 | County Treasury | N/A | 8990423 | N/A | 8990423 | 100% | 8990423 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurumo Market Access Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurumo Market Access Roads |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5708070 | 5708070 | 5708070 | County Treasury | N/A | 5708070 | N/A | 5708070 | 100% | 5708070 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widening And Maintenance Of Gakwegori Gatunduri | Reshaping, drainage repair and resurfacing | To improve traffic flow, enhance safety and extend the lifespan of the road | Widened and well- maintained road | Road | Widening And Maintenance Of Gakwegori Gatunduri |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5899093 | 5899093 | 5899093 | County Treasury | N/A | 5899093 | N/A | 5899093 | 100% | 5899093 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kivue To Karingari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kivue To Karingari Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 4992060 | 4992060 | 4992060 | County Treasury | N/A | 4992060 | N/A | 4992060 | 100% | 4992060 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiringa Market – Kavuru Primary Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiringa Market – Kavuru Primary Junction Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5937692 | 5937692 | 5937692 | County Treasury | N/A | 5937692 | N/A | 5937692 | 100% | 5937692 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jerusalem – Kiangungi Dispensary Road In Mbeti South | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Jerusalem – Kiangungi Dispensary Road In Mbeti South |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5300156 | 5300156 | 5300156 | County Treasury | N/A | 5300156 | N/A | 5300156 | 100% | 5300156 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathanje – Kauraciri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathanje – Kauraciri Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5100670 | 5100670 | 5100670 | County Treasury | N/A | 5100670 | N/A | 5100670 | 100% | 5100670 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Old B6 Junction – Njeruri Tbc-Tarmac Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Old B6 Junction – Njeruri Tbc-Tarmac Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5847560 | 5847560 | 5847560 | County Treasury | N/A | 5847560 | N/A | 5847560 | 100% | 5847560 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchangori – Kirurumwe – Makengi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muchangori – Kirurumwe – Makengi Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5040345 | 5040345 | 5040345 | County Treasury | N/A | 5040345 | N/A | 5040345 | 100% | 5040345 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Scheme – Kathangari Kithungururu Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Scheme – Kathangari Kithungururu Factory Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5699776 | 5699776 | 5699776 | County Treasury | N/A | 5699776 | N/A | 5699776 | 100% | 5699776 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kibugu Tarmac – Nguviu Boys – Mwara Njogu Tbc Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kibugu Tarmac – Nguviu Boys – Mwara Njogu Tbc Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5748496 | 5748496 | 5748496 | County Treasury | N/A | 5748496 | N/A | 5748496 | 100% | 5748496 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Issaco Township Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Issaco Township Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5599320 | 5599320 | 5599320 | County Treasury | N/A | 5599320 | N/A | 5599320 | 100% | 5599320 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ishiara – Karerema Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ishiara – Karerema Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5899913 | 5899913 | 5899913 | County Treasury | N/A | 5899913 | N/A | 5899913 | 100% | 5899913 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirie Mugwanjogu Road In Muminji Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirie Mugwanjogu Road In Muminji Ward |  | Muminji |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5847270 | 5847270 | 5847270 | County Treasury | N/A | 5847270 | N/A | 5847270 | 100% | 5847270 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Bat – Riandu Road In Nthawa Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Bat – Riandu Road In Nthawa Ward |  | Nthawa |  | Road | Road | Road | 2019-01-07 | 17/02/2020 | 30/6/2020 | 30/6/2020 | 5100449 | 5100449 | 5100449 | County Treasury | N/A | 5100449 | N/A | 5100449 | 100% | 5100449 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Runyenjes – Kigaa To Bitumen Standards | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Runyenjes – Kigaa To Bitumen Standards |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 33156639 | 33156639 | 33156639 | County Treasury | N/A | 33156639 | N/A | 33156639 | 100% | 33156639 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Kanja – Mukuuri To Bitumen Standards | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Kanja – Mukuuri To Bitumen Standards |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 69988594 | 69988594 | 69988594 | County Treasury | N/A | 69988594 | N/A | 69988594 | 100% | 69988594 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Uchumi Kiambuthi Phase 3 To Bitumen Standard | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Uchumi Kiambuthi Phase 3 To Bitumen Standard |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 9246081 | 9246081 | 9246081 | County Treasury | N/A | 9246081 | N/A | 9246081 | 100% | 9246081 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kivwe – Kithimu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kivwe – Kithimu Road |  | Kithimu |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 5476012 | 5476012 | 5476012 | County Treasury | N/A | 5476012 | N/A | 5476012 | 100% | 5476012 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kairuri – Karuriri Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kairuri – Karuriri Market Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 5767514 | 5767514 | 5767514 | County Treasury | N/A | 5767514 | N/A | 5767514 | 100% | 5767514 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Old B6 At Kcc– Katharaka Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Old B6 At Kcc– Katharaka Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 6854150 | 6854150 | 6854150 | County Treasury | N/A | 6854150 | N/A | 6854150 | 100% | 6854150 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ack Muthege Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ack Muthege Church Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 4206276 | 4206276 | 4206276 | County Treasury | N/A | 4206276 | N/A | 4206276 | 100% | 4206276 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Makima Town – Mwea Game Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Makima Town – Mwea Game Road |  | Mwea |  | Road | Road | Road | 2019-01-07 | 2020-02-04 | 30/6/2020 | 30/6/2020 | 5701400 | 5701400 | 5701400 | County Treasury | N/A | 5701400 | N/A | 5701400 | 100% | 5701400 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading of Bitumen standards of Mate Nthagaiya road Phase II | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading of Bitumen standards of Mate Nthagaiya road Phase II |  |  |  | Road | Road | Road | 2019-01-07 | 16/02/2020 | 30/6/2020 | 30/6/2020 | 9376286 | 9376286 | 9376286 | County Treasury | N/A | 9376286 | N/A | 9376286 | 100% | 9376286 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Market Maintenance-Kagaari North | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced market maintenance costs in the community | Road | Market Maintenance-Kagaari North |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 16/02/2020 | 30/6/2020 | 30/6/2020 | 999630 | 999630 | 999630 | County Treasury | N/A | 999630 | N/A | 999630 | 100% | 999630 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karau Kiethiga Kwa Mbogo Wa Mugambi Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karau Kiethiga Kwa Mbogo Wa Mugambi Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1999251 | 1999251 | 1999251 | County Treasury | N/A | 1999251 | N/A | 1999251 | 100% | 1999251 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurina Peter Road And Kamwingunyi Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurina Peter Road And Kamwingunyi Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 3496913 | 3496913 | 3496913 | County Treasury | N/A | 3496913 | N/A | 3496913 | 100% | 3496913 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurumo Market Road And Murari Kariru Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurumo Market Road And Murari Kariru Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 2499150 | 2499150 | 2499150 | County Treasury | N/A | 2499150 | N/A | 2499150 | 100% | 2499150 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngoiri -Kigumu Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngoiri -Kigumu Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 991695 | 991695 | 991695 | County Treasury | N/A | 991695 | N/A | 991695 | 100% | 991695 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rianjeru-Rwika- Gachoka Market Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rianjeru-Rwika- Gachoka Market Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 3844426 | 3844426 | 3844426 | County Treasury | N/A | 3844426 | N/A | 3844426 | 100% | 3844426 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kibugua Kafumbuta Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kibugua Kafumbuta Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 3593766 | 3593766 | 3593766 | County Treasury | N/A | 3593766 | N/A | 3593766 | 100% | 3593766 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kianjagi Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kianjagi Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1988298 | 1988298 | 1988298 | County Treasury | N/A | 1988298 | N/A | 1988298 | 100% | 1988298 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mwaniki –Kwa Nyaga Wa Loise Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Mwaniki –Kwa Nyaga Wa Loise Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 3597684 | 3597684 | 3597684 | County Treasury | N/A | 3597684 | N/A | 3597684 | 100% | 3597684 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kune Muvuriri Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kune Muvuriri Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1801625 | 1801625 | 1801625 | County Treasury | N/A | 1801625 | N/A | 1801625 | 100% | 1801625 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of 2km Kambu -Gatangiri Road (Mavuria Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of 2km Kambu -Gatangiri Road (Mavuria Ward) |  | Mavuria |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 999456 | 999456 | 999456 | County Treasury | N/A | 999456 | N/A | 999456 | 100% | 999456 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathima Kathangari Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathima Kathangari Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1.298,040.00 | 1.298,040.00 | 1.298,040.00 | County Treasury | N/A | 1.298,040.00 | N/A | 1.298,040.00 | 100% | 1.298,040.00 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamugere- Kevote Ward (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamugere- Kevote Ward (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 2698856 | 2698856 | 2698856 | County Treasury | N/A | 2698856 | N/A | 2698856 | 100% | 2698856 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gikuuri –Gichagi Road (Runyejes Central Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gikuuri –Gichagi Road (Runyejes Central Ward) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1996024 | 1996024 | 1996024 | County Treasury | N/A | 1996024 | N/A | 1996024 | 100% | 1996024 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Murithi Wa Ndogo –Njiru Kathuki (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Murithi Wa Ndogo –Njiru Kathuki (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 3498096 | 3498096 | 3498096 | County Treasury | N/A | 3498096 | N/A | 3498096 | 100% | 3498096 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirigi Gicagi (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirigi Gicagi (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1, 999,835.82 | 1, 999,835.82 | 1, 999,835.82 | County Treasury | N/A | 1, 999,835.82 | N/A | 1, 999,835.82 | 100% | 1, 999,835.82 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngeca –Katharane Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngeca –Katharane Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 1,959,021.00) | 1,959,021.00) | 1,959,021.00) | County Treasury | N/A | 1,959,021.00) | N/A | 1,959,021.00) | 100% | 1,959,021.00) | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Dubai Ciiri Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Dubai Ciiri Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 18/06/2020 | 30/6/2020 | 30/6/2020 | 998852 | 998852 | 998852 | County Treasury | N/A | 998852 | N/A | 998852 | 100% | 998852 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kandete And Iriviro Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kandete And Iriviro Road |  |  |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 1984760 | 1984760 | 1984760 | County Treasury | N/A | 1984760 | N/A | 1984760 | 100% | 1984760 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathanje Sec Sch – Paskware Road(Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathanje Sec Sch – Paskware Road(Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2990161 | 2990161 | 2990161 | County Treasury | N/A | 2990161 | N/A | 2990161 | 100% | 2990161 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening/Maintenance Of Kiereri-Kamukwega Road(Mbeti North Ward) | Clearing, resurfacing | To enchance connectivity and reduce road maintenance cost | New roads and reduced maintenance cost | Road | Opening/Maintenance Of Kiereri-Kamukwega Road(Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 1997346 | 1997346 | 1997346 | County Treasury | N/A | 1997346 | N/A | 1997346 | 100% | 1997346 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangariri Gwa Kaari Kang’ethia Road(Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathangariri Gwa Kaari Kang’ethia Road(Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3991560 | 3991560 | 3991560 | County Treasury | N/A | 3991560 | N/A | 3991560 | 100% | 3991560 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karungu - Kcc Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karungu - Kcc Road |  |  |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3111816 | 3111816 | 3111816 | County Treasury | N/A | 3111816 | N/A | 3111816 | 100% | 3111816 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St. Alphonse Sec Sch – Mwithi Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of St. Alphonse Sec Sch – Mwithi Access Road |  |  |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3108568 | 3108568 | 3108568 | County Treasury | N/A | 3108568 | N/A | 3108568 | 100% | 3108568 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiandathi Kathigari Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiandathi Kathigari Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 1686060 | 1686060 | 1686060 | County Treasury | N/A | 1686060 | N/A | 1686060 | 100% | 1686060 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ntheuni Drift( Mwea Ward) | Excavation, construction | To improve safety, and ccessibilty of towns by roads | Accessible town by vehicles | Road | Construction Of Ntheuni Drift( Mwea Ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2344720 | 2344720 | 2344720 | County Treasury | N/A | 2344720 | N/A | 2344720 | 100% | 2344720 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ntheuni Drift( Mwea Ward) | Excavation, construction | To improve safety, and ccessibilty of towns by roads | Accessible town by vehicles | Road | Construction Of Ntheuni Drift( Mwea Ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2002724 | 2002724 | 2002724 | County Treasury | N/A | 2002724 | N/A | 2002724 | 100% | 2002724 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nembure Karingari Markert Rand And Nembure Academy (Gaturi South Ward). | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nembure Karingari Markert Rand And Nembure Academy (Gaturi South Ward). |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2966932 | 2966932 | 2966932 | County Treasury | N/A | 2966932 | N/A | 2966932 | 100% | 2966932 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Matiru Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Matiru Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3104200 | 3104200 | 3104200 | County Treasury | N/A | 3104200 | N/A | 3104200 | 100% | 3104200 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kagumori Gatareri Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kagumori Gatareri Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3887160 | 3887160 | 3887160 | County Treasury | N/A | 3887160 | N/A | 3887160 | 100% | 3887160 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Dozing For Opening Of Roads In Muminji (Muminji Ward) | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Dozing For Opening Of Roads In Muminji (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3796494 | 3796494 | 3796494 | County Treasury | N/A | 3796494 | N/A | 3796494 | 100% | 3796494 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Kamiungu Bridge (Kagaari North Ward) | Site clearance, excavation, foundation preparation and construction | To enable safe and reliable crossing of vehicles and pedestrians | A well-constructed drift strong and reliable | Road | Construction Of Kamiungu Bridge (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3235221 | 3235221 | 3235221 | County Treasury | N/A | 3235221 | N/A | 3235221 | 100% | 3235221 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mugo Mwithi Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mugo Mwithi Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3491281 | 3491281 | 3491281 | County Treasury | N/A | 3491281 | N/A | 3491281 | 100% | 3491281 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads In Nthawa (Nthawa Ward) | Dozing, grading and Clearing | To enhance connectivity | Accessibility enabled to other towns | Road | Opening Of Roads In Nthawa (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2997338 | 2997338 | 2997338 | County Treasury | N/A | 2997338 | N/A | 2997338 | 100% | 2997338 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Kamukenda - Kandongu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Kamukenda - Kandongu Road |  |  |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2512676 | 2512676 | 2512676 | County Treasury | N/A | 2512676 | N/A | 2512676 | 100% | 2512676 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Ndamunge Kathungu Road (Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Ndamunge Kathungu Road (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3113614 | 3113614 | 2562208 | County Treasury | N/A | 3113614 | N/A | 3113614 | 100% | 3113614 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Kathangari - Kithiruri Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Kathangari - Kithiruri Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2562208 | 2562208 | 2562208 | County Treasury | N/A | 2562208 | N/A | 2562208 | 100% | 2562208 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads In Nthawa Ward (Nthawa Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading Of Roads In Nthawa Ward (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2997208 | 2997208 | 2997208 | County Treasury | N/A | 2997208 | N/A | 2997208 | 100% | 2997208 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiandogo – Gichuki Road (Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiandogo – Gichuki Road (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3198201 | 3198201 | 3198201 | County Treasury | N/A | 3198201 | N/A | 3198201 | 100% | 3198201 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mikuuri Siakago Tarmac Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mikuuri Siakago Tarmac Road (Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2395829 | 2395829 | 2395829 | County Treasury | N/A | 2395829 | N/A | 2395829 | 100% | 2395829 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Kamwe – Kaseveni Road, Maintenance Of Wakalia – Kangocho - Gikumene Road And Maintenance Of Kizito – Gitaraka Girls High Road (Mwea Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Kamwe – Kaseveni Road, Maintenance Of Wakalia – Kangocho - Gikumene Road And Maintenance Of Kizito – Gitaraka Girls High Road (Mwea Ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2998054 | 2998054 | 2998054 | County Treasury | N/A | 2998054 | N/A | 2998054 | 100% | 2998054 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Culverts Installation At Kithare, Mivutiri, Karundori, Kiaragana, Mile Saba Road (Kyeni North Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Culverts Installation At Kithare, Mivutiri, Karundori, Kiaragana, Mile Saba Road (Kyeni North Ward) |  | Kyeni North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2998054 | 2998054 | 2998054 | County Treasury | N/A | 2998054 | N/A | 2998054 | 100% | 2998054 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Muthusi - Musingini Road (Mwea Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Muthusi - Musingini Road (Mwea Ward) |  | Kyeni South |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 999085 | 999085 | 999085 | County Treasury | N/A | 999085 | N/A | 999085 | 100% | 999085 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mugumori - Gakwegori Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mugumori - Gakwegori Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2994523 | 2994523 | 2994523 | County Treasury | N/A | 2994523 | N/A | 2994523 | 100% | 2994523 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamugere – Gituri - Mathiga Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamugere – Gituri - Mathiga Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3445130 | 3445130 | 3445130 | County Treasury | N/A | 3445130 | N/A | 3445130 | 100% | 3445130 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiandari Kwa Mumo Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiandari Kwa Mumo Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3245277 | 3245277 | 3245277 | County Treasury | N/A | 3245277 | N/A | 3245277 | 100% | 3245277 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karimari Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karimari Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3398916 | 3398916 | 3398916 | County Treasury | N/A | 3398916 | N/A | 3398916 | 100% | 3398916 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathera Gatitu Road (Runyenjes Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathera Gatitu Road (Runyenjes Ward) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 2495230 | 2495230 | 2495230 | County Treasury | N/A | 2495230 | N/A | 2495230 | 100% | 2495230 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Prime Road (Kirimari Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Prime Road (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 999808 | 999808 | 999808 | County Treasury | N/A | 999808 | N/A | 999808 | 100% | 999808 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Kwa Musyoka Drift (Mwea Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Construction Of Kwa Musyoka Drift (Mwea Ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 1968965 | 1968965 | 1968965 | County Treasury | N/A | 1968965 | N/A | 1968965 | 100% | 1968965 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance And Installatiion Of Culverts At Kwa Ngila – Kwa Nguli Road (Mwea ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance And Installatiion Of Culverts At Kwa Ngila – Kwa Nguli Road (Mwea ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 949773 | 949773 | 949773 | County Treasury | N/A | 949773 | N/A | 949773 | 100% | 949773 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithanje Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kithanje Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 1983484 | 1983484 | 1983484 | County Treasury | N/A | 1983484 | N/A | 1983484 | 100% | 1983484 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichegori Kwa Sammy Gakure Kang’ethia Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichegori Kwa Sammy Gakure Kang’ethia Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3131420 | 3131420 | 3131420 | County Treasury | N/A | 3131420 | N/A | 3131420 | 100% | 3131420 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngurukiri – Kanginga Road, Maintenance Of Wagaciuru Hague Road, Maintenance Of Gakwegori – Karago Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngurukiri – Kanginga Road, Maintenance Of Wagaciuru Hague Road, Maintenance Of Gakwegori – Karago Road (Kyeni South Ward) |  | Kyeni South |  | Road | Road | Road | 2019-01-07 | 15/06/2020 | 30/6/2020 | 30/6/2020 | 3996490 | 3996490 | 3996490 | County Treasury | N/A | 3996490 | N/A | 3996490 | 100% | 3996490 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rwere Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rwere Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 1196470 | 1196470 | 1196470 | County Treasury | N/A | 1196470 | N/A | 1196470 | 100% | 1196470 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamuriati Bridge Road (Ruguru Ngandori Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamuriati Bridge Road (Ruguru Ngandori Ward) |  | Ruguru Ngandori |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 1499300 | 1499300 | 1499300 | County Treasury | N/A | 1499300 | N/A | 1499300 | 100% | 1499300 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambevo Mivukori Road (Kithimu Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kambevo Mivukori Road (Kithimu Ward) |  | Kithimu |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 2394820 | 2394820 | 2394820 | County Treasury | N/A | 2394820 | N/A | 2394820 | 100% | 2394820 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthiari Road (Runyenjes Central Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muthiari Road (Runyenjes Central Ward) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 3496840 | 3496840 | 3496840 | County Treasury | N/A | 3496840 | N/A | 3496840 | 100% | 3496840 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mikuuri Siakago Tarmack Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mikuuri Siakago Tarmack Road (Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 2395829 | 2395829 | 2395829 | County Treasury | N/A | 2395829 | N/A | 2395829 | 100% | 2395829 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Widening And Maintenance Of Kiumu- Gakwegori Road | Reshaping, drainage repair and resurfacing | To improve traffic flow, enhance safety and extend the lifespan of the road | Widened and well- maintained road | Road | Widening And Maintenance Of Kiumu- Gakwegori Road |  |  |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 2996512 | 2996512 | 2996512 | County Treasury | N/A | 2996512 | N/A | 2996512 | 100% | 2996512 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jane Kiande Kwa Muchangi Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Jane Kiande Kwa Muchangi Road (Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 1497107 | 1497107 | 1497107 | County Treasury | N/A | 1497107 | N/A | 1497107 | 100% | 1497107 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Mbovue Njuki Imwi Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Mbovue Njuki Imwi Road (Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 1797629 | 1797629 | 1797629 | County Treasury | N/A | 1797629 | N/A | 1797629 | 100% | 1797629 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiereri – Kamukwego Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiereri – Kamukwego Road (Mbeti North Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 19/05/2020 | 30/6/2020 | 30/6/2020 | 1997346 | 1997346 | 1997346 | County Treasury | N/A | 1997346 | N/A | 1997346 | 100% | 1997346 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing And Gravelling Of Kombo Munyiri Road (Mbeti South Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Dozing And Gravelling Of Kombo Munyiri Road (Mbeti South Ward) |  | mbeti North |  | Road | Road | Road | 2019-01-07 | 2020-04-05 | 30/6/2020 | 30/6/2020 | 2996744 | 2996744 | 2996744 | County Treasury | N/A | 2996744 | N/A | 2996744 | 100% | 2996744 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Macumo Primary Road, Maintenance Of Kiangusu (Kagaari South) | Procurement, resurfacing, cleaning and cutting grass | To improve connectivityand prevent expenses | Completed road and reduced maintenance cost | Road | Completion Of Macumo Primary Road, Maintenance Of Kiangusu (Kagaari South) |  | Kagaari South |  | Road | Road | Road | 2019-01-07 | 2020-04-05 | 30/6/2020 | 30/6/2020 | 2196664 | 2196664 | 2196664 | County Treasury | N/A | 2196664 | N/A | 2196664 | 100% | 2196664 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiambuthi Sunrise Kabuchoro Road (Kirimari Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiambuthi Sunrise Kabuchoro Road (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 1603895 | 1603895 | 1603895 | County Treasury | N/A | 1603895 | N/A | 1603895 | 100% | 1603895 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nduuri-Magigita Road (Kagaairi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nduuri-Magigita Road (Kagaairi North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2909164 | 2909164 | 2909164 | County Treasury | N/A | 2909164 | N/A | 2909164 | 100% | 2909164 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Three (3) Floodlights At Ciangera Market (Evurori Ward) | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation Of Three (3) Floodlights At Ciangera Market (Evurori Ward) |  | Evuvori |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 1199550 | 1199550 | 1199550 | County Treasury | N/A | 1199550 | N/A | 1199550 | 100% | 1199550 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirongori Mbiruri Road –Maintenace Of Kagondu Road (Runyenjes Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirongori Mbiruri Road –Maintenace Of Kagondu Road (Runyenjes Ward) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2996686 | 2996686 | 2996686 | County Treasury | N/A | 2996686 | N/A | 2996686 | 100% | 2996686 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Gacungu Kagumori Road- Maintenace Of Nyagari Dispensary Hague Road (Kyeni South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Gacungu Kagumori Road- Maintenace Of Nyagari Dispensary Hague Road (Kyeni South Ward) |  | kyeni South |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2798065 | 2798065 | 2798065 | County Treasury | N/A | 2798065 | N/A | 2798065 | 100% | 2798065 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing Of Roads Kiambere Ward (Kiambere Ward) | Clearing, grubbing, cutting and filling | To provide a well-prepared road corridor that supports durable pavememnt construction | well dozed road corridor | Road | Dozing Of Roads Kiambere Ward (Kiambere Ward) |  | Kiambere |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 3499500 | 3499500 | 3499500 | County Treasury | N/A | 3499500 | N/A | 3499500 | 100% | 3499500 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kang’ethia Kwa Gicatha Road-Maintenance Of Kibugu Kithira Road-Gacherori Primary Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kang’ethia Kwa Gicatha Road-Maintenance Of Kibugu Kithira Road-Gacherori Primary Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 3992451 | 3992451 | 3992451 | County Treasury | N/A | 3992451 | N/A | 3992451 | 100% | 3992451 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamisa Gicagi Road-Maintenace Of Ngui Road (Runyenjes Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamisa Gicagi Road-Maintenace Of Ngui Road (Runyenjes Ward) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2498560 | 2498560 | 2498560 | County Treasury | N/A | 2498560 | N/A | 2498560 | 100% | 2498560 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Machinery (Grader) For Road Maintenance Works In Kiambere Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Machinery (Grader) For Road Maintenance Works In Kiambere Ward |  | Kiambere |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 1499834 | 1499834 | 1499834 | County Treasury | N/A | 1499834 | N/A | 1499834 | 100% | 1499834 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gachagori Road-Maintenance Of Kigaa Ack Road (Runyenjes Central) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gachagori Road-Maintenance Of Kigaa Ack Road (Runyenjes Central) |  | Runyejnes |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2990422 | 2990422 | 2990422 | County Treasury | N/A | 2990422 | N/A | 2990422 | 100% | 2990422 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Neburi Viki Iriari Road-Maintenance Of Kamiri Josiah Iriari Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Neburi Viki Iriari Road-Maintenance Of Kamiri Josiah Iriari Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2993032 | 2993032 | 2993032 | County Treasury | N/A | 2993032 | N/A | 2993032 | 100% | 2993032 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts And Drifts (Muminji Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts And Drifts (Muminji Ward) |  | Muminji |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 3999576 | 3999576 | 3999576 | County Treasury | N/A | 3999576 | N/A | 3999576 | 100% | 3999576 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Eapc Nguyori Road-Muganjuki Road ,Opening Of Karimwaro Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Eapc Nguyori Road-Muganjuki Road ,Opening Of Karimwaro Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/06/2020 | 30/6/2020 | 30/6/2020 | 2997417 | 2997417 | 2997417 | County Treasury | N/A | 2997417 | N/A | 2997417 | 100% | 2997417 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathageri Urati Road CompletionOf Ndunduri Kangiga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathageri Urati Road CompletionOf Ndunduri Kangiga Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/06/2020 | 30/6/2020 | 30/6/2020 | 3999576 | 3999576 | 3999576 | County Treasury | N/A | 3999576 | N/A | 3999576 | 100% | 3999576 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Deliverance Church – Modern, Sisto Nyaga And Orion Day Care – Karlo Rudisho Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Deliverance Church – Modern, Sisto Nyaga And Orion Day Care – Karlo Rudisho Road |  |  |  | Road | Road | Road | 2019-01-07 | 17/06/2020 | 30/6/2020 | 30/6/2020 | 3970216 | 3970216 | 3970216 | County Treasury | N/A | 3970216 | N/A | 3970216 | 100% | 3970216 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karue Ngai Ndethia Road (Gaturi North ) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karue Ngai Ndethia Road (Gaturi North ) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 17/06/2020 | 30/6/2020 | 30/6/2020 | 2997556 | 2997556 | 2997556 | County Treasury | N/A | 2997556 | N/A | 2997556 | 100% | 2997556 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangari St. Joseph Road (Gaturi North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathangari St. Joseph Road (Gaturi North) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 17/06/2020 | 30/6/2020 | 30/6/2020 | 2998136 | 2998136 | 2998136 | County Treasury | N/A | 2998136 | N/A | 2998136 | 100% | 2998136 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngo’ngi – Mivukori Road Maintenance /Widening Of Gatumu – Mbirori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngo’ngi – Mivukori Road Maintenance /Widening Of Gatumu – Mbirori Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3643166 | 3643166 | 3643166 | County Treasury | N/A | 3643166 | N/A | 3643166 | 100% | 3643166 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithimu Market Access Road Maintenance Of Gitumbi Kwa John Mathanjuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kithimu Market Access Road Maintenance Of Gitumbi Kwa John Mathanjuki Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3119414 | 3119414 | 3119414 | County Treasury | N/A | 3119414 | N/A | 3119414 | 100% | 3119414 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance/Widening Of Kavaruka – Kwa Karuru – Iganjagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance/Widening Of Kavaruka – Kwa Karuru – Iganjagi Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3214998 | 3214998 | 3214998 | County Treasury | N/A | 3214998 | N/A | 3214998 | 100% | 3214998 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St Michael Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of St Michael Primary School Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 998887 | 998887 | 998887 | County Treasury | N/A | 998887 | N/A | 998887 | 100% | 998887 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Muindi – Kwa Gichoni Feeder Roads, Maintenance Of Gachichiro Kathungu Road (Kagaari South) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Muindi – Kwa Gichoni Feeder Roads, Maintenance Of Gachichiro Kathungu Road (Kagaari South) |  | Kagaari South |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3721976 | 3721976 | 3721976 | County Treasury | N/A | 3721976 | N/A | 3721976 | 100% | 3721976 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchangi Maguta Kathuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muchangi Maguta Kathuriri Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 898594 | 898594 | 898594 | County Treasury | N/A | 898594 | N/A | 898594 | 100% | 898594 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing Of Gaturi Access Road | Clearing, grubbing, cutting and filling | To provide a well-prepared road corridor that supports durable pavememnt construction | well dozed road corridor | Road | Dozing Of Gaturi Access Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 999340 | 999340 | 999340 | County Treasury | N/A | 999340 | N/A | 999340 | 100% | 999340 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathiri – Gituri And Karue Road Maintenance Of Karume – Kathigai – Ambogo Road (Gaturi North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathiri – Gituri And Karue Road Maintenance Of Karume – Kathigai – Ambogo Road (Gaturi North) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 2546699 | 2546699 | 2546699 | County Treasury | N/A | 2546699 | N/A | 2546699 | 100% | 2546699 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance F Kiethetu – Kavutiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance F Kiethetu – Kavutiri Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 983912 | 983912 | 983912 | County Treasury | N/A | 983912 | N/A | 983912 | 100% | 983912 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nthamari – 1st Kenya Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nthamari – 1st Kenya Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 999630 | 999630 | 999630 | County Treasury | N/A | 999630 | N/A | 999630 | 100% | 999630 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Old Stadium Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Old Stadium Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 1998668 | 1998668 | 1998668 | County Treasury | N/A | 1998668 | N/A | 1998668 | 100% | 1998668 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Keruri Road,Maintenance Of Makengi – Gicagi Road,Maintenance Of Mathiga – Ngerueri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Keruri Road,Maintenance Of Makengi – Gicagi Road,Maintenance Of Mathiga – Ngerueri Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3495373 | 3495373 | 3495373 | County Treasury | N/A | 3495373 | N/A | 3495373 | 100% | 3495373 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Njeki – Dispensary Road Completion Of Ena Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Njeki – Dispensary Road Completion Of Ena Market Road |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3478840 | 3478840 | 3478840 | County Treasury | N/A | 3478840 | N/A | 3478840 | 100% | 3478840 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriru Kathimba Road, Kathiakari And Kiamatuto | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiriru Kathimba Road, Kathiakari And Kiamatuto |  |  |  | Road | Road | Road | 2019-01-07 | 16/04/2020 | 30/6/2020 | 30/6/2020 | 3496170 | 3496170 | 3496170 | County Treasury | N/A | 3496170 | N/A | 3496170 | 100% | 3496170 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Kanjiri Gabions (Kagaari North) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Kanjiri Gabions (Kagaari North) |  | kagaari North |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 |  |  |  | County Treasury | N/A
| Completion Of Naivas Stadium Road (Kirimari Ward) | Roofing, seating installation, lighting system | To provide a fully functional, safe and modern sports and events facility | Completed stadium holding events | Road | Completion Of Naivas Stadium Road (Kirimari Ward) |  | Kirimari |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 1994910 | 1994910 | 1994910 | County Treasury | N/A | 1994910 | N/A | 1994910 | 100% | 1994910 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Manual Shaping Of Mugurumari Forest Road (Nginda Ward) | Trimming and levelling | To improve surface uniforminty, drainage and efficiency | Aligned reoad of the perfect width and surface level | Road | Manual Shaping Of Mugurumari Forest Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2490312 | 2490312 | 2490312 | County Treasury | N/A | 2490312 | N/A | 2490312 | 100% | 2490312 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rutune Kiandari Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rutune Kiandari Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 3991108 | 3991108 | 3991108 | County Treasury | N/A | 3991108 | N/A | 3991108 | 100% | 3991108 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuvori – Karau Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbuvori – Karau Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 1499532 | 1499532 | 1499532 | County Treasury | N/A | 1499532 | N/A | 1499532 | 100% | 1499532 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rupingazi Ruma Tpc Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rupingazi Ruma Tpc Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2494140 | 2494140 | 2494140 | County Treasury | N/A | 2494140 | N/A | 2494140 | 100% | 2494140 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathakwa Sec School Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathakwa Sec School Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 997020 | 997020 | 997020 | County Treasury | N/A | 997020 | N/A | 997020 | 100% | 997020 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Selected Roads In The Ward (Mbeti South) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Gravelling Of Selected Roads In The Ward (Mbeti South) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2391938 | 2391938 | 2391938 | County Treasury | N/A | 2391938 | N/A | 2391938 | 100% | 2391938 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads (Mbeti South) | Clearing, excavation and cutting | To establish a defined and accessible roadway | Improved connectivity | Road | Opening Of Roads (Mbeti South) |  | mbeti south |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2998890 | 2998890 | 2998890 | County Treasury | N/A | 2998890 | N/A | 2998890 | 100% | 2998890 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Itangiri Karwigi Road (Mbeti South) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Itangiri Karwigi Road (Mbeti South) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2990132 | 2990132 | 2990132 | County Treasury | N/A | 2990132 | N/A | 2990132 | 100% | 2990132 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Road Maintenance Works (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Road Maintenance Works (Mbeti South Ward) |  | Mbeti south |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 1999190 | 1999190 | 1999190 | County Treasury | N/A | 1999190 | N/A | 1999190 | 100% | 1999190 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanduu – Kathuriri – Itabua Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanduu – Kathuriri – Itabua Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-03-04 | 30/6/2020 | 30/6/2020 | 2998223 | 2998223 | 2998223 | County Treasury | N/A | 2998223 | N/A | 2998223 | 100% | 2998223 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Njumbiri Loop Road(Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Njumbiri Loop Road(Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3097014 | 3097014 | 3097014 | County Treasury | N/A | 3097014 | N/A | 3097014 | 100% | 3097014 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kasarani – Rupingazi Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kasarani – Rupingazi Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3594845 | 3594845 | 3594845 | County Treasury | N/A | 3594845 | N/A | 3594845 | 100% | 3594845 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Itabua Secondary School Ng’eng’e Road (Mbeti North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Itabua Secondary School Ng’eng’e Road (Mbeti North) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2696072 | 2696072 | 2696072 | County Treasury | N/A | 2696072 | N/A | 2696072 | 100% | 2696072 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kevote Karue Road(Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kevote Karue Road(Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2099139 | 2099139 | 2099139 | County Treasury | N/A | 2099139 | N/A | 2099139 | 100% | 2099139 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kanyorora Road(Runyenjes Central Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kanyorora Road(Runyenjes Central Ward) |  | Runyenjes |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2104994 | 2104994 | 2104994 | County Treasury | N/A | 2104994 | N/A | 2104994 | 100% | 2104994 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiang’ombe (Runyenjes Central Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiang’ombe (Runyenjes Central Ward) |  | Runyenjes |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2886706 | 2886706 | 2886706 | County Treasury | N/A | 2886706 | N/A | 2886706 | 100% | 2886706 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Karatina – Mutivi Road (Evurore Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Karatina – Mutivi Road (Evurore Ward) |  | Evurore Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1997098 | 1997098 | 1997098 | County Treasury | N/A | 1997098 | N/A | 1997098 | 100% | 1997098 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Weru’s County Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Weru’s County Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1998078 | 1998078 | 1998078 | County Treasury | N/A | 1998078 | N/A | 1998078 | 100% | 1998078 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Mukui-Muragari Road (Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Mukui-Muragari Road (Kagaari North Ward) |  | Kagaari North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3534682 | 3534682 | 3534682 | County Treasury | N/A | 3534682 | N/A | 3534682 | 100% | 3534682 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance/Installation of Culverts at Kwa Kimilu-Kilia Road(Mwea Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Maintenance/Installation of Culverts at Kwa Kimilu-Kilia Road(Mwea Ward) |  | Mwea |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1496290 | 1496290 | 1496290 | County Treasury | N/A | 1496290 | N/A | 1496290 | 100% | 1496290 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiathi – Kanyariri Road(Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiathi – Kanyariri Road(Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1498186 | 1498186 | 1498186 | County Treasury | N/A | 1498186 | N/A | 1498186 | 100% | 1498186 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngimari – Munyori Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngimari – Munyori Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1496846 | 1496846 | 1496846 | County Treasury | N/A | 1496846 | N/A | 1496846 | 100% | 1496846 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Riverside Tende Road and Maintenance of Karurina and Gicagi Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Riverside Tende Road and Maintenance of Karurina and Gicagi Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3998021 | 3998021 | 3998021 | County Treasury | N/A | 3998021 | N/A | 3998021 | 100% | 3998021 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiambogo Road and Maintenance of Gatunduri Road (Gaturi South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiambogo Road and Maintenance of Gatunduri Road (Gaturi South Ward) |  | Gaturi South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3494616 | 3494616 | 3494616 | County Treasury | N/A | 3494616 | N/A | 3494616 | 100% | 3494616 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kathangari Junction Gituri Primary | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kathangari Junction Gituri Primary |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1275884 | 1275884 | 1275884 | County Treasury | N/A | 1275884 | N/A | 1275884 | 100% | 1275884 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Hire of Machinery (A Grader) for Road Maintenance works and opening and Grading of Kiandomba – Mbarwaro | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire of Machinery (A Grader) for Road Maintenance works and opening and Grading of Kiandomba – Mbarwaro |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3778462 | 3778462 | 3778462 | County Treasury | N/A | 3778462 | N/A | 3778462 | 100% | 3778462 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Majengo road (Kirimari Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Majengo road (Kirimari Ward) |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1484622 | 1484622 | 1484622 | County Treasury | N/A | 1484622 | N/A | 1484622 | 100% | 1484622 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Muthigi –Kiungu Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Muthigi –Kiungu Road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1990326 | 1990326 | 1990326 | County Treasury | N/A | 1990326 | N/A | 1990326 | 100% | 1990326 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiamagai –Nthambo – Kibogi (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiamagai –Nthambo – Kibogi (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1496017 | 1496017 | 1496017 | County Treasury | N/A | 1496017 | N/A | 1496017 | 100% | 1496017 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ruvutiri Ngurueri Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ruvutiri Ngurueri Road (Gaturi North Ward) |  | Gaturi North |  |  | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2997176 | 2997176 | 2997176 | County Treasury | N/A | 2997176 | N/A | 2997176 | 100% | 2997176 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance/Widening of Kinyango Dumpsite – Don Bosco (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance/Widening of Kinyango Dumpsite – Don Bosco (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3994332 | 3994332 | 3994332 | County Treasury | N/A | 3994332 | N/A | 3994332 | 100% | 3994332 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance/Clearing of Kinyango Dumpsite and Access Road (Mbeti North Ward) | Clearing, burning | To provide a safe and a clean environment | Well-maintained road and a managed dumpsite | Road | Maintenance/Clearing of Kinyango Dumpsite and Access Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 995356 | 995356 | 995356 | County Treasury | N/A | 995356 | N/A | 995356 | 100% | 995356 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of A9 Junction to Kwa Rasta Road (Mbeti North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of A9 Junction to Kwa Rasta Road (Mbeti North Ward) |  | Mbeti North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3180315 | 3180315 | 3180315 | County Treasury | N/A | 3180315 | N/A | 3180315 | 100% | 3180315 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Muchagori – Muva Road, Maintenance of Kianyangi-s A Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Muchagori – Muva Road, Maintenance of Kianyangi-s A Road (Gaturi North Ward) |  | Gaturi North Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3393199 | 3393199 | 3393199 | County Treasury | N/A | 3393199 | N/A | 3393199 | 100% | 3393199 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Nguiri – Kamuvoro Road (Gaturi North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Nguiri – Kamuvoro Road (Gaturi North) |  | gaturi North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2195731 | 2195731 | 2195731 | County Treasury | N/A | 2195731 | N/A | 2195731 | 100% | 2195731 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gichugu – Ikunguru Road (Gaturi North) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gichugu – Ikunguru Road (Gaturi North) |  | gaturi North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1997063 | 1997063 | 1997063 | County Treasury | N/A | 1997063 | N/A | 1997063 | 100% | 1997063 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of First Kenyan – Kathigai – Kakato – Kariguri Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of First Kenyan – Kathigai – Kakato – Kariguri Road (Gaturi North Ward) |  | Gaturi North Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1578719 | 1578719 | 1578719 | County Treasury | N/A | 1578719 | N/A | 1578719 | 100% | 1578719 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gaikiro – Kithunguthia Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gaikiro – Kithunguthia Road (Gaturi North Ward) |  | Gaturi North |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2489635 | 2489635 | 2489635 | County Treasury | N/A | 2489635 | N/A | 2489635 | 100% | 2489635 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Zoori – Kianjeru – Gatitu Road (Gaturi North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Zoori – Kianjeru – Gatitu Road (Gaturi North Ward) |  | Gaturi North Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2196928 | 2196928 | 2196928 | County Treasury | N/A | 2196928 | N/A | 2196928 | 100% | 2196928 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gitongoro – Kiegucu – Karimi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gitongoro – Kiegucu – Karimi Road |  | Karimi |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2189324 | 2189324 | 2189324 | County Treasury | N/A | 2189324 | N/A | 2189324 | 100% | 2189324 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts in New Road and Construction of Mbaraga Primary and Secondary Culverts plus on line of Culvert (Evurore Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts in New Road and Construction of Mbaraga Primary and Secondary Culverts plus on line of Culvert (Evurore Ward) |  | Evurore Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2498281 | 2498281 | 2498281 | County Treasury | N/A | 2498281 | N/A | 2498281 | 100% | 2498281 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kangaru Roads, Installation of Culverts at Riamaciri and Chirst Isaiah Dallas ( Kirimari Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Maintenance of Kangaru Roads, Installation of Culverts at Riamaciri and Chirst Isaiah Dallas ( Kirimari Ward) |  | Kirimari Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2291856 | 2291856 | 2291856 | County Treasury | N/A | 2291856 | N/A | 2291856 | 100% | 2291856 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngandi Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngandi Road (Nginda Ward) |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1496934 | 1496934 | 1496934 | County Treasury | N/A | 1496934 | N/A | 1496934 | 100% | 1496934 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiangeni – Musingini Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiangeni – Musingini Road |  |  |  | Road | Road |  | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1486907 | 1486907 | 1486907 | County Treasury | N/A | 1486907 | N/A | 1486907 | 100% | 1486907 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kamutungi – Mwonge Road (Mbeti South Ward) | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Opening and Grading of Kamutungi – Mwonge Road (Mbeti South Ward) |  | Mbeti South Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2597376 | 2597376 | 2597376 | County Treasury | N/A | 2597376 | N/A | 2597376 | 100% | 2597376 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngirimari kwa Thegetha Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngirimari kwa Thegetha Road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3646746 | 3646746 | 3646746 | County Treasury | N/A | 3646746 | N/A | 3646746 | 100% | 3646746 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ndamunge Kathugu Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ndamunge Kathugu Road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3101541 | 3101541 | 3101541 | County Treasury | N/A | 3101541 | N/A | 3101541 | 100% | 3101541 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Karuriri – Gicagi Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Karuriri – Gicagi Road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2086781 | 2086781 | 2086781 | County Treasury | N/A | 2086781 | N/A | 2086781 | 100% | 2086781 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Various Roads in Makima (Makima Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Various Roads in Makima (Makima Ward) |  | makima Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3487118 | 3487118 | 3487118 | County Treasury | N/A | 3487118 | N/A | 3487118 | 100% | 3487118 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gatitu Road (Runyenjes Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gatitu Road (Runyenjes Ward) |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1996106 | 1996106 | 1996106 | County Treasury | N/A | 1996106 | N/A | 1996106 | 100% | 1996106 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Hire of Machinery Bull Dozer for various Roads (Makima Ward) | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire of Machinery Bull Dozer for various Roads (Makima Ward) |  | Makima |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3497610 | 3497610 | 3497610 | County Treasury | N/A | 3497610 | N/A | 3497610 | 100% | 3497610 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Hire of Machinery (Bull Dozer and a Grader) for road works (Evurore Ward) | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire of Machinery (Bull Dozer and a Grader) for road works (Evurore Ward) |  | Evurore |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3994395 | 3994395 | 3994395 | County Treasury | N/A | 3994395 | N/A | 3994395 | 100% | 3994395 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kathangariri Factory Muguramari TBC road, Maintenance of Wacumbi – Kathigari Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kathangariri Factory Muguramari TBC road, Maintenance of Wacumbi – Kathigari Road (Nginda Ward) |  | Nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2990933 | 2990933 | 2990933 | County Treasury | N/A | 2990933 | N/A | 2990933 | 100% | 2990933 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngarari Road, Maintenance of Mbiruri Nduuri Junction (Runyenjes Central Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngarari Road, Maintenance of Mbiruri Nduuri Junction (Runyenjes Central Ward) |  | Runyenjes Central Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1758393 | 1758393 | 1758393 | County Treasury | N/A | 1758393 | N/A | 1758393 | 100% | 1758393 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Rwika by-pass Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Rwika by-pass Road (Mbeti South Ward) |  | mbeti south Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2497512 | 2497512 | 2497512 | County Treasury | N/A | 2497512 | N/A | 2497512 | 100% | 2497512 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Nguru-Itabua Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Nguru-Itabua Road |  | itabua road |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1695978 | 1695978 | 1695978 | County Treasury | N/A | 1695978 | N/A | 1695978 | 100% | 1695978 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murraming of Shauri Market Road (Kirimari Ward) | Clearing and levelling | To improve ground stability, drainage and accessibility within the market area | Enhanced functionality, hygine | Road | Murraming of Shauri Market Road (Kirimari Ward) |  | kirimari Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 999267 | 999267 | 999267 | County Treasury | N/A | 999267 | N/A | 999267 | 100% | 999267 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kibugu kwa Sub-chief Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kibugu kwa Sub-chief Road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 3,799.996.00 | 3,799.996.00 | 3,799.996.00 | County Treasury | N/A | 3,799.996.00 | N/A | 3,799.996.00 | 100% | 3,799.996.00 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Njue Junction _ Njagi wa Mboso- Kibugu road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Njue Junction _ Njagi wa Mboso- Kibugu road (Nginda Ward) |  | Nginda Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 2991588 | 2991588 | 2991588 | County Treasury | N/A | 2991588 | N/A | 2991588 | 100% | 2991588 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kamwimbi – Kariguri Road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kamwimbi – Kariguri Road (Mbeti South Ward) |  | Mbeti South |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 999609 | 999609 | 999609 | County Treasury | N/A | 999609 | N/A | 999609 | 100% | 999609 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ndarwa Road (Mbeti South) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ndarwa Road (Mbeti South) |  |  |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1695522 | 1695522 | 1695522 | County Treasury | N/A | 1695522 | N/A | 1695522 | 100% | 1695522 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiandari Mururiri Kathigai Road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiandari Mururiri Kathigai Road (Nginda Ward) |  | Nginda |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1794519 | 1794519 | 1794519 | County Treasury | N/A | 1794519 | N/A | 1794519 | 100% | 1794519 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kanyonga Karigu Primary – Newsite Posho mill Junction roa Kiambere ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kanyonga Karigu Primary – Newsite Posho mill Junction roa Kiambere ward |  | Junction roa Kiambere ward |  | Road | Road | Road | 2019-01-07 | 2020-08-06 | 30/6/2020 | 30/6/2020 | 1997172 | 1997172 | 1997172 | County Treasury | N/A | 1997172 | N/A | 1997172 | 100% | 1997172 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Mufu-Kaurndori road and Kavuriri-Kathiruri road (Kyeni North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Mufu-Kaurndori road and Kavuriri-Kathiruri road (Kyeni North Ward) |  | Kyeni North Ward |  | Road | Road | Road | 2019-01-07 | 2020-08-06 | 30/6/2020 | 30/6/2020 | 2498270 | 2498270 | 2498270 | County Treasury | N/A | 2498270 | N/A | 2498270 | 100% | 2498270 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kanyakiri-kwa Mugo road (Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kanyakiri-kwa Mugo road (Kagaari North Ward) |  | kagaari north Ward |  | Road | Road | Road | 2019-01-07 | 2020-08-06 | 30/6/2020 | 30/6/2020 | 3996086 | 3996086 | 3996086 | County Treasury | N/A | 3996086 | N/A | 3996086 | 100% | 3996086 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Weru – County road (Mbeti South Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Weru – County road (Mbeti South Ward) |  | mbeti south Ward |  | Road | Road | Road | 2019-01-07 | 22/06/2020 | 30/6/2020 | 30/6/2020 | 1997098 | 1997098 | 1997098 | County Treasury | N/A | 1997098 | N/A | 1997098 | 100% | 1997098 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Rehabilitation of Gakuu drift (Nthawa Ward) | Clearing and excavation of damaged sections | To restore the structural integrity, safety and functionallity | Safe, durable and reliable crossing | Road | Rehabilitation of Gakuu drift (Nthawa Ward) |  |  |  | Road | Road | Road | 2019-01-07 | 2020-01-07 | 30/6/2020 | 30/6/2020 | 599526 | 599526 | 599526 | County Treasury | N/A | 599526 | N/A | 599526 | 100% | 599526 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiangari-Gaciku road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiangari-Gaciku road |  | kiangari-gaciku road |  | Road | Road | Road | 2019-01-07 | 2020-01-07 | 30/6/2020 | 30/6/2020 | 1992948 | 1992948 | 1992948 | County Treasury | N/A | 1992948 | N/A | 1992948 | 100% | 1992948 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kirie-Nduuri road (Kagaari North Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kirie-Nduuri road (Kagaari North Ward) |  | kagaari north Ward |  | Road | Road | Road | 2019-01-07 | 2020-01-07 | 30/6/2020 | 30/6/2020 | 999456 | 999456 | 999456 | County Treasury | N/A | 999456 | N/A | 999456 | 100% | 999456 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation of culverts and drift repair of Itira Karimari road, Repair of Thura Micegethiu drift – Muminji ward, Installation of culverts and repair of Kiogora drift Gatothia (Muminji Ward) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of culverts and drift repair of Itira Karimari road, Repair of Thura Micegethiu drift – Muminji ward, Installation of culverts and repair of Kiogora drift Gatothia (Muminji Ward) |  | Muminji Ward |  | Road | Road | Road | 2019-01-07 | 2020-01-07 | 30/6/2020 | 30/6/2020 | 2799498 | 2799498 | 2799498 | County Treasury | N/A | 2799498 | N/A | 2799498 | 100% | 2799498 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction of Kiriiri drift Phase II | Site clearance, excavation, foundation preparation and construction | To provide a safe, durable and reliable passage | A cost effective and resilient crossing solution | Road | Construction of Kiriiri drift Phase II |  |  |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 1399293 | 1399293 | 1399293 | County Treasury | N/A | 1399293 | N/A | 1399293 | 100% | 1399293 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiegucu-Karimi Nguviu road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiegucu-Karimi Nguviu road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2065224 | 2065224 | 2065224 | County Treasury | N/A | 2065224 | N/A | 2065224 | 100% | 2065224 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction of Box Culvert at Kathangariri Mwea game reserve | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Construction of Box Culvert at Kathangariri Mwea game reserve |  | game |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 3778881 | 3778881 | 3778881 | County Treasury | N/A | 3778881 | N/A | 3778881 | 100% | 3778881 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Murraming of Nguthiru Mungunguri raod (Mbeti SouthWard) | Clearing and levelling | To improve ground stability, drainage and accessibility within the market area | Enhanced functionality, hygine | Road | Murraming of Nguthiru Mungunguri raod (Mbeti SouthWard) |  | mbeti SouthWard |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 1498221 | 1498221 | 1498221 | County Treasury | N/A | 1498221 | N/A | 1498221 | 100% | 1498221 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Rehabilitation of rweria drift – rehabilitation of Kithanga drift – Installation of Kambora culverts, installation of culverts for Mathai road (Nthawa Ward) | Clearing and excavation of damaged sections | To restore the structural integrity, safety and functionallity | Safe, durable and reliable crossing | Road | Rehabilitation of rweria drift – rehabilitation of Kithanga drift – Installation of Kambora culverts, installation of culverts for Mathai road (Nthawa Ward) |  | Nthawa |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2484989 | 2484989 | 2484989 | County Treasury | N/A | 2484989 | N/A | 2484989 | 100% | 2484989 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Zouri –Munyori – Kianjeru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Zouri –Munyori – Kianjeru Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-09-07 | 30/6/2020 | 30/6/2020 | 2197806 | 2197806 | 2197806 | County Treasury | N/A | 2197806 | N/A | 2197806 | 100% | 2197806 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of BAT Tarmac Nguruka Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of BAT Tarmac Nguruka Road |  |  |  | Road | Road | Road | 2019-01-07 | 2020-09-07 | 30/6/2020 | 30/6/2020 | 2397192 | 2397192 | 2397192 | County Treasury | N/A | 2397192 | N/A | 2397192 | 100% | 2397192 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gichugu-Ikunguru road kwa Women road (Nginda Ward) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gichugu-Ikunguru road kwa Women road (Nginda Ward) |  | nginda Ward |  | Road | Road | Road | 2019-01-07 | 2020-01-07 | 30/6/2020 | 30/6/2020 | 1999440 | 1999440 | 1999440 | County Treasury | N/A | 1999440 | N/A | 1999440 | 100% | 1999440 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gituva –Rupingazi road (Mbeti South) | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gituva –Rupingazi road (Mbeti South) |  | Mbeti |  | Road | Road | Road | 2019-01-07 | 25/06/2020 | 30/6/2020 | 30/6/2020 | 2085065 | 2085065 | 2085065 | County Treasury | N/A | 2085065 | N/A | 2085065 | 100% | 2085065 | N/A | N/A | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2018/2019
| Maintenance Of Rugumu Kiangosi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rugumu Kiangosi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1948661 | 1948661 | 1948661 | County Treasury | N/A | 1948661 | N/A | 1948661 | 100% | 1948661 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambevo Kagumori Karimari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kambevo Kagumori Karimari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3042048 | 3042048 | 3042048 | County Treasury | N/A | 3042048 | N/A | 3042048 | 100% | 3042048 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nguviu Ngerwe | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nguviu Ngerwe |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2399112 | 2399112 | 2399112 | County Treasury | N/A | 2399112 | N/A | 2399112 | 100% | 2399112 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gati Iguru Tea Buying Centre Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gati Iguru Tea Buying Centre Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5099418 | 5099418 | 5099418 | County Treasury | N/A | 5099418 | N/A | 5099418 | 100% | 5099418 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngosi /Nguthi Bridge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngosi /Nguthi Bridge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5099418 | 5099418 | 5099418 | County Treasury | N/A | 5099418 | N/A | 5099418 | 100% | 5099418 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Renji- Kiandari Kagumori | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Renji- Kiandari Kagumori |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1963277 | 1963277 | 1963277 | County Treasury | N/A | 1963277 | N/A | 1963277 | 100% | 1963277 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndunda Ngerwe Gakurungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ndunda Ngerwe Gakurungu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1974013 | 1974013 | 1974013 | County Treasury | N/A | 1974013 | N/A | 1974013 | 100% | 1974013 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthigi Kiungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muthigi Kiungu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1991766 | 1991766 | 1991766 | County Treasury | N/A | 1991766 | N/A | 1991766 | 100% | 1991766 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karuari- Mukongoro Kwa Gichonge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karuari- Mukongoro Kwa Gichonge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1923740 | 1923740 | 1923740 | County Treasury | N/A | 1923740 | N/A | 1923740 | 100% | 1923740 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenanace Of Gicherori- Kwa Gakure- Kiamuvuro A And B | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenanace Of Gicherori- Kwa Gakure- Kiamuvuro A And B |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2871610 | 2871610 | 2871610 | County Treasury | N/A | 2871610 | N/A | 2871610 | 100% | 2871610 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutira Iguru –Kabugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutira Iguru –Kabugu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1999817 | 1999817 | 1999817 | County Treasury | N/A | 1999817 | N/A | 1999817 | 100% | 1999817 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthigi Ack Kiangosi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muthigi Ack Kiangosi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2140650 | 2140650 | 2140650 | County Treasury | N/A | 2140650 | N/A | 2140650 | 100% | 2140650 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kavari Thambana Kiandari Rupingasi | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kavari Thambana Kiandari Rupingasi |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2493037 | 2493037 | 2493037 | County Treasury | N/A | 2493037 | N/A | 2493037 | 100% | 2493037 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthigi To Kiangichu Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muthigi To Kiangichu Access Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1992184 | 1992184 | 1992184 | County Treasury | N/A | 1992184 | N/A | 1992184 | 100% | 1992184 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2451614 | 2451614 | 2451614 | County Treasury | N/A | 2451614 | N/A | 2451614 | 100% | 2451614 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading Of Various Roads In Nginda | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Various Roads In Nginda |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2451614 | 2451614 | 2451614 | County Treasury | N/A | 2451614 | N/A | 2451614 | 100% | 2451614 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gravelling Of Various Roads In Nginda | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling Of Various Roads In Nginda |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1478246 | 1478246 | 1478246 | County Treasury | N/A | 1478246 | N/A | 1478246 | 100% | 1478246 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muvandori – Kauga Tbc Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muvandori – Kauga Tbc Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1440928 | 1440928 | 1440928 | County Treasury | N/A | 1440928 | N/A | 1440928 | 100% | 1440928 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Anthonio – Ngunyumu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Anthonio – Ngunyumu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2633722 | 2633722 | 2633722 | County Treasury | N/A | 2633722 | N/A | 2633722 | 100% | 2633722 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenanace Of Kwa Nguo Ngarari Tbc – Kwa William Bridge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenanace Of Kwa Nguo Ngarari Tbc – Kwa William Bridge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2886776 | 2886776 | 2886776 | County Treasury | N/A | 2886776 | N/A | 2886776 | 100% | 2886776 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngirimari Kwa Thegetha Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngirimari Kwa Thegetha Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3655912 | 3655912 | 3655912 | County Treasury | N/A | 3655912 | N/A | 3655912 | 100% | 3655912 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Mathanjuki – Gachiigi Kwa Bedan Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Mathanjuki – Gachiigi Kwa Bedan Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2888110 | 2888110 | 2888110 | County Treasury | N/A | 2888110 | N/A | 2888110 | 100% | 2888110 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndiuri Kiruari Kwa Kiivia Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ndiuri Kiruari Kwa Kiivia Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499836 | 3499836 | 3499836 | County Treasury | N/A | 3499836 | N/A | 3499836 | 100% | 3499836 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriari Kathangari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiriari Kathangari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3085600 | 3085600 | 3085600 | County Treasury | N/A | 3085600 | N/A | 3085600 | 100% | 3085600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gicagi Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gicagi Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 999804 | 999804 | 999804 | County Treasury | N/A | 999804 | N/A | 999804 | 100% | 999804 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kairuri- Kiriari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kairuri- Kiriari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3484585 | 3484585 | 3484585 | County Treasury | N/A | 3484585 | N/A | 3484585 | 100% | 3484585 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kibugua Kairuri | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kibugua Kairuri |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3495022 | 3495022 | 3495022 | County Treasury | N/A | 3495022 | N/A | 3495022 | 100% | 3495022 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Kamuruati Box Culvert | Site preparation, excavation and construction | To provide a safe and durable passage for road traffic | Managed storm water | Road | Construction Of Kamuruati Box Culvert |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2981047 | 2981047 | 2981047 | County Treasury | N/A | 2981047 | N/A | 2981047 | 100% | 2981047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rianjagi Bridge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rianjagi Bridge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1999246 | 1999246 | 1999246 | County Treasury | N/A | 1999246 | N/A | 1999246 | 100% | 1999246 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kabara Bridge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kabara Bridge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1765885 | 1765885 | 1765885 | County Treasury | N/A | 1765885 | N/A | 1765885 | 100% | 1765885 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction Of Ngosi Bridge | Excavation, foundation preparation and construction | To provide a safe and durable passage for road traffic | A strong, duarable and reliable bridge | Road | Construction Of Ngosi Bridge |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3898713 | 3898713 | 3898713 | County Treasury | N/A | 3898713 | N/A | 3898713 | 100% | 3898713 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A |  | N/A
| Maintenance Of Manyatta Do’s Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Manyatta Do’s Access Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2476368 | 2476368 | 2476368 | County Treasury | N/A | 2476368 | N/A | 2476368 | 100% | 2476368 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karoriri – Kairuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karoriri – Kairuri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2476368 | 2476368 | 2476368 | County Treasury | N/A | 2476368 | N/A | 2476368 | 100% | 2476368 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirege- Ngurweri Road Maintenance Of Wamutema Gwa Ufo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirege- Ngurweri Road Maintenance Of Wamutema Gwa Ufo Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1984732 | 1984732 | 1984732 | County Treasury | N/A | 1984732 | N/A | 1984732 | 100% | 1984732 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Igumo, Kwa Elijah Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Igumo, Kwa Elijah Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2987812 | 2987812 | 2987812 | County Treasury | N/A | 2987812 | N/A | 2987812 | 100% | 2987812 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rukuriri- Mutira Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rukuriri- Mutira Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2987812 | 2987812 | 2987812 | County Treasury | N/A | 2987812 | N/A | 2987812 | 100% | 2987812 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nthunguri Gitwa Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nthunguri Gitwa Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2987812 | 2987812 | 2987812 | County Treasury | N/A | 2987812 | N/A | 2987812 | 100% | 2987812 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Iriari Kithare Kanduviu Mutateru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Iriari Kithare Kanduviu Mutateru Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3497055 | 3497055 | 3497055 | County Treasury | N/A | 3497055 | N/A | 3497055 | 100% | 3497055 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mufu Kiangungi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mufu Kiangungi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3497055 | 3497055 | 3497055 | County Treasury | N/A | 3497055 | N/A | 3497055 | 100% | 3497055 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Iriari- Kiaragana Njeruri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Iriari- Kiaragana Njeruri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499760 | 3499760 | 3499760 | County Treasury | N/A | 3499760 | N/A | 3499760 | 100% | 3499760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karigiri Njeruri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karigiri Njeruri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499760 | 3499760 | 3499760 | County Treasury | N/A | 3499760 | N/A | 3499760 | 100% | 3499760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathari Coffee Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathari Coffee Factory Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499760 | 3499760 | 3499760 | County Treasury | N/A | 3499760 | N/A | 3499760 | 100% | 3499760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Okwa Mrefu- Mivukori – Ngungi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Okwa Mrefu- Mivukori – Ngungi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1999924 | 1999924 | 1999924 | County Treasury | N/A | 1999924 | N/A | 1999924 | 100% | 1999924 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwangaza Factory- Kyandundu Quarry Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mwangaza Factory- Kyandundu Quarry Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5698843 | 5698843 | 5698843 | County Treasury | N/A | 5698843 | N/A | 5698843 | 100% | 5698843 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamuthatha- Mwangaza Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamuthatha- Mwangaza Factory Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5698843 | 5698843 | 5698843 | County Treasury | N/A | 5698843 | N/A | 5698843 | 100% | 5698843 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Cereal Board-Kavaruka Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Cereal Board-Kavaruka Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5698843 | 5698843 | 5698843 | County Treasury | N/A | 5698843 | N/A | 5698843 | 100% | 5698843 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kauriro Full Gospel Kyandundu Primary Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kauriro Full Gospel Kyandundu Primary Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4298647 | 4298647 | 4298647 | County Treasury | N/A | 4298647 | N/A | 4298647 | 100% | 4298647 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Kithimu | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts In Kithimu |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4298647 | 4298647 | 4298647 | County Treasury | N/A | 4298647 | N/A | 4298647 | 100% | 4298647 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Igumo Catholic- Gakui – Dagoreti Kithangai Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Igumo Catholic- Gakui – Dagoreti Kithangai Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1940170 | 1940170 | 1940170 | County Treasury | N/A | 1940170 | N/A | 1940170 | 100% | 1940170 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Machinery For Road Works Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Machinery For Road Works Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2995700 | 2995700 | 2995700 | County Treasury | N/A | 2995700 | N/A | 2995700 | 100% | 2995700 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Usambara Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Usambara Junction Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3480441 | 3480441 | 3480441 | County Treasury | N/A | 3480441 | N/A | 3480441 | 100% | 3480441 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthanthara –Muiru-Kogeni | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muthanthara –Muiru-Kogeni |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2998288 | 2998288 | 2998288 | County Treasury | N/A | 2998288 | N/A | 2998288 | 100% | 2998288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts At King’oro Stream | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts At King’oro Stream |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2998288 | 2998288 | 2998288 | County Treasury | N/A | 2998288 | N/A | 2998288 | 100% | 2998288 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Witwa- Kathugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Witwa- Kathugu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2247976 | 2247976 | 2247976 | County Treasury | N/A | 2247976 | N/A | 2247976 | 100% | 2247976 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Machinery (Grader)For Maintenance Of Roads Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Machinery (Grader)For Maintenance Of Roads Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2972964 | 2972964 | 2972964 | County Treasury | N/A | 2972964 | N/A | 2972964 | 100% | 2972964 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mla Chake- Mumburi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mla Chake- Mumburi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2195880 | 2195880 | 2195880 | County Treasury | N/A | 2195880 | N/A | 2195880 | 100% | 2195880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Sarava –Gituto- Ithagana Drift | Cleaning, removal debris and repair of damaged areas | To prevent storm water from flooding on the road | Controlled storm water | Road | Maintenance Of Kwa Sarava –Gituto- Ithagana Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2195880 | 2195880 | 2195880 | County Treasury | N/A | 2195880 | N/A | 2195880 | 100% | 2195880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makunguru- Kwa Andu Ambogo | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Makunguru- Kwa Andu Ambogo |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2195880 | 2195880 | 2195880 | County Treasury | N/A | 2195880 | N/A | 2195880 | 100% | 2195880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwangaza- Matangiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mwangaza- Matangiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 930000 | 930000 | 930000 | County Treasury | N/A | 930000 | N/A | 930000 | 100% | 930000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Mururiri Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Mururiri Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1498996 | 1498996 | 1498996 | County Treasury | N/A | 1498996 | N/A | 1498996 | 100% | 1498996 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Muthanu Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Proposed Construction Of Muthanu Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3486496 | 3486496 | 3486496 | County Treasury | N/A | 3486496 | N/A | 3486496 | 100% | 3486496 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Grader For Road Works Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Grader For Road Works Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5386321 | 5386321 | 5386321 | County Treasury | N/A | 5386321 | N/A | 5386321 | 100% | 5386321 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Bull Dozer In Muminji | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Bull Dozer In Muminji |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5386321 | 5386321 | 5386321 | County Treasury | N/A | 5386321 | N/A | 5386321 | 100% | 5386321 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Bush Clearing On Selected Roads | Cutting and clearing | To improve visibility, accessibility and road safety | Cleared road corridors | Road | Bush Clearing On Selected Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 5386321 | 5386321 | 5386321 | County Treasury | N/A | 5386321 | N/A | 5386321 | 100% | 5386321 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Gatakari Njokavi Drift | Excavation, construction and installation | To control storm water | Flooding water controled | Road | Installation Of Gatakari Njokavi Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1798377 | 1798377 | 1798377 | County Treasury | N/A | 1798377 | N/A | 1798377 | 100% | 1798377 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Thura Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Thura Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1493739 | 1493739 | 1493739 | County Treasury | N/A | 1493739 | N/A | 1493739 | 100% | 1493739 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of The Proposed Karambari Thura Ntharawe Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of The Proposed Karambari Thura Ntharawe Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4203501 | 4203501 | 4203501 | County Treasury | N/A | 4203501 | N/A | 4203501 | 100% | 4203501 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Muminji | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Cuverts In Muminji |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4206334 | 4206334 | 4206334 | County Treasury | N/A | 4206334 | N/A | 4206334 | 100% | 4206334 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Kivwe Base Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Kivwe Base Culverts |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4206334 | 4206334 | 4206334 | County Treasury | N/A | 4206334 | N/A | 4206334 | 100% | 4206334 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Gravelling On Selected Roads Across The Ward | Hauling, gravelling and watering | A durable, stable and well-drained road surface | A suitable road for safe and efficient vehicle and pedestrian use | Road | Gravelling On Selected Roads Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1980352 | 1980352 | 1980352 | County Treasury | N/A | 1980352 | N/A | 1980352 | 100% | 1980352 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Yoder Scheme Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Yoder Scheme Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1465544 | 1465544 | 1465544 | County Treasury | N/A | 1465544 | N/A | 1465544 | 100% | 1465544 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyariri Ngangari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanyariri Ngangari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2865773 | 2865773 | 2865773 | County Treasury | N/A | 2865773 | N/A | 2865773 | 100% | 2865773 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rwethe Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rwethe Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2865773 | 2865773 | 2865773 | County Treasury | N/A | 2865773 | N/A | 2865773 | 100% | 2865773 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ivinge Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ivinge Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1997752 | 1997752 | 1997752 | County Treasury | N/A | 1997752 | N/A | 1997752 | 100% | 1997752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Machinery And Equipments For Road Works Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Machinery And Equipments For Road Works Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4999136 | 4999136 | 4999136 | County Treasury | N/A | 4999136 | N/A | 4999136 | 100% | 4999136 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ivaru Bridges Gabions And Extra Culverts | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Ivaru Bridges Gabions And Extra Culverts |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1498480 | 1498480 | 1498480 | County Treasury | N/A | 1498480 | N/A | 1498480 | 100% | 1498480 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rugakori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rugakori Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3186811 | 3186811 | 3186811 | County Treasury | N/A | 3186811 | N/A | 3186811 | 100% | 3186811 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Meka Munyori Nganduri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Meka Munyori Nganduri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 832845 | 832845 | 832845 | County Treasury | N/A | 832845 | N/A | 832845 | 100% | 832845 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gikanguta Ack Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gikanguta Ack Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3487714 | 3487714 | 3487714 | County Treasury | N/A | 3487714 | N/A | 3487714 | 100% | 3487714 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Runganga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Runganga Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3487714 | 3487714 | 3487714 | County Treasury | N/A | 3487714 | N/A | 3487714 | 100% | 3487714 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathima Karwagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathima Karwagi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3493642 | 3493642 | 3493642 | County Treasury | N/A | 3493642 | N/A | 3493642 | 100% | 3493642 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karingari Market | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karingari Market |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3493642 | 3493642 | 3493642 | County Treasury | N/A | 3493642 | N/A | 3493642 | 100% | 3493642 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kianyaga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kianyaga Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3493642 | 3493642 | 3493642 | County Treasury | N/A | 3493642 | N/A | 3493642 | 100% | 3493642 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njuguna- Gicindano Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Njuguna- Gicindano Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1901300 | 1901300 | 1901300 | County Treasury | N/A | 1901300 | N/A | 1901300 | 100% | 1901300 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1901300 | 1901300 | 1901300 | County Treasury | N/A | 1901300 | N/A | 1901300 | 100% | 1901300 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiawanja Kiangoma Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiawanja Kiangoma Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3434374 | 3434374 | 3434374 | County Treasury | N/A | 3434374 | N/A | 3434374 | 100% | 3434374 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Triumph Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Triumph Church Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3434374 | 3434374 | 3434374 | County Treasury | N/A | 3434374 | N/A | 3434374 | 100% | 3434374 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kietheru Catholic Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kietheru Catholic Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1496609 | 1496609 | 1496609 | County Treasury | N/A | 1496609 | N/A | 1496609 | 100% | 1496609 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kietheru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kietheru Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3461850 | 3461850 | 3461850 | County Treasury | N/A | 3461850 | N/A | 3461850 | 100% | 3461850 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Polytecnic Iriari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Polytecnic Iriari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3461850 | 3461850 | 3461850 | County Treasury | N/A | 3461850 | N/A | 3461850 | 100% | 3461850 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ciangoga Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Ciangoga Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2399158 | 2399158 | 2399158 | County Treasury | N/A | 2399158 | N/A | 2399158 | 100% | 2399158 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutuobare- 3km Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutuobare- 3km Junction Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1760889 | 1760889 | 1760889 | County Treasury | N/A | 1760889 | N/A | 1760889 | 100% | 1760889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gituru Complex-Rutumbi-Karura Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gituru Complex-Rutumbi-Karura Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1760889 | 1760889 | 1760889 | County Treasury | N/A | 1760889 | N/A | 1760889 | 100% | 1760889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2299871 | 2299871 | 2299871 | County Treasury | N/A | 2299871 | N/A | 2299871 | 100% | 2299871 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing Of Kagaari South Access Road | Clearing, grubbing, cutting and filling | To provide a well-prepared road corridor that supports durable pavememnt construction | well dozed road corridor | Road | Dozing Of Kagaari South Access Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2579562 | 2579562 | 2579562 | County Treasury | N/A | 2579562 | N/A | 2579562 | 100% | 2579562 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Kagaari South Access | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading Of Kagaari South Access |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2332992 | 2332992 | 2332992 | County Treasury | N/A | 2332992 | N/A | 2332992 | 100% | 2332992 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Gatua – Nguo Box Culvert | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Gatua – Nguo Box Culvert |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3899995 | 3899995 | 3899995 | County Treasury | N/A | 3899995 | N/A | 3899995 | 100% | 3899995 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Ngwego Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Proposed Construction Of Ngwego Bridge |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2199952 | 2199952 | 2199952 | County Treasury | N/A | 2199952 | N/A | 2199952 | 100% | 2199952 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mugui Cavairi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mugui Cavairi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3982507 | 3982507 | 3982507 | County Treasury | N/A | 3982507 | N/A | 3982507 | 100% | 3982507 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nduuri Dispensary Eapc Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nduuri Dispensary Eapc Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1998889 | 1998889 | 1998889 | County Treasury | N/A | 1998889 | N/A | 1998889 | 100% | 1998889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kithuriri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1999577 | 1999577 | 1999577 | County Treasury | N/A | 1999577 | N/A | 1999577 | 100% | 1999577 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gold Mine Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gold Mine Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2999516 | 2999516 | 2999516 | County Treasury | N/A | 2999516 | N/A | 2999516 | 100% | 2999516 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Levelling Of Kianjokoma Stage Road | Clearing, removal of debris, filling and cutting | Toachieve a uniform, smooth and properly graded surface | Levelled road providing smooth and safe surface | Road | Levelling Of Kianjokoma Stage Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2999516 | 2999516 | 2999516 | County Treasury | N/A | 2999516 | N/A | 2999516 | 100% | 2999516 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Market Ring Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Market Ring Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2999516 | 2999516 | 2999516 | County Treasury | N/A | 2999516 | N/A | 2999516 | 100% | 2999516 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Kithinji Bridge | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kithinji Bridge |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499999 | 3499999 | 3499999 | County Treasury | N/A | 3499999 | N/A | 3499999 | 100% | 3499999 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathuiani-Nduguini-Mwanyani Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathuiani-Nduguini-Mwanyani Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2159862 | 2159862 | 2159862 | County Treasury | N/A | 2159862 | N/A | 2159862 | 100% | 2159862 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Unguni- Mung’etho Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Unguni- Mung’etho Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2159862 | 2159862 | 2159862 | County Treasury | N/A | 2159862 | N/A | 2159862 | 100% | 2159862 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makima Market Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Makima Market Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1958489 | 1958489 | 1958489 | County Treasury | N/A | 1958489 | N/A | 1958489 | 100% | 1958489 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngeca- Katharane Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngeca- Katharane Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1958489 | 1958489 | 1958489 | County Treasury | N/A | 1958489 | N/A | 1958489 | 100% | 1958489 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Musyoka- Kambiti- Muthilu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Musyoka- Kambiti- Muthilu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1996592 | 1996592 | 1996592 | County Treasury | N/A | 1996592 | N/A | 1996592 | 100% | 1996592 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kakawa- Kambiti-Muthilu-Kathiani Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kakawa- Kambiti-Muthilu-Kathiani Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1738492 | 1738492 | 1738492 | County Treasury | N/A | 1738492 | N/A | 1738492 | 100% | 1738492 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culvert In Makima | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culvert In Makima |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 861222 | 861222 | 861222 | County Treasury | N/A | 861222 | N/A | 861222 | 100% | 861222 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Karaba-Wango Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Karaba-Wango Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2481008 | 2481008 | 2481008 | County Treasury | N/A | 2481008 | N/A | 2481008 | 100% | 2481008 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gategi Market Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gategi Market Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2481008 | 2481008 | 2481008 | County Treasury | N/A | 2481008 | N/A | 2481008 | 100% | 2481008 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngandi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngandi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1498250 | 1498250 | 1498250 | County Treasury | N/A | 1498250 | N/A | 1498250 | 100% | 1498250 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Wango Drift-Kwa Kimilu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of assets though timely interventions | Well maintained drift | Road | Maintenance Of Wango Drift-Kwa Kimilu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1991221 | 1991221 | 1991221 | County Treasury | N/A | 1991221 | N/A | 1991221 | 100% | 1991221 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Drift At Wango Kilia | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Drift At Wango Kilia |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1999994 | 1999994 | 1999994 | County Treasury | N/A | 1999994 | N/A | 1999994 | 100% | 1999994 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambo Catholic Pcea Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kambo Catholic Pcea Church Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1528010 | 1528010 | 1528010 | County Treasury | N/A | 1528010 | N/A | 1528010 | 100% | 1528010 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Kephis- Rupingazi Inn Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Kephis- Rupingazi Inn Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4506600 | 4506600 | 4506600 | County Treasury | N/A | 4506600 | N/A | 4506600 | 100% | 4506600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatunduri- Full Gospel Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatunduri- Full Gospel Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1354677 | 1354677 | 1354677 | County Treasury | N/A | 1354677 | N/A | 1354677 | 100% | 1354677 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Grading Of Roads ( Hire Of Machinery -100hrs ) | Clearing, earthworks, levelling and compaction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Grading Of Roads ( Hire Of Machinery -100hrs ) |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1994782 | 1994782 | 1994782 | County Treasury | N/A | 1994782 | N/A | 1994782 | 100% | 1994782 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Roads ( Hire Of Machinery 100 Hrs | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Roads ( Hire Of Machinery 100 Hrs |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1994782 | 1994782 | 1994782 | County Treasury | N/A | 1994782 | N/A | 1994782 | 100% | 1994782 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Roads (Hire Of Machinery 130 M3 | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Roads (Hire Of Machinery 130 M3 |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1847787 | 1847787 | 1847787 | County Treasury | N/A | 1847787 | N/A | 1847787 | 100% | 1847787 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Embu High- Country View Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Embu High- Country View Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2099072 | 2099072 | 2099072 | County Treasury | N/A | 2099072 | N/A | 2099072 | 100% | 2099072 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Box Culvert Of John Mathanjuki Nyaga M’kuma Road | Site preparation, excavation and construction | To provide a safe and durable passage for road traffic | Managed storm water | Road | Proposed Box Culvert Of John Mathanjuki Nyaga M’kuma Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3997248 | 3997248 | 3997248 | County Treasury | N/A | 3997248 | N/A | 3997248 | 100% | 3997248 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Karurina- Nyaga M’kuma Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Karurina- Nyaga M’kuma Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1386177 | 1386177 | 1386177 | County Treasury | N/A | 1386177 | N/A | 1386177 | 100% | 1386177 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of John Mathanjuki-Nyaga M’kuma | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of John Mathanjuki-Nyaga M’kuma |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1997961 | 1997961 | 1997961 | County Treasury | N/A | 1997961 | N/A | 1997961 | 100% | 1997961 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts At Ithata | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts At Ithata |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1498476 | 1498476 | 1498476 | County Treasury | N/A | 1498476 | N/A | 1498476 | 100% | 1498476 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kaunyuri Muthatari Pcea Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kaunyuri Muthatari Pcea Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2998454 | 2998454 | 2998454 | County Treasury | N/A | 2998454 | N/A | 2998454 | 100% | 2998454 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts At Kiairangu | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts At Kiairangu |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1647339 | 1647339 | 1647339 | County Treasury | N/A | 1647339 | N/A | 1647339 | 100% | 1647339 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Mbeti North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts In Mbeti North |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1907678 | 1907678 | 1907678 | County Treasury | N/A | 1907678 | N/A | 1907678 | 100% | 1907678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirimari Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kirimari Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1985224 | 1985224 | 1985224 | County Treasury | N/A | 1985224 | N/A | 1985224 | 100% | 1985224 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Repair Of Water Drainage Behind Makuti | Excavation, pipe laying | To ensure that water reach to its destinated area safe and clean | Uncontaminated water flowing through the pipes | Road | Repair Of Water Drainage Behind Makuti |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1698217 | 1698217 | 1698217 | County Treasury | N/A | 1698217 | N/A | 1698217 | 100% | 1698217 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jua Kali Shed Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Jua Kali Shed Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1698217 | 1698217 | 1698217 | County Treasury | N/A | 1698217 | N/A | 1698217 | 100% | 1698217 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Dozer To Do Dozing Works | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Dozer To Do Dozing Works |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2071760 | 2071760 | 2071760 | County Treasury | N/A | 2071760 | N/A | 2071760 | 100% | 2071760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Grader To Grade And Spread Gravel Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Grader To Grade And Spread Gravel Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2071760 | 2071760 | 2071760 | County Treasury | N/A | 2071760 | N/A | 2071760 | 100% | 2071760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Dumping Of Gravel Using Hired Lorries In Grade Roads Across The Ward | Loading, hauling and dumping | To strengthen the road formation, reduce dust and erosion | Gravel-dumped section stabilized surface | Road | Dumping Of Gravel Using Hired Lorries In Grade Roads Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2481240 | 2481240 | 2481240 | County Treasury | N/A | 2481240 | N/A | 2481240 | 100% | 2481240 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutira A And B Kathanjuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutira A And B Kathanjuri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2944190 | 2944190 | 2944190 | County Treasury | N/A | 2944190 | N/A | 2944190 | 100% | 2944190 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangari Kianjuki Catholic Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathangari Kianjuki Catholic Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2944190 | 2944190 | 2944190 | County Treasury | N/A | 2944190 | N/A | 2944190 | 100% | 2944190 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kevote Ack Market- Mutaravo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kevote Ack Market- Mutaravo Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2944190 | 2944190 | 2944190 | County Treasury | N/A | 2944190 | N/A | 2944190 | 100% | 2944190 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Widening Of Muva Gacengi Road | Clearing, earthworks, levelling and compaction | To improve traffic capacity and reduce congestion at the exit point | Widened road | Road | Widening Of Muva Gacengi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 999800 | 999800 | 999800 | County Treasury | N/A | 999800 | N/A | 999800 | 100% | 999800 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ikunguru Mbogari Kiangechu | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ikunguru Mbogari Kiangechu |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2929324 | 2929324 | 2929324 | County Treasury | N/A | 2929324 | N/A | 2929324 | 100% | 2929324 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kavari Ruvutiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kavari Ruvutiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2929324 | 2929324 | 2929324 | County Treasury | N/A | 2929324 | N/A | 2929324 | 100% | 2929324 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Gitongoro Gicagi Kiriru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Gitongoro Gicagi Kiriru Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2929324 | 2929324 | 2929324 | County Treasury | N/A | 2929324 | N/A | 2929324 | 100% | 2929324 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Kaguchori Kianjeru Mutharanderu Gatitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kaguchori Kianjeru Mutharanderu Gatitu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1307065 | 1307065 | 1307065 | County Treasury | N/A | 1307065 | N/A | 1307065 | 100% | 1307065 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gituri St Joseph | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gituri St Joseph |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1881914 | 1881914 | 1881914 | County Treasury | N/A | 1881914 | N/A | 1881914 | 100% | 1881914 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiandathi Mururiri Kathigai Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiandathi Mururiri Kathigai Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1776029 | 1776029 | 1776029 | County Treasury | N/A | 1776029 | N/A | 1776029 | 100% | 1776029 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Proposed Kabuguri Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Proposed Kabuguri Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1883960 | 1883960 | 1883960 | County Treasury | N/A | 1883960 | N/A | 1883960 | 100% | 1883960 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ndagori Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Ndagori Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1675110 | 1675110 | 1675110 | County Treasury | N/A | 1675110 | N/A | 1675110 | 100% | 1675110 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Gitaru Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Gitaru Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1728278 | 1728278 | 1728278 | County Treasury | N/A | 1728278 | N/A | 1728278 | 100% | 1728278 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of The Proposed Kathuri Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of The Proposed Kathuri Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1780252 | 1780252 | 1780252 | County Treasury | N/A | 1780252 | N/A | 1780252 | 100% | 1780252 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Equipments (Grader For Road Works Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Equipments (Grader For Road Works Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3499920 | 3499920 | 3499920 | County Treasury | N/A | 3499920 | N/A | 3499920 | 100% | 3499920 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Hire Of Equipment (Bull Dozer) Across The Ward | Material handling, excavation, lifting | To ensure efficient, timely, and safe completion of operations while meeting required technical and quality standards | Delivered, installed and operational machinery | Road | Hire Of Equipment (Bull Dozer) Across The Ward |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 4496856 | 4496856 | 4496856 | County Treasury | N/A | 4496856 | N/A | 4496856 | 100% | 4496856 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Kiriiri Box Culvert | Site preparation, excavation and construction | To provide a safe and durable passage for road traffic | Managed storm water | Road | Proposed Construction Of Kiriiri Box Culvert |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2492942 | 2492942 | 2492942 | County Treasury | N/A | 2492942 | N/A | 2492942 | 100% | 2492942 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Ngarira Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Proposed Construction Of Ngarira Drift |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3438840 | 3438840 | 3438840 | County Treasury | N/A | 3438840 | N/A | 3438840 | 100% | 3438840 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitare Gichagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gitare Gichagi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3998200 | 3998200 | 3998200 | County Treasury | N/A | 3998200 | N/A | 3998200 | 100% | 3998200 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichichie Gichagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichichie Gichagi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2496877 | 2496877 | 2496877 | County Treasury | N/A | 2496877 | N/A | 2496877 | 100% | 2496877 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamica Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamica Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2496877 | 2496877 | 2496877 | County Treasury | N/A | 2496877 | N/A | 2496877 | 100% | 2496877 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyorora Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanyorora Access Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 2942637 | 2942637 | 2942637 | County Treasury | N/A | 2942637 | N/A | 2942637 | 100% | 2942637 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gacagori Gitare Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gacagori Gitare Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3662180 | 3662180 | 3662180 | County Treasury | N/A | 3662180 | N/A | 3662180 | 100% | 3662180 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathuriri Gitare Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathuriri Gitare Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3895678 | 3895678 | 3895678 | County Treasury | N/A | 3895678 | N/A | 3895678 | 100% | 3895678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karuri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3895678 | 3895678 | 3895678 | County Treasury | N/A | 3895678 | N/A | 3895678 | 100% | 3895678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichagi Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3895678 | 3895678 | 3895678 | County Treasury | N/A | 3895678 | N/A | 3895678 | 100% | 3895678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutandari Kigumo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mutandari Kigumo Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 999015 | 999015 | 999015 | County Treasury | N/A | 999015 | N/A | 999015 | 100% | 999015 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Runyenjes Technical Institute Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Runyenjes Technical Institute Junction Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 996436 | 996436 | 996436 | County Treasury | N/A | 996436 | N/A | 996436 | 100% | 996436 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mbugua Kathunguri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Mbugua Kathunguri Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 951437 | 951437 | 951437 | County Treasury | N/A | 951437 | N/A | 951437 | 100% | 951437 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kinthithe Nyagari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kinthithe Nyagari Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1996012 | 1996012 | 1996012 | County Treasury | N/A | 1996012 | N/A | 1996012 | 100% | 1996012 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Improvement Of Kathanjuri Market Roads | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Improvement Of Kathanjuri Market Roads |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 1996012 | 1996012 | 1996012 | County Treasury | N/A | 1996012 | N/A | 1996012 | 100% | 1996012 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karurumo Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karurumo Market Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3906439 | 3906439 | 3906439 | County Treasury | N/A | 3906439 | N/A | 3906439 | 100% | 3906439 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Methodist Church- Gaititu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Methodist Church- Gaititu Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3906439 | 3906439 | 3906439 | County Treasury | N/A | 3906439 | N/A | 3906439 | 100% | 3906439 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathanjuri Kathera Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathanjuri Kathera Road |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 3906439 | 3906439 | 3906439 | County Treasury | N/A | 3906439 | N/A | 3906439 | 100% | 3906439 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts In Kyeni South | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts In Kyeni South |  |  |  | Road | Road | Road | 2018-01-07 | 2019-10-06 | 30/6/2019 | 30/6/2019 | 999940 | 999940 | 999940 | County Treasury | N/A | 999940 | N/A | 999940 | 100% | 999940 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Haniel- Njukiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Haniel- Njukiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2121582 | 2121582 | 2121582 | County Treasury | N/A | 2121582 | N/A | 2121582 | 100% | 2121582 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kangaru Market Ring Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kangaru Market Ring Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2121582 | 2121582 | 2121582 | County Treasury | N/A | 2121582 | N/A | 2121582 | 100% | 2121582 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Shauri- Delivarance Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Shauri- Delivarance Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1173731 | 1173731 | 1173731 | County Treasury | N/A | 1173731 | N/A | 1173731 | 100% | 1173731 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Spring Valley – Ngondi | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Spring Valley – Ngondi |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1111570 | 1111570 | 1111570 | County Treasury | N/A | 1111570 | N/A | 1111570 | 100% | 1111570 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiambuthi- Kiwanuka Sunrise Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kiambuthi- Kiwanuka Sunrise Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1128100 | 1128100 | 1128100 | County Treasury | N/A | 1128100 | N/A | 1128100 | 100% | 1128100 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mzalendo Tengetenge St. Teresa’s Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mzalendo Tengetenge St. Teresa’s Access Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2101446 | 2101446 | 2101446 | County Treasury | N/A | 2101446 | N/A | 2101446 | 100% | 2101446 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kithimu-Itabua-Kimangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintance Of Kithimu-Itabua-Kimangaru Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3638363 | 3638363 | 3638363 | County Treasury | N/A | 3638363 | N/A | 3638363 | 100% | 3638363 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Miandari- Kiringa Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Miandari- Kiringa Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3837934 | 3837934 | 3837934 | County Treasury | N/A | 3837934 | N/A | 3837934 | 100% | 3837934 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambuke- Kanambiu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kambuke- Kanambiu Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3837934 | 3837934 | 3837934 | County Treasury | N/A | 3837934 | N/A | 3837934 | 100% | 3837934 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Karanja Kiangui Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Karanja Kiangui Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1980862 | 1980862 | 1980862 | County Treasury | N/A | 1980862 | N/A | 1980862 | 100% | 1980862 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rianjagi – Ndiriri – Kirigi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Rianjagi – Ndiriri – Kirigi Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1689192 | 1689192 | 1689192 | County Treasury | N/A | 1689192 | N/A | 1689192 | 100% | 1689192 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigari Primary – Kairuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kigari Primary – Kairuri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2351332 | 2351332 | 2351332 | County Treasury | N/A | 2351332 | N/A | 2351332 | 100% | 2351332 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamviu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamviu Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1464871 | 1464871 | 1464871 | County Treasury | N/A | 1464871 | N/A | 1464871 | 100% | 1464871 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatunduri Muthigiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatunduri Muthigiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2773838 | 2773838 | 2773838 | County Treasury | N/A | 2773838 | N/A | 2773838 | 100% | 2773838 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kauguri- Gaciari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kauguri- Gaciari Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2773838 | 2773838 | 2773838 | County Treasury | N/A | 2773838 | N/A | 2773838 | 100% | 2773838 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Kathangariri Kiambogo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Kathangariri Kiambogo Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2667507 | 2667507 | 2667507 | County Treasury | N/A | 2667507 | N/A | 2667507 | 100% | 2667507 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ack. Muthigi – Kiamanya Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ack. Muthigi – Kiamanya Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2667507 | 2667507 | 2667507 | County Treasury | N/A | 2667507 | N/A | 2667507 | 100% | 2667507 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbiruri – Kathuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbiruri – Kathuriri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3438680 | 3438680 | 3438680 | County Treasury | N/A | 3438680 | N/A | 3438680 | 100% | 3438680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitare – Kariguiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gitare – Kariguiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3438680 | 3438680 | 3438680 | County Treasury | N/A | 3438680 | N/A | 3438680 | 100% | 3438680 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kigaa- Kagumori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kigaa- Kagumori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2303528 | 2303528 | 2303528 | County Treasury | N/A | 2303528 | N/A | 2303528 | 100% | 2303528 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ngarari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ngarari Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2303528 | 2303528 | 2303528 | County Treasury | N/A | 2303528 | N/A | 2303528 | 100% | 2303528 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathunguri – Kariru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kathunguri – Kariru Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3868600 | 3868600 | 3868600 | County Treasury | N/A | 3868600 | N/A | 3868600 | 100% | 3868600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kasafari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kasafari Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3868600 | 3868600 | 3868600 | County Treasury | N/A | 3868600 | N/A | 3868600 | 100% | 3868600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanginga- Kigumo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanginga- Kigumo Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1813254 | 1813254 | 1813254 | County Treasury | N/A | 1813254 | N/A | 1813254 | 100% | 1813254 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mivutiri – Gatumbi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mivutiri – Gatumbi Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3758202 | 3758202 | 3758202 | County Treasury | N/A | 3758202 | N/A | 3758202 | 100% | 3758202 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitumbi- Mufu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gitumbi- Mufu Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3758202 | 3758202 | 3758202 | County Treasury | N/A | 3758202 | N/A | 3758202 | 100% | 3758202 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanginga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kanginga Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1932618 | 1932618 | 1932618 | County Treasury | N/A | 1932618 | N/A | 1932618 | 100% | 1932618 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nduuri Market Ring Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nduuri Market Ring Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2695295 | 2695295 | 2695295 | County Treasury | N/A | 2695295 | N/A | 2695295 | 100% | 2695295 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Kanja Market – Catholic Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenace Of Kanja Market – Catholic Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2695295 | 2695295 | 2695295 | County Treasury | N/A | 2695295 | N/A | 2695295 | 100% | 2695295 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mukuuri Market To Catholic Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mukuuri Market To Catholic Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2695295 | 2695295 | 2695295 | County Treasury | N/A | 2695295 | N/A | 2695295 | 100% | 2695295 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbuinjeru Market- Kamanga Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbuinjeru Market- Kamanga Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2489615 | 2489615 | 2489615 | County Treasury | N/A | 2489615 | N/A | 2489615 | 100% | 2489615 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenca Of Ngorova- Janake Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenca Of Ngorova- Janake Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2489615 | 2489615 | 2489615 | County Treasury | N/A | 2489615 | N/A | 2489615 | 100% | 2489615 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gaikama- Joana Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gaikama- Joana Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2489615 | 2489615 | 2489615 | County Treasury | N/A | 2489615 | N/A | 2489615 | 100% | 2489615 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichugu- Gaikiro Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gichugu- Gaikiro Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1798365 | 1798365 | 1798365 | County Treasury | N/A | 1798365 | N/A | 1798365 | 100% | 1798365 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchagori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Muchagori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3817537 | 3817537 | 3817537 | County Treasury | N/A | 3817537 | N/A | 3817537 | 100% | 3817537 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance F Ngure – Karue Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance F Ngure – Karue Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3817537 | 3817537 | 3817537 | County Treasury | N/A | 3817537 | N/A | 3817537 | 100% | 3817537 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Spot Imrovement Of R20 Iria Itune - Kilia Road | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Spot Imrovement Of R20 Iria Itune - Kilia Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2990016 | 2990016 | 2990016 | County Treasury | N/A | 2990016 | N/A | 2990016 | 100% | 2990016 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Spot Improvement Of Wango - Kilia Road | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Spot Improvement Of Wango - Kilia Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2990016 | 2990016 | 2990016 | County Treasury | N/A | 2990016 | N/A | 2990016 | 100% | 2990016 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Syongua - Kwa Kaswii Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Syongua - Kwa Kaswii Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2439132 | 2439132 | 2439132 | County Treasury | N/A | 2439132 | N/A | 2439132 | 100% | 2439132 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Kwa Ndui - Kwa Kathiani Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Kwa Ndui - Kwa Kathiani Primary School Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2439132 | 2439132 | 2439132 | County Treasury | N/A | 2439132 | N/A | 2439132 | 100% | 2439132 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karimari - Kiang'anjaa Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karimari - Kiang'anjaa Primary School Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2479842 | 2479842 | 2479842 | County Treasury | N/A | 2479842 | N/A | 2479842 | 100% | 2479842 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of 511 Tamaka Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of 511 Tamaka Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2479842 | 2479842 | 2479842 | County Treasury | N/A | 2479842 | N/A | 2479842 | 100% | 2479842 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nguthi - Kandari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nguthi - Kandari Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3274622 | 3274622 | 3274622 | County Treasury | N/A | 3274622 | N/A | 3274622 | 100% | 3274622 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mabati Juu - Mutindwa Primary School - Muthithiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mabati Juu - Mutindwa Primary School - Muthithiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1953092 | 1953092 | 1953092 | County Treasury | N/A | 1953092 | N/A | 1953092 | 100% | 1953092 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ikomenie - Nyambori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Ikomenie - Nyambori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1953092 | 1953092 | 1953092 | County Treasury | N/A | 1953092 | N/A | 1953092 | 100% | 1953092 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kariari - Gichigori - Kathigari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kariari - Gichigori - Kathigari Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1661677 | 1661677 | 1661677 | County Treasury | N/A | 1661677 | N/A | 1661677 | 100% | 1661677 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mariari - Icukiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mariari - Icukiri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1661677 | 1661677 | 1661677 | County Treasury | N/A | 1661677 | N/A | 1661677 | 100% | 1661677 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Riacina - Kanthenge - Karura Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Riacina - Kanthenge - Karura Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1991952 | 1991952 | 1991952 | County Treasury | N/A | 1991952 | N/A | 1991952 | 100% | 1991952 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kilee - Kwa Mucheru - Mutundu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kilee - Kwa Mucheru - Mutundu Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2711511 | 2711511 | 2711511 | County Treasury | N/A | 2711511 | N/A | 2711511 | 100% | 2711511 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kalisa - Mulukusi Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kalisa - Mulukusi Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2711511 | 2711511 | 2711511 | County Treasury | N/A | 2711511 | N/A | 2711511 | 100% | 2711511 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwea - Mwanzo Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mwea - Mwanzo Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1927224 | 1927224 | 1927224 | County Treasury | N/A | 1927224 | N/A | 1927224 | 100% | 1927224 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Yoder - Rianguu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Yoder - Rianguu Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1842892 | 1842892 | 1842892 | County Treasury | N/A | 1842892 | N/A | 1842892 | 100% | 1842892 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Miti – Rianguu | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kwa Miti – Rianguu |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1842892 | 1842892 | 1842892 | County Treasury | N/A | 1842892 | N/A | 1842892 | 100% | 1842892 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nganduri - Gatorori Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Nganduri - Gatorori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1788224 | 1788224 | 1788224 | County Treasury | N/A | 1788224 | N/A | 1788224 | 100% | 1788224 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Meka - Kamunyange Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Meka - Kamunyange Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1788224 | 1788224 | 1788224 | County Treasury | N/A | 1788224 | N/A | 1788224 | 100% | 1788224 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Deb Muraru - Mbita Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Deb Muraru - Mbita Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1835816 | 1835816 | 1835816 | County Treasury | N/A | 1835816 | N/A | 1835816 | 100% | 1835816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Assorted Sizes Of Culverts On Selected Roads | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Assorted Sizes Of Culverts On Selected Roads |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1835816 | 1835816 | 1835816 | County Treasury | N/A | 1835816 | N/A | 1835816 | 100% | 1835816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kune - Kuui - Uvariri | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kune - Kuui - Uvariri |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1867600 | 1867600 | 1867600 | County Treasury | N/A | 1867600 | N/A | 1867600 | 100% | 1867600 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatorrori - Gacuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatorrori - Gacuriri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1833844 | 1833844 | 1833844 | County Treasury | N/A | 1833844 | N/A | 1833844 | 100% | 1833844 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamumu - Rwanjeru Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamumu - Rwanjeru Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1833844 | 1833844 | 1833844 | County Treasury | N/A | 1833844 | N/A | 1833844 | 100% | 1833844 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwaitho - Mung'ao - Zaire Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mwaitho - Mung'ao - Zaire Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2517142 | 2517142 | 2517142 | County Treasury | N/A | 2517142 | N/A | 2517142 | 100% | 2517142 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamachu - Mung'ao - Kwa Mbao Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kamachu - Mung'ao - Kwa Mbao Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 2517142 | 2517142 | 2517142 | County Treasury | N/A | 2517142 | N/A | 2517142 | 100% | 2517142 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gikingiri - B.A.T Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gikingiri - B.A.T Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1408310 | 1408310 | 1408310 | County Treasury | N/A | 1408310 | N/A | 1408310 | 100% | 1408310 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kambo Full Gospel Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Kambo Full Gospel Church Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 5799768 | 5799768 | 5799768 | County Treasury | N/A | 5799768 | N/A | 5799768 | 100% | 5799768 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mbaci - Kianjoya Road In Evurori Ward | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Mbaci - Kianjoya Road In Evurori Ward |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 1852752 | 1852752 | 1852752 | County Treasury | N/A | 1852752 | N/A | 1852752 | 100% | 1852752 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Macumo- Siakago Tarmac Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Macumo- Siakago Tarmac Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 5859334 | 5859334 | 5859334 | County Treasury | N/A | 5859334 | N/A | 5859334 | 100% | 5859334 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karugu –Ena Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Karugu –Ena Market Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 5859334 | 5859334 | 5859334 | County Treasury | N/A | 5859334 | N/A | 5859334 | 100% | 5859334 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatambararia-Ugweri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance Of Gatambararia-Ugweri Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 5859334 | 5859334 | 5859334 | County Treasury | N/A | 5859334 | N/A | 5859334 | 100% | 5859334 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Kwa Mutoi Junction To Nduuri Shopping Center And Kwa Mutoi Juntion To Mukuuri Shopping Center Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Kwa Mutoi Junction To Nduuri Shopping Center And Kwa Mutoi Juntion To Mukuuri Shopping Center Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 125624218 | 125624218 | 125624218 | County Treasury | N/A | 125624218 | N/A | 125624218 | 100% | 125624218 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Kangaru – Kairuri Road (Phase Two) | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Kangaru – Kairuri Road (Phase Two) |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 15317046 | 15317046 | 15317046 | County Treasury | N/A | 15317046 | N/A | 15317046 | 100% | 15317046 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Mbiruri Nduuri Junction Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Mbiruri Nduuri Junction Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 54848946 | 54848946 | 54848946 | County Treasury | N/A | 54848946 | N/A | 54848946 | 100% | 54848946 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Mbiruri Nduuri Junction Road(Phase 2) | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Mbiruri Nduuri Junction Road(Phase 2) |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 12189454 | 12189454 | 12189454 | County Treasury | N/A | 12189454 | N/A | 12189454 | 100% | 12189454 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Ishiara Town Roads | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Ishiara Town Roads |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 9406730 | 9406730 | 9406730 | County Treasury | N/A | 9406730 | N/A | 9406730 | 100% | 9406730 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Kavutiri Factory-Muchagori Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Kavutiri Factory-Muchagori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 31127087 | 31127087 | 31127087 | County Treasury | N/A | 31127087 | N/A | 31127087 | 100% | 31127087 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Kavutiri Factory-Muchagori Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Kavutiri Factory-Muchagori Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 9588641 | 9588641 | 9588641 | County Treasury | N/A | 9588641 | N/A | 9588641 | 100% | 9588641 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Kiritiri Town Roads Phase 2 | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Kiritiri Town Roads Phase 2 |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 17791790 | 17791790 | 17791790 | County Treasury | N/A | 17791790 | N/A | 17791790 | 100% | 17791790 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of Uchumi- Kiambuthi-Minn Inn Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standards Of Uchumi- Kiambuthi-Minn Inn Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 19240663 | 19240663 | 19240663 | County Treasury | N/A | 19240663 | N/A | 19240663 | 100% | 19240663 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Siakago Town Roads | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Siakago Town Roads |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 9406730 | 9406730 | 9406730 | County Treasury | N/A | 9406730 | N/A | 9406730 | 100% | 9406730 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standard Of Naivas Stadium Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading To Bitumen Standard Of Naivas Stadium Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 3290260 | 3290260 | 3290260 | County Treasury | N/A | 3290260 | N/A | 3290260 | 100% | 3290260 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Mate-Nthagaiya Road | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Mate-Nthagaiya Road |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 22629063 | 22629063 | 22629063 | County Treasury | N/A | 22629063 | N/A | 22629063 | 100% | 22629063 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Uchumi-Kiambuthi-Minni Inn Phase 2 | Excavation, construction | To improve traffic capacity and reduce congestion at the exit point | A wider, smoother, and more durable roaad exit | Road | Upgrading Of Uchumi-Kiambuthi-Minni Inn Phase 2 |  |  |  | Road | Road | Road | 2018-01-07 | 26/3/2019 | 30/6/2019 | 30/6/2019 | 16870721 | 16870721 | 16870721 | County Treasury | N/A | 16870721 | N/A | 16870721 | 100% | 16870721 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
2017/2018
| Mantenance Of Kairungu- Kirangano Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kairungu- Kirangano Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 999713 | N/A | 287 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Allamano Primary-Kiarangana Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Allamano Primary-Kiarangana Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2180510 | 2180510 | 2180510 | County treasury | N/A | 2180510 | N/A | 2180510 | 100% | 2179363 | N/A | 1147 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kevote -Kavue Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kevote -Kavue Road |  | Kivue |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1003330 | 1003330 | 1003330 | County treasury | N/A | 1003330 | N/A | 1003330 | 100% | 1003330 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Gaikiro Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Gaikiro Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1000048 | 1000048 | 1000048 | County treasury | N/A | 1000048 | N/A | 1000048 | 100% | 1000048 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Gichugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Gichugu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1394375 | 1394375 | 1394375 | County treasury | N/A | 1394375 | N/A | 1394375 | 100% | 1394375 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Muchagori Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Muchagori Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1000048 | 1000048 | 1000048 | County treasury | N/A | 1000048 | N/A | 1000048 | 100% | 1000048 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenence Of Nguire Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenence Of Nguire Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1000048 | 1000048 | 1000048 | County treasury | N/A | 1000048 | N/A | 1000048 | 100% | 1000048 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kiamatuto-Jafti-Gacengi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kiamatuto-Jafti-Gacengi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1299345 | 1299345 | 1299345 | County treasury | N/A | 1299345 | N/A | 1299345 | 100% | 1299345 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kathiakari-Ikirungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kathiakari-Ikirungu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1480357 | 1480357 | 1480357 | County treasury | N/A | 1480357 | N/A | 1480357 | 100% | 1480357 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kiangima-Kanjikeru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kiangima-Kanjikeru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1982173 | 1982173 | 1982173 | County treasury | N/A | 1982173 | N/A | 1982173 | 100% | 1956961 | 28612 | N/A | Completed | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Rwika-Kinondo Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Rwika-Kinondo Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2019-01-07 | 3136350 | 3136350 | 3136350 | County treasury | N/A | 3136350 | N/A | 3136350 | 100% | 3097220 | 39130 | N/A | Completed | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Mutunduri-Kathuri-Nyaga Jeremia Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Mutunduri-Kathuri-Nyaga Jeremia Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2019-01-07 | 2687105 | 2687105 | 2687105 | County treasury | N/A | 2687105 | N/A | 2687105 | 100% | 2611833 | 75272 | N/A | Completed | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kimangaru -Gikingiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kimangaru -Gikingiri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2019-01-07 | 1933784 | 1933784 | 1933784 | County treasury | N/A | 1933784 | N/A | 1933784 | 100% | 1933784 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Public Works- Prison - Ngomano Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Public Works- Prison - Ngomano Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2019-01-07 | 1379985 | 1379985 | 1379985 | County treasury | N/A | 1379985 | N/A | 1379985 | 100% | 1379985 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathande-Murara Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathande-Murara Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Nduuri-Kirimiri Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Nduuri-Kirimiri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kiathari- Kanja Dispensary Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kiathari- Kanja Dispensary Road |  | Kirimiri |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2781766 | 2781766 | 2781766 | County treasury | N/A | 2781766 | N/A | 2781766 | 100% | 2781766 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kinyonga A-B Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kinyonga A-B Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2394375 | 2394375 | 2394375 | County treasury | N/A | 2394375 | N/A | 2394375 | 100% | 2387762 | 6613 | N/A | Completed | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Nguviu Catholic -Gikimiri Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Nguviu Catholic -Gikimiri Factory Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2317315 | 2317315 | 2317315 | County treasury | N/A | 2317315 | N/A | 2317315 | 100% | 2317315 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Kithungururu-Nthambo-Kangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Kithungururu-Nthambo-Kangaru Road |  | Nthambo |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 2371678 | 2371678 | 2371678 | County treasury | N/A | 2371678 | N/A | 2371678 | 100% | 2371678 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Stage Kplc Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Stage Kplc Road |  |  |  | Road | Road | Road | 2017-01-07 | 2018-01-01 | 30/6/2018 | 2018-01-07 | 1354903 | 1354903 | 1354903 | County treasury | N/A | 1354903 | N/A | 1354903 | 100% | 1354903 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kathangari-Scheme Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kathangari-Scheme Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2340613 | 2340613 | 2340613 | County treasury | N/A | 2340613 | N/A | 2340613 | 100% | 2340613 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Dallas-Ndumari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Dallas-Ndumari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1487526 | 1487526 | 1487526 | County treasury | N/A | 1487526 | N/A | 1487526 | 100% | 1487526 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Makumbiri-Kwa Ucuru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Makumbiri-Kwa Ucuru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1989342 | 1989342 | 1989342 | County treasury | N/A | 1989342 | N/A | 1989342 | 100% | 1989342 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kawanjara- Kavangua Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kawanjara- Kavangua Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 3050324 | 3050324 | 3050324 | County treasury | N/A | 3050324 | N/A | 3050324 | 100% | 3050324 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kiringa-Ndumari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kiringa-Ndumari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 3136350 | 3136350 | 3136350 | County treasury | N/A | 3136350 | N/A | 3136350 | 100% | 3136350 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Mbuvori-Karau Pri Sch-Kathuniri Primray Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Mbuvori-Karau Pri Sch-Kathuniri Primray Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2903364 | 2903364 | 2903364 | County treasury | N/A | 2903364 | N/A | 2903364 | 100% | 2903364 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kathangariri Market-Muvabduri-Muthigi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kathangariri Market-Muvabduri-Muthigi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2691884 | 2691884 | 2691884 | County treasury | N/A | 2691884 | N/A | 2691884 | 100% | 2691884 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Gichegeni-Iriria Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Gichegeni-Iriria Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kathari-Ithinjue Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kathari-Ithinjue Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Makutano-Kirege Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Makutano-Kirege Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1581766 | 1581766 | 1581766 | County treasury | N/A | 1581766 | N/A | 1581766 | 100% | 1581766 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Tarmac-Kaveti Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Tarmac-Kaveti Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1994719 | 1994719 | 1994719 | County treasury | N/A | 1994719 | N/A | 1994719 | 100% | 1994719 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kavumbu-Ndii Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kavumbu-Ndii Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1399708 | 1399708 | 1399708 | County treasury | N/A | 1399708 | N/A | 1399708 | 100% | 1399708 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kavumbu-Ndii Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kavumbu-Ndii Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Nyagaari Dispensary-Kathara-Karago Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Nyagaari Dispensary-Kathara-Karago Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2781766 | 2781766 | 2781766 | County treasury | N/A | 2781766 | N/A | 2781766 | 100% | 2781766 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kwa George Kamitaa-Karurumo Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kwa George Kamitaa-Karurumo Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2894375 | 2894375 | 2894375 | County treasury | N/A | 2894375 | N/A | 2894375 | 100% | 2894375 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kwamethano-Nduva Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kwamethano-Nduva Access Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 3674010 | 3674010 | 3674010 | County treasury | N/A | 3674010 | N/A | 3674010 | 100% | 3494551 | 179459 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantanance Of Njeruri-Ikunduri Kwa Ucuru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantanance Of Njeruri-Ikunduri Kwa Ucuru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Gikuuri-Nthagaiya Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Gikuuri-Nthagaiya Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Kenga-Tea Room Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Kenga-Tea Room Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1742013 | 1742013 | 1742013 | County treasury | N/A | 1742013 | N/A | 1742013 | 100% | 1742013 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Manyattaa Filling Station-Do's Office Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Manyattaa Filling Station-Do's Office Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1539858 | 1539858 | 1539858 | County treasury | N/A | 1539858 | N/A | 1539858 | 100% | 1539858 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mantenance Of Gitare Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mantenance Of Gitare Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2675755 | 2675755 | 2675755 | County treasury | N/A | 2675755 | N/A | 2675755 | 100% | 3141727 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Muthano-Kianamu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Muthano-Kianamu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2394379 | 2394379 | 2394379 | County treasury | N/A | 2394379 | N/A | 2394379 | 100% | 2059835 | 334544 | N/A | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kombo-Katharane Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kombo-Katharane Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2992974 | 2992974 | 2992974 | County treasury | N/A | 2992974 | N/A | 2992974 | 100% | 2720560 | 272414 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Kamurugu-Ngiori Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Kamurugu-Ngiori Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1393137 | 1393137 | 1393137 | County treasury | N/A | 1393137 | N/A | 1393137 | 100% | 1393137 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Gitaraka-Twenze Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Gitaraka-Twenze Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2780897 | 2780897 | 2780897 | County treasury | N/A | 2780897 | N/A | 2780897 | 100% | 2780897 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Gitaraka-Twenze Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Gitaraka-Twenze Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 893113 | 893113 | 893113 | County treasury | N/A | 893113 | N/A | 893113 | 100% | 893113 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Wakaria-Kwa Muroba Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Wakaria-Kwa Muroba Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 898489 | 898489 | 898489 | County treasury | N/A | 898489 | N/A | 898489 | 100% | 898489 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwamweli Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwamweli Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 3291558 | 3291558 | 3291558 | County treasury | N/A | 3291558 | N/A | 3291558 | 100% | 2667988 | 623570 | N/A | Completed | 81% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gategi-Koma Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gategi-Koma Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1997108 | 1997108 | 1997108 | County treasury | N/A | 1997108 | N/A | 1997108 | 100% | 1997108 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Karingari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Karingari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2385418 | 2385418 | 2385418 | County treasury | N/A | 2385418 | N/A | 2385418 | 100% | 2385418 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kaguchori-Kianjeru-Mutharanderi-Gatitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kaguchori-Kianjeru-Mutharanderi-Gatitu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1500071 | 1500071 | 1500071 | County treasury | N/A | 1500071 | N/A | 1500071 | 100% | 1440033 | 60038 | N/A | Ongoing | 96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Mutira B-Keruri Primary Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Mutira B-Keruri Primary Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 917885 | 82162 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Karingari-Ruganga Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Karingari-Ruganga Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2385418 | 2385418 | 2385418 | County treasury | N/A | 2385418 | N/A | 2385418 | 100% | 2385418 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kithunguthia -Muva-Gichuru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kithunguthia -Muva-Gichuru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 1000047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamumu Junction- Karerema Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kamumu Junction- Karerema Junction Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2175000 | 2175000 | 2175000 | County treasury | N/A | 2175000 | N/A | 2175000 | 100% | 2175000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Kivwe-Mwanya Wa Kavari Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Kivwe-Mwanya Wa Kavari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2771936 | 2771936 | 2771936 | County treasury | N/A | 2771936 | N/A | 2771936 | 100% | 1804148 | 967788 | N/A | Ongoing | 65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Itiira-Mianjatiri Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Itiira-Mianjatiri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2386613 | 2386613 | 2386613 | County treasury | N/A | 2386613 | N/A | 2386613 | 100% | 2386613 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Siakago-Kathitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Siakago-Kathitu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2997753 | 2997753 | 2997753 | County treasury | N/A | 2997753 | N/A | 2997753 | 100% | 2997753 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kaiga-Karume-Kyfiti-Mutumbai-Kathuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kaiga-Karume-Kyfiti-Mutumbai-Kathuri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 951837 | 48210 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kiandathi-Mururiri-Kambo-Kathigai Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kiandathi-Mururiri-Kambo-Kathigai Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1299345 | 1299345 | 1299345 | County treasury | N/A | 1299345 | N/A | 1299345 | 100% | 1237245 | 62100 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kathangari-Kevote-Kamugere-Kasarani Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kathangari-Kevote-Kamugere-Kasarani Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 915837 | 84210 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Gatura-Mathiga A And B -Ngurueri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Gatura-Mathiga A And B -Ngurueri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 951837 | 48210 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kiethetu-Ndagakira-Kabuge-Kiambugi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kiethetu-Ndagakira-Kabuge-Kiambugi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1500071 | 1500071 | 1500071 | County treasury | N/A | 1500071 | N/A | 1500071 | 100% | 1500071 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kathanjuri-Nginda-Kariguri-Kaguchori Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kathanjuri-Nginda-Kariguri-Kaguchori Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1500071 | 1500071 | 1500071 | County treasury | N/A | 1500071 | N/A | 1500071 | 100% | 1500071 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Igarie-Ack Kibogi-Muthageri-Kavari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Igarie-Ack Kibogi-Muthageri-Kavari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 1000047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Ndatu-Allumano Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Ndatu-Allumano Primary School Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2180510 | 2180510 | 2180510 | County treasury | N/A | 2180510 | N/A | 2180510 | 100% | 2100757 | 79753 | N/A | Ongoing | 96% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Gikingiri-Riandu-Ciambugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Gikingiri-Riandu-Ciambugu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2780000 | 2780000 | 2780000 | County treasury | N/A | 2780000 | N/A | 2780000 | 100% | 2780000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kanyangi-Mbaraga-Ishiara Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kanyangi-Mbaraga-Ishiara Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Kamumu Junction-Ngunyumu-Uvariri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Kamumu Junction-Ngunyumu-Uvariri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndune-Manyati-Mulukusi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndune-Manyati-Mulukusi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2018-01-07 | 3996606 | 3996606 | 3996606 | County treasury | N/A | 3996606 | N/A | 3996606 | 100% | 3996606 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintance Of Karura-Kathari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintance Of Karura-Kathari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 892516 | 892516 | 892516 | County treasury | N/A | 892516 | N/A | 892516 | 100% | 892516 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Improvement Of Drainage System Across The Ward | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Improvement Of Drainage System Across The Ward |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 998853 | 998853 | 998853 | County treasury | N/A | 998853 | N/A | 998853 | 100% | 998853 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutuobare Market-Shauri-Riacina Primary School-Mutuobare Cattle Dip Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mutuobare Market-Shauri-Riacina Primary School-Mutuobare Cattle Dip Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2780300 | 2780300 | 2780300 | County treasury | N/A | 2780300 | N/A | 2780300 | 100% | 2442768 | 339532 | N/A | Ongoing | 88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Ntharawe-Tamaka Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Ntharawe-Tamaka Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1995316 | 1995316 | 1995316 | County treasury | N/A | 1995316 | N/A | 1995316 | 100% | 1995316 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Drainage Works On A Section Of Ngangari Road | Excavation, Culvert installation | To provide smooth passability by vihicles | well-drained road | Road | Drainage Works On A Section Of Ngangari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2245627 | 2245627 | 2245627 | County treasury | N/A | 2245627 | N/A | 2245627 | 100% | 2060552 | 185075 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Improvement Of Drainage System Across The Ward | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Improvement Of Drainage System Across The Ward |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2781484 | 2781484 | 2781484 | County treasury | N/A | 2781484 | N/A | 2781484 | 100% | 2779822 | 1662 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njeru Gukemba-Kimangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Njeru Gukemba-Kimangaru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2985805 | 2985805 | 2985805 | County treasury | N/A | 2985805 | N/A | 2985805 | 100% | 2985805 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kamau Kathiaka-Itabua Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kamau Kathiaka-Itabua Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2975052 | 2975052 | 2975052 | County treasury | N/A | 2975052 | N/A | 2975052 | 100% | 2975052 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mukiria-Mangote-Karerema Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Mukiria-Mangote-Karerema Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1992209 | 7791 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kikumene-Kithaayoni Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kikumene-Kithaayoni Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 593816 | 593816 | 593816 | County treasury | N/A | 593816 | N/A | 593816 | 100% | 593816 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makahawani Kamweli Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Makahawani Kamweli Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 998853 | 998853 | 998853 | County treasury | N/A | 998853 | N/A | 998853 | 100% | 998853 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriko-Riandu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiriko-Riandu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3096143 | 3096143 | 3096143 | County treasury | N/A | 3096143 | N/A | 3096143 | 100% | 2770443 | 325700 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Gatakari-Karambari Road | Route survey, clearing, earthworks and construction | To improve accessibility and connectivity | New towns lacking road infrastructure now accessible | Road | Opening Of Gatakari-Karambari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1890827 | 1890827 | 1890827 | County treasury | N/A | 1890827 | N/A | 1890827 | 100% | 1890827 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Mukuuri Junction-Gogo Road | Earthwork, pavement construction, drainage inastallation | To ensure safe, durable and efficient trasportation | Improved connectivity | Road | Completion Of Mukuuri Junction-Gogo Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Mugui-Gichuki Road | Earthwork, pavement construction, drainage inastallation | To ensure safe, durable and efficient trasportation | Improved connectivity | Road | Completion Of Mugui-Gichuki Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 750000 | 750000 | 750000 | County treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Thingingi-Gitakari Road | Earthwork, pavement construction, drainage inastallation | To ensure safe, durable and efficient trasportation | Improved connectivity | Road | Completion Of Thingingi-Gitakari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 750000 | 750000 | 750000 | County treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithiruri-Kathande-Paskwale Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kithiruri-Kathande-Paskwale Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jirani Buying Centre-Kanyaari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Jirani Buying Centre-Kanyaari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Siakago Police Station-Mianjatiri Drift | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Siakago Police Station-Mianjatiri Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1175683 | 1175683 | 1175683 | County treasury | N/A | 1175683 | N/A | 1175683 | 100% | 1000764 | 174919 | N/A | Ongoing | 85% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kagumori-A.C.K Kambevo-Karimari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kagumori-A.C.K Kambevo-Karimari Road |  | Kirimari |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1966043 | 1966043 | 1966043 | County treasury | N/A | 1966043 | N/A | 1966043 | 100% | 1966043 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karuari-Mukongoro-Gwa Gichonge Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karuari-Mukongoro-Gwa Gichonge Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1451682 | 1451682 | 1451682 | County treasury | N/A | 1451682 | N/A | 1451682 | 100% | 1451682 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakurungu-Ngere Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gakurungu-Ngere Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1379944 | 1379944 | 1379944 | County treasury | N/A | 1379944 | N/A | 1379944 | 100% | 1379944 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gicherori-Kithiria Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | More resilient road network | Road | Maintenance Of Gicherori-Kithiria Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 982126 | 982126 | 982126 | County treasury | N/A | 982126 | N/A | 982126 | 100% | 982126 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Kabara Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Kabara Bridge |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3179345 | 320655 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Ngwego Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Ngwego Bridge |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 4500000 | 4500000 | 4500000 | County treasury | N/A | 4500000 | N/A | 4500000 | 100% | 3999547 | 500453 | N/A | Ongoing | 89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Rianjagi Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Rianjagi Bridge |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3179674 | 320326 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Itundu Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Itundu Bridge |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 3654518 | 654518 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Mashiara – Mucue Bridge | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Completion Of Mashiara – Mucue Bridge |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2159697 | 340303 | N/A | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation Of Culverts |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 361144 | 61144 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Installation Of Culverts | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Proposed Installation Of Culverts |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1973525 | 26475 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Culverts Of Open Roads (Kivue – Getua Road And Karambari – Kiang’anja Road) | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Proposed Construction Of Culverts Of Open Roads (Kivue – Getua Road And Karambari – Kiang’anja Road) |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2700000 | 2700000 | 2700000 | County treasury | N/A | 2700000 | N/A | 2700000 | 100% | 2664464 | 35536 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Gwa Gatui Box Culvert | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Gwa Gatui Box Culvert |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2650370 | 2650370 | 2650370 | County treasury | N/A | 2650370 | N/A | 2650370 | 100% | 2421353 | 229017 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Improvement Of Drainage System | Procurement, quality assurance | To enhance safety, functionality and usability | Enhanced infrustructure | Road | Improvement Of Drainage System |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1990656 | 9344 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of Proposed Kiogora Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of Proposed Kiogora Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3426567 | 734333 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of The Proposed Mianjatiri - Thura Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of The Proposed Mianjatiri - Thura Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Irenge Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Proposed Construction Of Irenge Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3426567 | 734333 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Proposed Construction Of Ndatu -Kanguuri Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Proposed Construction Of Ndatu -Kanguuri Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1661847 | 338153 | N/A | Ongoing | 83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mukongoro-Muthigi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mukongoro-Muthigi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1451682 | 1451682 | 1451682 | County treasury | N/A | 1451682 | N/A | 1451682 | 100% | 1451682 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kangethia-Kiandome Gwa Kaari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kangethia-Kiandome Gwa Kaari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 967788 | 967788 | 967788 | County treasury | N/A | 967788 | N/A | 967788 | 100% | 967788 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rugumu-Muthigi-Mukongoro Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Rugumu-Muthigi-Mukongoro Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1928407 | 1928407 | 1928407 | County treasury | N/A | 1928407 | N/A | 1928407 | 100% | 1928407 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Jikaze-Gitiburi-Kwa Andu Ambogo School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Jikaze-Gitiburi-Kwa Andu Ambogo School Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 991684 | 991684 | 991684 | County treasury | N/A | 991684 | N/A | 991684 | 100% | 991684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Cianyi-Matangiri-Ikindu Drift-Ndatu River Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Cianyi-Matangiri-Ikindu Drift-Ndatu River Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 902074 | 902074 | 902074 | County treasury | N/A | 902074 | N/A | 902074 | 100% | 902074 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyonga-Sinai Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kanyonga-Sinai Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 798842 | 201158 | N/A | Ongoing | 80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of A Section Of Unguni Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of A Section Of Unguni Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 416387 | 83613 | N/A | Ongoing | 83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Macembe-Rwethe Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Macembe-Rwethe Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 878178 | 878178 | 878178 | County treasury | N/A | 878178 | N/A | 878178 | 100% | 612335 | 265843 | N/A | Ongoing | 70% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karue-Ngai Ndethia-Musungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karue-Ngai Ndethia-Musungu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 951837 | 48210 | N/A | Completed | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Michegethio Muruathayia Road | Clearing, excavation and cutting | To establish a defined and accessible roadway | Improved connectivity | Road | Opening Of Michegethio Muruathayia Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kathangari-Gituri- St Joseph Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kathangari-Gituri- St Joseph Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 918234 | 81813 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gwakandii-Ngirimari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gwakandii-Ngirimari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3713871 | 3713871 | 3713871 | County treasury | N/A | 3713871 | N/A | 3713871 | 100% | 3713871 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kairuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kairuri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1588785 | 1588785 | 1588785 | County treasury | N/A | 1588785 | N/A | 1588785 | 100% | 1588785 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kabara-Kwa Dauti Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kabara-Kwa Dauti Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1684668 | 1684668 | 1684668 | County treasury | N/A | 1684668 | N/A | 1684668 | 100% | 1684668 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kau-Kangaara Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kau-Kangaara Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2996558 | 2996558 | 2996558 | County treasury | N/A | 2996558 | N/A | 2996558 | 100% | 2944107 | 52451 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gichagi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gichagi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 1000047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karungu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karungu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1489318 | 1489318 | 1489318 | County treasury | N/A | 1489318 | N/A | 1489318 | 100% | 1489318 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Gacagori-Gitare Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenace Of Gacagori-Gitare Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1500071 | 1500071 | 1500071 | County treasury | N/A | 1500071 | N/A | 1500071 | 100% | 1500071 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Cattle Dip-Kathari-Gaturi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Cattle Dip-Kathari-Gaturi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tarmac-Mufu-Kwamburi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tarmac-Mufu-Kwamburi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njeruri-Mvuturi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Njeruri-Mvuturi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriga-Karundori | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiriga-Karundori |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1190021 | 1190021 | 1190021 | County treasury | N/A | 1190021 | N/A | 1190021 | 100% | 1190021 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rukuriri-Nthumbira Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Rukuriri-Nthumbira Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatitu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gatitu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1500072 | 1500072 | 1500072 | County treasury | N/A | 1500072 | N/A | 1500072 | 100% | 1500072 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tunai Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tunai Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 1000047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenace Of Gachuki Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenace Of Gachuki Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000047 | 1000047 | 1000047 | County treasury | N/A | 1000047 | N/A | 1000047 | 100% | 1000047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Enna-Nduuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Enna-Nduuri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1458662 | 1458662 | 1458662 | County treasury | N/A | 1458662 | N/A | 1458662 | 100% | 1458662 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karingari Market Shed | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karingari Market Shed |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 290827 | 290827 | 290827 | County treasury | N/A | 290827 | N/A | 290827 | 100% | 290827 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karingari Sloughter-Mirundi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karingari Sloughter-Mirundi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 976749 | 976749 | 976749 | County treasury | N/A | 976749 | N/A | 976749 | 100% | 976749 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Karingari-Nemburi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Karingari-Nemburi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 955840 | 955840 | 955840 | County treasury | N/A | 955840 | N/A | 955840 | 100% | 955840 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njakairi Junction-Karurina-Kithumi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Njakairi Junction-Karurina-Kithumi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1799369 | 1799369 | 1799369 | County treasury | N/A | 1799369 | N/A | 1799369 | 100% | 1799369 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Njiru Advocate-Kangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Njiru Advocate-Kangaru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1614772 | 1614772 | 1614772 | County treasury | N/A | 1614772 | N/A | 1614772 | 100% | 1614772 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kutus Whole Sellers-Liberty Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kutus Whole Sellers-Liberty Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1523370 | 1523370 | 1523370 | County treasury | N/A | 1523370 | N/A | 1523370 | 100% | 1523370 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gaciigi-Keria Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gaciigi-Keria Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1446305 | 1446305 | 1446305 | County treasury | N/A | 1446305 | N/A | 1446305 | 100% | 1254421 | 191884 | N/A | Ongoing | 88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kiriari-Rwere-Kenga Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kiriari-Rwere-Kenga Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1935576 | 1935576 | 1935576 | County treasury | N/A | 1935576 | N/A | 1935576 | 100% | 1666685 | 268891 | N/A | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gacigi-Kwamwaniki Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gacigi-Kwamwaniki Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 970775 | 970775 | 970775 | County treasury | N/A | 970775 | N/A | 970775 | 100% | 891440 | 79335 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Martiru-Kiamatogi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Martiru-Kiamatogi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2090064 | 2090064 | 2090064 | County treasury | N/A | 2090064 | N/A | 2090064 | 100% | 1802236 | 287828 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatururu-Ngimari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gatururu-Ngimari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 492736 | 492736 | 492736 | County treasury | N/A | 492736 | N/A | 492736 | 100% | 468362 | 24374 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kirigi-Mukanguroad | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kirigi-Mukanguroad |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 483894 | 483894 | 483894 | County treasury | N/A | 483894 | N/A | 483894 | 100% | 448695 | 35199 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of St Micheal Pri Sch And Kapingazi-Kangaru Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of St Micheal Pri Sch And Kapingazi-Kangaru Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1526954 | 1526954 | 1526954 | County treasury | N/A | 1526954 | N/A | 1526954 | 100% | 1526954 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kinpost Old Stadium Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kinpost Old Stadium Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1616564 | 1616564 | 1616564 | County treasury | N/A | 1616564 | N/A | 1616564 | 100% | 1616564 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Rurima’s Building-Sport Club Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Rurima’s Building-Sport Club Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 681036 | 681036 | 681036 | County treasury | N/A | 681036 | N/A | 681036 | 100% | 650568 | 30468 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Aic Church-Ap’s Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Aic Church-Ap’s Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 899684 | 899684 | 899684 | County treasury | N/A | 899684 | N/A | 899684 | 100% | 827925 | 71759 | N/A | Ongoing | 92% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nyangeri-Tarmac Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Nyangeri-Tarmac Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1500071 | 1500071 | 1500071 | County treasury | N/A | 1500071 | N/A | 1500071 | 100% | 1330063 | 170008 | N/A | Ongoing | 89% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Dozing Of Kagaari Access Road | Clearing, grubbing, cutting and filling | To provide a well-prepared road corridor that supports durable pavememnt construction | well dozed road corridor | Road | Dozing Of Kagaari Access Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2497132 | 2497132 | 2497132 | County treasury | N/A | 2497132 | N/A | 2497132 | 100% | 2247419 | 249713 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Whispering Hotel-Miriti Tarmack Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Whispering Hotel-Miriti Tarmack Junction Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1136255 | 1136255 | 1136255 | County treasury | N/A | 1136255 | N/A | 1136255 | 100% | 1136255 | N/A | N/A | Completed | 100%\ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gatunduri Full Gospel-Mageca Junction Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gatunduri Full Gospel-Mageca Junction Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 508985 | 508985 | 508985 | County treasury | 508985 | 508985 | N/A | 508985 | 100% | 508985 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mageca Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mageca Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1490110 | 1490110 | 1490110 | County treasury | N/A | 1490110 | N/A | 1490110 | 100% | 1490110 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kithecu-Migwi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kithecu-Migwi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 991684 | 991684 | 991684 | County treasury | N/A | 991684 | N/A | 991684 | 100% | 991684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of The Proposed Unguni Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction Of The Proposed Unguni Drift |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1780730 | 1780730 | 1780730 | County treasury | N/A | 1780730 | N/A | 1780730 | 100% | 1410163 | 370567 | N/A | Ongoing | 79% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gakwegori-Kapingazi Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gakwegori-Kapingazi Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 781.399.20 | 781.399.20 | 781.399.20 | County treasury | N/A | 781.399.20 | N/A | 781.399.20 | 100% | 686771 | 94568 | N/A | Ongoing | 88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintence Of Kamiu-Kabuga-Bluevalley Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintence Of Kamiu-Kabuga-Bluevalley Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 899684 | 899684 | 899684 | County treasury | N/A | 899684 | N/A | 899684 | 100% | 782285 | 117399 | N/A | Ongoing | 87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Makathi-Mutunduri-Gatunduri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Makathi-Mutunduri-Gatunduri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2082536 | 2082536 | 2082536 | County treasury | N/A | 2082536 | N/A | 2082536 | 100% | 2055725 | 26811 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kairungu-Mutunduri-Tarmac Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kairungu-Mutunduri-Tarmac Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2082536 | 2082536 | 2082536 | County treasury | N/A | 2082536 | N/A | 2082536 | 100% | 2053502 | 29034 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Mdogo-Kamiu-Catholic Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Mdogo-Kamiu-Catholic Church Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1746798 | 1746798 | 1746798 | County treasury | N/A | 1746798 | N/A | 1746798 | 100% | 1746798 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanjikeru-Kiereri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kanjikeru-Kiereri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1845966 | 1845966 | 1845966 | County treasury | N/A | 1845966 | N/A | 1845966 | 100% | 1845966 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimangaru-Gikingiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kimangaru-Gikingiri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1298748 | 1298748 | 1298748 | County treasury | N/A | 1298748 | N/A | 1298748 | 100% | 1298748 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mugoya-Kimando Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mugoya-Kimando Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1491110 | 1491110 | 1491110 | County treasury | N/A | 1491110 | N/A | 1491110 | 100% | 1352036 | 13974 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimandu-Ithara Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kimandu-Ithara Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1928407 | 1928407 | 1928407 | County treasury | N/A | 1928407 | N/A | 1928407 | 100% | 1928407 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kimangaru-Itabua Day Sec Sch Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kimangaru-Itabua Day Sec Sch Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1684668 | 1684668 | 1684668 | County treasury | N/A | 1684668 | N/A | 1684668 | 100% | 1684668 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ugweri-Market-Ack Church Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ugweri-Market-Ack Church Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1411358 | 1411358 | 1411358 | County treasury | N/A | 1411358 | N/A | 1411358 | 100% | 1411358 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tarmac-Kanduri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tarmac-Kanduri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1946329 | 1946329 | 1946329 | County treasury | N/A | 1946329 | N/A | 1946329 | 100% | 1946329 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gachiriro-Kathugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gachiriro-Kathugu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2150640 | 2150640 | 2150640 | County treasury | N/A | 2150640 | N/A | 2150640 | 100% | 1892563 | 258077 | N/A | Ongoing | 88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Nemburi-Nduuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Nemburi-Nduuri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3354999 | 3354999 | 3354999 | County treasury | N/A | 3354999 | N/A | 3354999 | 100% | 3333492 | 21507 | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gachoka-Gachuriri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gachoka-Gachuriri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3877126 | 3877126 | 3877126 | County treasury | N/A | 3877126 | N/A | 3877126 | 100% | 3877126 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndivuri-Burrow Pit-Bethel Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndivuri-Burrow Pit-Bethel Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1230644 | 1230644 | 1230644 | County treasury | N/A | 1230644 | N/A | 1230644 | 100% | 1230644 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kanyariri-Ngangari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kanyariri-Ngangari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1432267 | 167733 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Manyatta-Kithanje-Kiaragana Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Manyatta-Kithanje-Kiaragana Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2000095 | 2000095 | 2000095 | County treasury | N/A | 2000095 | N/A | 2000095 | 100% | 2000095 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mutunduri-Rianjagi-Guakiande Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mutunduri-Rianjagi-Guakiande Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2763572 | 2763572 | 2763572 | County treasury | N/A | 2763572 | N/A | 2763572 | 100% | 2763572 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Gitumbu Vct-Kiandundu Access Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Gitumbu Vct-Kiandundu Access Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2418275 | 2418275 | 2418275 | County treasury | N/A | 2418275 | N/A | 2418275 | 100% | 2388166 | 30108 | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muthanthara-Muiru-Kigori Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Muthanthara-Muiru-Kigori Primary School Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 797529 | 797529 | 797529 | County treasury | N/A | 797529 | N/A | 797529 | 100% | 536465 | 261064 | N/A | Ongoing | 67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mukiria-Kamukanya-Karangiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mukiria-Kamukanya-Karangiri Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1397816 | 1397816 | 1397816 | County treasury | N/A | 1397816 | N/A | 1397816 | 100% | 1031112 | 366704 | N/A | Ongoing | 74% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kamraciri-Mutiria Iguru-Kabugu Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Kamraciri-Mutiria Iguru-Kabugu Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 878178 | 878178 | 878178 | County treasury | N/A | 878178 | N/A | 878178 | 100% | 587842 | 290336 | N/A | Ongoing | 67% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kamumu-Karerema-Ishiara Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Kamumu-Karerema-Ishiara Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 474944 | 474944 | 474944 | County treasury | N/A | 474944 | N/A | 474944 | 100% | 407487 | 67457 | N/A | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Mugoyio-Ena-Kathangutari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Mugoyio-Ena-Kathangutari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 597977 | 597977 | 597977 | County treasury | N/A | 597977 | N/A | 597977 | 100% | 597977 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Police-Gacegi-Kangari Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Police-Gacegi-Kangari Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 860256 | 860256 | 860256 | County treasury | N/A | 860256 | N/A | 860256 | 100 | 860256 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Police-Mbaraga-Kangiti-Ena River Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Police-Mbaraga-Kangiti-Ena River Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 716880 | 716880 | 716880 | County treasury | N/A | 716880 | N/A | 716880 | 100% | 716880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Karengero-Rweria-Kanyuambora Market Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Karengero-Rweria-Kanyuambora Market Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 740776 | 740776 | 740776 | County treasury | N/A | 740776 | N/A | 740776 | 100% | 740776 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Opening Of Bahati Junction-Usambara Junction | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Opening Of Bahati Junction-Usambara Junction |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3540000 | 3540000 | 3540000 | County treasury | N/A | 3540000 | N/A | 3540000 | 100% | 3061078 | 478922 | N/A | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Riacina Kanthenge Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Riacina Kanthenge Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1406877 | 93123 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Kwa Kisilu-Mwanzo Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Kwa Kisilu-Mwanzo Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 1406877 | 1593123 | N/A | Ongoing | 47% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Mwanzo-Gatuanyaga Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Mwanzo-Gatuanyaga Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1251194 | 248806 | N/A | Ongoing | 83% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Ndume-Kithuyani Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Ndume-Kithuyani Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 946281 | 53719 | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Muchonoke-Kambaru Primary School Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Muchonoke-Kambaru Primary School Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2102848 | 2102848 | 2102848 | County treasury | N/A | 2102848 | N/A | 2102848 | 100% | 1949914 | 152934 | N/A | Ongoing | 93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Wakibia-Rithori-Water Well Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Wakibia-Rithori-Water Well Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1756356 | 1756356 | 1756356 | County treasury | N/A | 1756356 | N/A | 1756356 | 100% | 1658382 | 97974 | N/A | Ongoing | 94% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Kirindiri-Polytechnic Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Completion Of Kirindiri-Polytechnic Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1786823 | 1786823 | 1786823 | County treasury | N/A | 1786823 | N/A | 1786823 | 100% | 1634463 | 152360 | N/A | Ongoing | 91% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Kinthithe-Gachonge Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Completion Of Kinthithe-Gachonge Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 1623733 | 1623733 | 1623733 | County treasury | N/A | 1623733 | N/A | 1623733 | 100% | 1455027 | 168706 | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Maintenance Of Tarmac Judge Nduma Road | Resurfacing, cleaning, grass cutting and debris clearing | To maintain and improve the condition of existing roads | Improved road condition and year-round accessibility | Road | Maintenance Of Tarmac Judge Nduma Road |  |  |  | Road | Road | Road | 2017-01-07 | 2017-01-01 | 30/6/2018 | 2017-01-07 | 2264146 | 2264146 | 2264146 | County treasury | N/A | 2264146 | N/A | 2264146 | 100% | 2003680 | 260466 | N/A | Ongoing | 88% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2016/2017
| Kavondori-Gikondi Road-1.5M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kavondori-Gikondi Road-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1534482 | 1534482 | 1534482 | County treasury | N/A | 1534482 | N/A | 1534482 | 100% | 1534482 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mukombia-Kathuri-Gachara Road-1.65M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Mukombia-Kathuri-Gachara Road-1.65M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1646982 | 1646982 | 1646982 | County treasury | N/A | 1646982 | N/A | 1646982 | 100% | 1646982 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Wakaria-Gitaraka-Wango Road-1.5 M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Wakaria-Gitaraka-Wango Road-1.5 M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1681464 | 1681464 | 1681464 | County treasury | N/A | 1681464 | N/A | 1681464 | 100% | 1681464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gategi-Ngandi Road-1.6M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Gategi-Ngandi Road-1.6M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Mutuobare-Karura Road-1.7M | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Mutuobare-Karura Road-1.7M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1701395 | 1701395 | 1701395 | County treasury | N/A | 1701395 | N/A | 1701395 | 100% | 1701395 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Spot Murraming of Newsite-Mutuobare Road-1.4M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Spot Murraming of Newsite-Mutuobare Road-1.4M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1480086 | 1480086 | 1480086 | County treasury | N/A | 1480086 | N/A | 1480086 | 100% | 1480086 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kathugu Bridge/Drift-1.2M | excavation, constructionand installation | To improve conectivity and reliable passage across waterways | well constructed drifts | well looking housoe | Kathugu Bridge/Drift-1.2M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kithungururu-Kathangari Road-1.5M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kithungururu-Kathangari Road-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1656823 | 1656823 | 1656823 | County treasury | N/A | 1656823 | N/A | 1656823 | 100% | 1656823 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kangaru-Mikimbi-Nthambo-1.6M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kangaru-Mikimbi-Nthambo-1.6M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1524641 | 1524641 | 1524641 | County treasury | N/A | 1524641 | N/A | 1524641 | 100% | 1524641 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Widening and Murraming of Ndatu-Allamano-Kiaragana road-2.18M | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Widening and Murraming of Ndatu-Allamano-Kiaragana road-2.18M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kianjokoma Kagucu Road-1.1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kianjokoma Kagucu Road-1.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1184473 | 1184473 | 1184473 | County treasury | N/A | 1184473 | N/A | 1184473 | 100% | 1184473 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Muchagori Road-1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Muchagori Road-1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 997999 | 997999 | 997999 | County treasury | N/A | 997999 | N/A | 997999 | 100% | 997999 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Nguire Road-1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Nguire Road-1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 998992 | 998992 | 998992 | County treasury | N/A | 998992 | N/A | 998992 | 100% | 998992 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Nembure-Iriari Road-2.1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Nembure-Iriari Road-2.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Semi opening and Grading of Itiira-Ndutori-Gangara Road-3.1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Semi opening and Grading of Itiira-Ndutori-Gangara Road-3.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mwondu-Kaungu-Wangiro Road-2.5M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Mwondu-Kaungu-Wangiro Road-2.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murramming Cereals-Kamiu-GTI Road-1.5M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murramming Cereals-Kamiu-GTI Road-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming Muthatari-Mugoya-Karurina Road-1.6M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murraming Muthatari-Mugoya-Karurina Road-1.6M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1581464 | 1581464 | 1581464 | County treasury | N/A | 1581464 | N/A | 1581464 | 100% | 1581464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rwika-Rianjeru Road-1.1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Rwika-Rianjeru Road-1.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gikuuri Ivari Road-1.2M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Gikuuri Ivari Road-1.2M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Ngambari-Kinthithe-Gichonge Road-1.5M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murraming of Ngambari-Kinthithe-Gichonge Road-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rukuriri-Karigiri Road-1.5M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Rukuriri-Karigiri Road-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 10% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Mwiria Factory-Ewasco-Mukongori-Mbuvori-1.1M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Mwiria Factory-Ewasco-Mukongori-Mbuvori-1.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2057421 | 2057421 | 2057421 | County treasury | N/A | 2057421 | N/A | 2057421 | 100% | 2057421 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kibugu Market-Kangethia-Kiambogo-Kathangariri-Muvandori to Muthegi(Nginda/Ngandori water reservoir to Mukongoro)-2M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kibugu Market-Kangethia-Kiambogo-Kathangariri-Muvandori to Muthegi(Nginda/Ngandori water reservoir to Mukongoro)-2M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1124043 | 1124043 | 1124043 | County treasury | N/A | 1124043 | N/A | 1124043 | 100% | 1124043 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Karuriri-Ndwiga wa Mwathokori-1.5M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Karuriri-Ndwiga wa Mwathokori-1.5M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1471393 | 1471393 | 1471393 | County treasury | N/A | 1471393 | N/A | 1471393 | 100% | 1471393 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kithunguriri-Muguri-Mwenje Njeru-1.6M | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kithunguriri-Muguri-Mwenje Njeru-1.6M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1710071 | 1710071 | 1710071 | County treasury | N/A | 1710071 | N/A | 1710071 | 100% | 1710071 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Drfting Ngeca-Kamunyagia-Mashamba-2.1M | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Drfting Ngeca-Kamunyagia-Mashamba-2.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2100000 | 2100000 | 2100000 | County treasury | N/A | 2100000 | N/A | 2100000 | 100% | 2100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Ndunguni Drift-1M | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | Enhanced road safety for users | Road | Ndunguni Drift-1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1081464 | 1081464 | 1081464 | County treasury | N/A | 1081464 | N/A | 1081464 | 100% | 1081464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Shauri-Soweto Road-3.1M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murraming and Manual Reshaping of Shauri-Soweto Road-3.1M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3181464 | 3181464 | 3181464 | County treasury | N/A | 3181464 | N/A | 3181464 | 100% | 3181464 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kiogogo Market to Thura River-2.8M | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Kiogogo Market to Thura River-2.8M |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1221992 | 1221992 | 1221992 | County treasury | N/A | 1221992 | N/A | 1221992 | 100% | 1221992 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Main Road to Kariuki’s Residence to Chief’s Office | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Main Road to Kariuki’s Residence to Chief’s Office |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1959472 | 1959472 | 1959472 | County treasury | N/A | 1959472 | N/A | 1959472 | 100% | 1959472 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Appropriate Building Technology for Youth Empowerment-Kyeni North | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Appropriate Building Technology for Youth Empowerment-Kyeni North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Tarmacking of Embu-Kibugu Road | Base laying, compaction, construction | To provide a durable all-weathered road | High quality tarmacked road | Road | Tarmacking of Embu-Kibugu Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 346512554 | 346512554 | 346512554 | County treasury | N/A | 346512554 | N/A | 346512554 | 100% | 346512554 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Tarmacking of Kiritiri Market | Base laying, compaction, construction | To provide a durable all-weathered road | High quality tarmacked road | Road | Tarmacking of Kiritiri Market |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 20000000 | 20000000 | 20000000 | County treasury | N/A | 20000000 | N/A | 20000000 | 100% | 20000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kangaara-Kangondi Access road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kangaara-Kangondi Access road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1805419 | 1805419 | 1805419 | County treasury | N/A | 1805419 | N/A | 1805419 | 100% | 1805419 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rianjeru road-Mbeti South | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Rianjeru road-Mbeti South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1801758 | 1801758 | 1801758 | County treasury | N/A | 1801758 | N/A | 1801758 | 100% | 1801758 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kang’ethia-Kiandome | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kang’ethia-Kiandome |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 521360 | 521360 | 521360 | County treasury | N/A | 521360 | N/A | 521360 | 100% | 521360 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kang’ethia-Nthunguri-Kiiye River | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kang’ethia-Nthunguri-Kiiye River |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kariguri-Kamaunju Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kariguri-Kamaunju Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Karurua-Rutumba-Kiambere-Mutuobare Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Karurua-Rutumba-Kiambere-Mutuobare Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1557020 | 1557020 | 1557020 | County treasury | N/A | 1557020 | N/A | 1557020 | 100% | 1557020 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Thau-Kanjatari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Thau-Kanjatari Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 779221 | 779221 | 779221 | County treasury | N/A | 779221 | N/A | 779221 | 100% | 779221 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kwa Njege-Siakago Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kwa Njege-Siakago Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2300000 | 2300000 | 2300000 | County treasury | N/A | 2300000 | N/A | 2300000 | 100% | 2300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kathugu Bridge/Drift-Kagaari South |  | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Kathugu Bridge/Drift-Kagaari South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Thoko Njeru-Ndithiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Thoko Njeru-Ndithiri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3200000 | 3200000 | 3200000 | County treasury | N/A | 3200000 | N/A | 3200000 | 100% | 3200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Ngurueri Factory Road/Bridge | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Ngurueri Factory Road/Bridge |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gategi-Ngandi road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Gategi-Ngandi road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1068749 | 1068749 | 1068749 | County treasury | N/A | 1068749 | N/A | 1068749 | 100% | 1068749 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Muganjuki-Nduuri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Muganjuki-Nduuri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Iriari-Gichegeni Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Iriari-Gichegeni Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Roads-Mbeti South | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Roads-Mbeti South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 10000000 | 10000000 | 10000000 | County treasury | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | N/A | N/A | Completed | 100% | N/A | N/A |  | N/A | N/A
| Road Maintenance-Kagaari South | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Road Maintenance-Kagaari South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 15063629 | 15063629 | 15063629 | County treasury | N/A | 15063629 | N/A | 15063629 | 100% | 15063629 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Improvement of Access Roads-Kithimu | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Improvement of Access Roads-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2875629 | 2875629 | 2875629 | County treasury | N/A | 2875629 | N/A | 2875629 | 100% | 2875629 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kathiruri-Ngirimari-Gaciigi Catholic Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Construction of Kathiruri-Ngirimari-Gaciigi Catholic Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3735000 | 3735000 | 3735000 | County treasury | N/A | 3735000 | N/A | 3735000 | 100% | 3735000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kathuniri-Kathunguri-Mwendano Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Construction of Kathuniri-Kathunguri-Mwendano Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2371857 | 2371857 | 2371857 | County treasury | N/A | 2371857 | N/A | 2371857 | 100% | 2371857 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kiandongo-Kianjokoma Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kiandongo-Kianjokoma Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3360972 | 3360972 | 3360972 | County treasury | N/A | 3360972 | N/A | 3360972 | 100% | 3360972 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Nembure-Rukira-Junction-Kamuthatha Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Nembure-Rukira-Junction-Kamuthatha Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3445803 | 3445803 | 3445803 | County treasury | N/A | 3445803 | N/A | 3445803 | 100% | 3445803 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading of ACK Church Old Stadium –Emmanuel Pry. School Road | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading of ACK Church Old Stadium –Emmanuel Pry. School Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2193653 | 2193653 | 2193653 | County treasury | N/A | 2193653 | N/A | 2193653 | 100% | 2193653 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kasafari-Isaaco Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kasafari-Isaaco Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1506057 | 1506057 | 1506057 | County treasury | N/A | 1506057 | N/A | 1506057 | 100% | 1506057 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading of Gwakaithi-Iriri-Kanyangi Road | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading of Gwakaithi-Iriri-Kanyangi Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3239103 | 3239103 | 3239103 | County treasury | N/A | 3239103 | N/A | 3239103 | 100% | 3239103 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Gatunduri-Njakairi,Gatunduri-Mucunoke-ACK,Nembure-Karingari-Kagumori-Runganga Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Gatunduri-Njakairi,Gatunduri-Mucunoke-ACK,Nembure-Karingari-Kagumori-Runganga Roads |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3031105 | 3031105 | 3031105 | County treasury | N/A | 3031105 | N/A | 3031105 | 100% | 3031105 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kaveti-Karurumo-Kathunguri,Karurumo-Kasafari Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kaveti-Karurumo-Kathunguri,Karurumo-Kasafari Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2962210 | 2962210 | 2962210 | County treasury | N/A | 2962210 | N/A | 2962210 | 100% | 2962210 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Mondu-Kwa Rukungu-Riandu-Gikingiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Mondu-Kwa Rukungu-Riandu-Gikingiri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 925970 | 925970 | 925970 | County treasury | N/A | 925970 | N/A | 925970 | 100% | 925970 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading of EAPC Church Kathari-Kathugu Factory Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Grading of EAPC Church Kathari-Kathugu Factory Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3951801 | 3951801 | 3951801 | County treasury | N/A | 3951801 | N/A | 3951801 | 100% | 3951801 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ena Njeru Ithiga-Gatakari,Ena-Munandari-Mashiara,Gatunduri Kagwaci-Gichegeri-Kwa Juster Roads | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ena Njeru Ithiga-Gatakari,Ena-Munandari-Mashiara,Gatunduri Kagwaci-Gichegeri-Kwa Juster Roads |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3699922 | 3699922 | 3699922 | County treasury | N/A | 3699922 | N/A | 3699922 | 100% | 3699922 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Roads-Minor Repairs | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Roads-Minor Repairs |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4975907 | 4975907 | 4975907 | County treasury | N/A | 4975907 | N/A | 4975907 | 100% | 4975907 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| 12M Foot Bridge on Thuchi River at Kyeni | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | 12M Foot Bridge on Thuchi River at Kyeni |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 90309 | 90309 | 90309 | County treasury | N/A | 90309 | N/A | 90309 | 100% | 90309 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rehabilitation of Kwa Gakunju-Kibuguri-Ngaria Road | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Rehabilitation of Kwa Gakunju-Kibuguri-Ngaria Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 847004 | 847004 | 847004 | County treasury | N/A | 847004 | N/A | 847004 | 100% | 847004 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngurweri-Igarie/Gaturumbari Road-Gaturi North | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngurweri-Igarie/Gaturumbari Road-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2250047 | 2250047 | 2250047 | County treasury | N/A | 2250047 | N/A | 2250047 | 100% | 2250047 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Kathiga Kanyoka-Kamanju Road and Katangari Drift | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Kathiga Kanyoka-Kamanju Road and Katangari Drift |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2978258 | 2978258 | 2978258 | County treasury | N/A | 2978258 | N/A | 2978258 | 100% | 2978258 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Karingari Town-Nembure Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Karingari Town-Nembure Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1273657 | 1273657 | 1273657 | County treasury | N/A | 1273657 | N/A | 1273657 | 100% | 1273657 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Iriari-Kavutiri Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Iriari-Kavutiri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1735060 | 1735060 | 1735060 | County treasury | N/A | 1735060 | N/A | 1735060 | 100% | 1735060 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kamwambia-Kasafari-Slip Road and Box Culverts | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Kamwambia-Kasafari-Slip Road and Box Culverts |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3936209 | 3936209 | 3936209 | County treasury | N/A | 3936209 | N/A | 3936209 | 100% | 3936209 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rehabilitation of Mlachake-Kanthenge-Kwa Daisy Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Rehabilitation of Mlachake-Kanthenge-Kwa Daisy Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1883244 | 1883244 | 1883244 | County treasury | N/A | 1883244 | N/A | 1883244 | 100% | 1883244 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Cleaning of Dumpsite | Collection, seggregation and transportation | To improve environmental health and public safety | Well- maintained dumpsite | Road | Cleaning of Dumpsite |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 464000 | 464000 | 464000 | County treasury | N/A | 464000 | N/A | 464000 | 100% | 464000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Gakuyu-Mutambiri Drift | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Gakuyu-Mutambiri Drift |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3530556 | 3530556 | 3530556 | County treasury | N/A | 3530556 | N/A | 3530556 | 100% | 3530556 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Mukuuri-Kirimiri Factory-Ena Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Mukuuri-Kirimiri Factory-Ena Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1405563 | 1405563 | 1405563 | County treasury | N/A | 1405563 | N/A | 1405563 | 100% | 1405563 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Ngiiri Town-Ngiiri Pry Sch. Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Ngiiri Town-Ngiiri Pry Sch. Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3567075 | 3567075 | 3567075 | County treasury | N/A | 3567075 | N/A | 3567075 | 100% | 3567075 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Uvariri-Ngunyumu-Gachoriri- | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Uvariri-Ngunyumu-Gachoriri- |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3900254 | 3900254 | 3900254 | County treasury | N/A | 3900254 | N/A | 3900254 | 100% | 3900254 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Buying of Culverts-Runyenjes S/C Ward | Procurement, delivery and quality verification | To ensure that the right quality culverts are installed | High quality culverts delivered and installed | Road | Buying of Culverts-Runyenjes S/C Ward |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 798000 | 798000 | 798000 | County treasury | N/A | 798000 | N/A | 798000 | 100% | 798000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kirurumwe Coffee Factory Footbridge | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Kirurumwe Coffee Factory Footbridge |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Gicherori-Kwa Gakure-Kwa Kariithi Road | Clearing, earthworks, levelling and compaction | To provide passage to new emerging cities | New towns accessible | Road | Construction of Gicherori-Kwa Gakure-Kwa Kariithi Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2700000 | 2700000 | 2700000 | County treasury | N/A | 2700000 | N/A | 2700000 | 100% | 2700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Uuya Drift | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Uuya Drift |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Thau-Kanjiri Bridge | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Thau-Kanjiri Bridge |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4400000 | 4400000 | 4400000 | County treasury | N/A | 4400000 | N/A | 4400000 | 100% | 4400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Mukangu-Mutabi’s-Mashariki Road | Site preparation, excavation and construction | To improve accessibilty | Well-constructed road | Road | Construction of Mukangu-Mutabi’s-Mashariki Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1010000 | 1010000 | 1010000 | County treasury | N/A | 1010000 | N/A | 1010000 | 100% | 1010000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Maintenance of Spring Valley-Kamiu Road | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Maintenance of Spring Valley-Kamiu Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2700000 | 2700000 | 2700000 | County treasury | N/A | 2700000 | N/A | 2700000 | 100% | 2700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Masiara-Mucuwe bridge | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Masiara-Mucuwe bridge |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kangiri Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kangiri Drift |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | N/A | N/A | Completed | 100% | N/A |  | N/A | N/A | N/A
| Construction of Mbonzuki Drifts | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Mbonzuki Drifts |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Ntharawe/Thura Drift | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Ntharawe/Thura Drift |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3797260 | 3797260 | 3797260 | County treasury | N/A | 3797260 | N/A | 3797260 | 100% | 3797260 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kiogora Drift-Muminji | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kiogora Drift-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3500000 | 3500000 | 3500000 | County treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kathangari drift-Kiambere | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kathangari drift-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Katharane Drift-Makima | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Katharane Drift-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Ndunguni Drift-Makima | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Ndunguni Drift-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Drift/Opening of Kwa Njuguna-Ndaiyu Road-Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Drift/Opening of Kwa Njuguna-Ndaiyu Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Drift/Opening of Gatituri-Gwakathuri Road-Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Drift/Opening of Gatituri-Gwakathuri Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Drift/Opening of Rwaigunyu-Kaageri Road-Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Drift/Opening of Rwaigunyu-Kaageri Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Drift/Opening of Gitumbi-Cianyi Kathana Road-Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Drift/Opening of Gitumbi-Cianyi Kathana Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Drift/Opening of Gikuyari-Kwamwari Road-Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Drift/Opening of Gikuyari-Kwamwari Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Gakuu-Muthambiri Drift -Nthawa | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Completion of Gakuu-Muthambiri Drift -Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Gichangai Bridge at Kwa Ruthiga-Nginda | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Gichangai Bridge at Kwa Ruthiga-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kandubiu Foot Bridge-Thuci River-Evurore | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kandubiu Foot Bridge-Thuci River-Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kakune Foot Bridge-Ena River-Evurore | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kakune Foot Bridge-Ena River-Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Kiunyu Bridge-Ruguru Ngandori | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Kiunyu Bridge-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Foot Bridge at Kamatara/Kirimiri and manual reshaping and opening of Road-Kagaari North | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Foot Bridge at Kamatara/Kirimiri and manual reshaping and opening of Road-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Bridge at Kithinji Mutura-Kagaari North | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Bridge at Kithinji Mutura-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Karirio Bridge-Gaturi North | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction of Karirio Bridge-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of High mast flood lights at Kawanjara Market | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of High mast flood lights at Kawanjara Market |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of High mast flood lights at Nthagaiya Market | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of High mast flood lights at Nthagaiya Market |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers-Kagaari South | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers-Kagaari South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 7500000 | 7500000 | 7500000 | County treasury | N/A | 7500000 | N/A | 7500000 | 100% | 7500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers-Gaturi North | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3550000 | 3550000 | 3550000 | County treasury | N/A | 3550000 | N/A | 3550000 | 100% | 3550000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kangaara-Kithimu | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kangaara-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kamutungi-Kithimu | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kamutungi-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of High mast Flood Light at Majengo Market | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of High mast Flood Light at Majengo Market |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1048000 | 1048000 | 1048000 | County treasury | N/A | 1048000 | N/A | 1048000 | 100% | 1048000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of High mast Flood Light at Kianjuki,Kibogi and Gaikiro markets-Gaturi North | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of High mast Flood Light at Kianjuki,Kibogi and Gaikiro markets-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Conversion of streetlights and floodlights to LED | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Conversion of streetlights and floodlights to LED |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 7000000 | 7000000 | 7000000 | County treasury | N/A | 7000000 | N/A | 7000000 | 100% | 7000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Solar Street Lighting Embu-Meru Road | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Solar Street Lighting Embu-Meru Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 14556000 | 14556000 | 14556000 | County treasury | N/A | 14556000 | N/A | 14556000 | 100% | 14556000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Flood Lights various Places | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Flood Lights various Places |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 11853860 | 11853860 | 11853860 | County treasury | N/A | 11853860 | N/A | 11853860 | 100% | 11853860 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformer at Gaikiro,Muvu,Gitumbi-Gaturi North | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformer at Gaikiro,Muvu,Gitumbi-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 6142000 | 6142000 | 6142000 | County treasury | N/A | 6142000 | N/A | 6142000 | 100% | 6142000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kangone Village-Kithimu | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kangone Village-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1020000 | 1020000 | 1020000 | County treasury | N/A | 1020000 | N/A | 1020000 | 100% | 1020000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers/Line Building at Kimangaru-Mbeti North | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers/Line Building at Kimangaru-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers//Line Building at Kagumori-Mbeti North | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers//Line Building at Kagumori-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kanyakiri-Njaguri,Keria,Riakamakia-Ruguru Ngandori | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kanyakiri-Njaguri,Keria,Riakamakia-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Transformers-Kyeni North | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Transformers-Kyeni North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Improvements of Market Floodlights at Mufu-Kyeni North | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Improvements of Market Floodlights at Mufu-Kyeni North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 430000 | 430000 | 430000 | County treasury | N/A | 430000 | N/A | 430000 | 100% | 430000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Improvements of Market Floodlights at Iriari-Kyeni North | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Improvements of Market Floodlights at Iriari-Kyeni North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 430000 | 430000 | 430000 | County treasury | N/A | 430000 | N/A | 430000 | 100% | 430000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformer at Kiambere Village-Kiambere | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformer at Kiambere Village-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers-Mbeti South | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers-Mbeti South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 6000000 | 6000000 | 6000000 | County treasury | N/A | 6000000 | N/A | 6000000 | 100% | 6000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers-Runyenjes Central | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers-Runyenjes Central |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Four(4) Flood lights-Runyenjes Central | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Four(4) Flood lights-Runyenjes Central |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1520000 | 1520000 | 1520000 | County treasury | N/A | 1520000 | N/A | 1520000 | 100% | 1520000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights-Mbeti South | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights-Mbeti South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Getua-Muminji | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Getua-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers -Nginda | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers -Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 8000000 | 8000000 | 8000000 | County treasury | N/A | 8000000 | N/A | 8000000 | 100% | 8000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kwa Mithamo-Kithimu | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kwa Mithamo-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Karuku Borehole-Mwea | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Karuku Borehole-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 750000 | 750000 | 750000 | County treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Transformers at Kithaayoni Section-Mwea | Supply, installation, testing and commissioning | To address challenges related to inadequate voltage levels and frequent power outages | Installed trasmormers quencing the electricity demand | Road | Installation of Transformers at Kithaayoni Section-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 750000 | 750000 | 750000 | County treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Nthingini Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Nthingini Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Wango Market-Mwea | Site preparation, excavation and installation | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Wango Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Two Flood lights(Solar) at Karaba Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Two Flood lights(Solar) at Karaba Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Gategi Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Gategi Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Mbonzuki Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Mbonzuki Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Gitaraka Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Gitaraka Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Kikumini Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Kikumini Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Iria-Itune Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Iria-Itune Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Two Flood lights(Solar) at Makutano Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Two Flood lights(Solar) at Makutano Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Kamweli Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Kamweli Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Kaseve Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Kaseve Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Kathiani Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Kathiani Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights(Solar) at Wakaria Market-Mwea | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights(Solar) at Wakaria Market-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Makima Market -Makima | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Makima Market -Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Mbondoni Market-Makima | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Mbondoni Market-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Kitoloni Market-Makima | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Kitoloni Market-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Gikuru Market-Makima | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Gikuru Market-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Karau,Kagumori,Kangethia, kathangariri, kibugu in Nginda. | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Karau,Kagumori,Kangethia, kathangariri, kibugu in Nginda. |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Kabubua Kanyama,Kamumu and Kavengero Markets-Evurore | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Kabubua Kanyama,Kamumu and Kavengero Markets-Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Kavungua-Kagaari South | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Kavungua-Kagaari South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| KPLC Lighting (LED)in Majengo,Spring Valley,Koi Mugo and Old Stadium Estates-Kirimari- | Installation of lighting poles, mounting of luminaries and connection to KPLC power | To improve lighting in roads, trading centres | reduced crime around the areas | Road | KPLC Lighting (LED)in Majengo,Spring Valley,Koi Mugo and Old Stadium Estates-Kirimari- |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5500000 | 5500000 | 5500000 | County treasury | N/A | 5500000 | N/A | 5500000 | 100% | 5500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Bumps at Majengo Ring Road-Kirimari | Marking, supply and construction | To prevent accident caused in the area due to everspeeding | ¦Reduced accidents | Road | Construction of Bumps at Majengo Ring Road-Kirimari |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Kithimu Open Air Markets-Kithimu | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Kithimu Open Air Markets-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights (3Lamp)-Mavuria | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights (3Lamp)-Mavuria |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Flood lights at Kararitiri,Munyutu,Kasarani-Kagaari North | Site assessment, mounting structures and installation of flood lights | To improve visibility, safety and security during night time hours | Well -light area | Road | Installation of Flood lights at Kararitiri,Munyutu,Kasarani-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction and Civil works-SUB TOTALS | Site preparation, excavation and installation | To improve drainage, accessibility and safety | More resilient road network | Road | Construction and Civil works-SUB TOTALS |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 156797120 | 156797120 | 156797120 | County treasury | N/A | 156797120 | N/A | 156797120 | 100% | 156797120 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Gakinduriri-Full Gospel-Ngumbuka Road | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murraming of Gakinduriri-Full Gospel-Ngumbuka Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murramming of Murari-Kathunguri Road | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murramming of Murari-Kathunguri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kamwithi- Mugumori Road-Gacagori | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Kamwithi- Mugumori Road-Gacagori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Manual road reshaping and machine Contracting-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Manual road reshaping and machine Contracting-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Roads of 25 Km -Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | Enhanced road safety for users | Road | Murraming of Roads of 25 Km -Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 |  |  |  | County treasury | N/A | [9 empty] | N/A | N/A | N/A | N/A | N/A
| Construction of Karitiri coffee factory foot bridge | Site preparation, excavation and installation | To improve road accessibility and reduce vehicle operating cost | More resilient road network | Road | Construction of Karitiri coffee factory foot bridge |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1501248 | 1501248 | 1501248 | County treasury | N/A | 1501248 | N/A | 1501248 | 100% | 1501248 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Buying/Improvement of Kianjokoma-Gitongoro-Kiegucu-Ikunguru-Gichugu Road | Purchase, widening, gravelling and grading | To formalize road ownership, enhance accessibility and upgrade the road infrastructure | improved road infrastructure | Road | Buying/Improvement of Kianjokoma-Gitongoro-Kiegucu-Ikunguru-Gichugu Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Getua-Kivue road-Muminji | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Getua-Kivue road-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4012521 | 4012521 | 4012521 | County treasury | N/A | 4012521 | N/A | 4012521 | 100% | 4012521 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kavuguri Road | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kavuguri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Heavy Grading of Mbarwari Kupuri Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Heavy Grading of Mbarwari Kupuri Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading of Mubuthu-Mariari Road-Kiambere | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Grading of Mubuthu-Mariari Road-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Mukameri-Gwakarigu Road-Kiambere | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Mukameri-Gwakarigu Road-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Ntharawe-Kathiga Kanyonga Road-Kiambere | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Ntharawe-Kathiga Kanyonga Road-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Spot Murraming of Ikomenie-Kiriariri Road-Kiambere | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Grading and Spot Murraming of Ikomenie-Kiriariri Road-Kiambere |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Polytechnic-Bethany-ACK Road-Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Polytechnic-Bethany-ACK Road-Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3600000 | 3600000 | 3600000 | County treasury | N/A | 3600000 | N/A | 3600000 | 100% | 3600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Kairimu- Hague-Mudo Kamanja Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Kairimu- Hague-Mudo Kamanja Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of St. Christopher-Mwalimu Dennis Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of St. Christopher-Mwalimu Dennis Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2400000 | 2400000 | 2400000 | County treasury | N/A | 2400000 | N/A | 2400000 | 100% | 2400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Kathegiri to Runganga Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Kathegiri to Runganga Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Gichindano-Njuguna Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Gichindano-Njuguna Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2200000 | 2200000 | 2200000 | County treasury | N/A | 2200000 | N/A | 2200000 | 100% | 2200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Karega-Gitungu to Mirundi Water Spring Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Karega-Gitungu to Mirundi Water Spring Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Kiambigo B Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Kiambigo B Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Grading of Ndumari-Slaughter to Kianjiru Road- Gaturi South | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Grading of Ndumari-Slaughter to Kianjiru Road- Gaturi South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Kivue-Gwagukenga Road-Muminji | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Kivue-Gwagukenga Road-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1800000 | 1800000 | 1800000 | County treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Micegethiu-Irathaniro Road-Muminji | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Micegethiu-Irathaniro Road-Muminji |  |  |  | Road | Road |  | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Karambari-Kiang’anja Road-Muminji | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Karambari-Kiang’anja Road-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1895000 | 1895000 | 1895000 | County treasury | N/A | 1895000 | N/A | 1895000 | 100% | 1895000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Replacement of Culverts at Gatakari Kivue Road-Muminji | Excavation, removal of the broken culvert and replacement | To provide easy crossing over for vehicles and pedestrinas | Strong and longlasting culvert installed | Road | Replacement of Culverts at Gatakari Kivue Road-Muminji |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Karuku Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Karuku Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Kamweli Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Kamweli Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Muranga Ndogo Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Muranga Ndogo Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Kasioni Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Kasioni Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Kaseveni Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Kaseveni Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming/Grading/Grader Hiring of Maali Road-Mwea | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming/Grading/Grader Hiring of Maali Road-Mwea |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Makima-Katharane Road-Makima | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Makima-Katharane Road-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Mbondoni Spillway Road-Makima | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Mbondoni Spillway Road-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Makima-Mwanzo Road-Makima | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Makima-Mwanzo Road-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Manzo-Kitoloni-Junction Road-Makima | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Manzo-Kitoloni-Junction Road-Makima |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Rukira-Kune Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Rukira-Kune Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Gatitu Kwa DC-Kaageri Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Gatitu Kwa DC-Kaageri Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Gwasarava-Witwa Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Gwasarava-Witwa Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Kambora-Muthano-Kianamu Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Kambora-Muthano-Kianamu Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Kivuru-Munyuri Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Kivuru-Munyuri Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Nginduri Road-Nthawa | Resurfacing, cleaning, grass cutting and debris clearing | To prevent further deterioration of road assets though timely interventions | Reduced road maintenance costs in the community | Road | Completion of Nginduri Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Kwereri-Mumburi Road-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Kwereri-Mumburi Road-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading/Opening of Kwa Meru-Kaungu-Nthawa | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading/Opening of Kwa Meru-Kaungu-Nthawa |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening,Grading and Murraming of Roads-Runyenjes Central | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Opening,Grading and Murraming of Roads-Runyenjes Central |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 20000000 | 20000000 | 20000000 | County treasury | N/A | 20000000 | N/A | 20000000 | 100% | 20000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Nyagari-Kinthithe Road-Kyeni South | Final earthworks, gravelling and drainage construction | To bring the road to a fully functional and servicable standard | Well build and complete road | Road | Completion of Nyagari-Kinthithe Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Kinthithe-Gichonge Road-Kyeni South | Final earthworks, gravelling and drainage construction | To bring the road to a fully functional and servicable standard | Well build and complete road | Road | Completion of Kinthithe-Gichonge Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 |  | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Kwa Mbugua-Kiamboa Road-Kyeni South | Final earthworks, gravelling and drainage construction | To bring the road to a fully functional and servicable standard | Well build and complete road | Road | Completion of Kwa Mbugua-Kiamboa Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Completion of Karurumo-Kaveti Road-Kyeni South | Final earthworks, gravelling and drainage construction | To bring the road to a fully functional and servicable standard | Well build and complete road | Road | Completion of Karurumo-Kaveti Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Kigumo-Magea Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Kigumo-Magea Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Kigumo-Kiang’ombe Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Kigumo-Kiang’ombe Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Kigumo-Mikundu Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Kigumo-Mikundu Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Kamitaa Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Kamitaa Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Canon habat-Zuru-Kathunguri Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Canon habat-Zuru-Kathunguri Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 10% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Kamavindi-kagumori-Thau Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Kamavindi-kagumori-Thau Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Bush Clearing and Murraming of Rwarari-Gacungu Road-Kyeni South | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Bush Clearing and Murraming of Rwarari-Gacungu Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Gwacema-Kithiga Road-Nginda | Clearing, earthworks, levelling and compaction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Gwacema-Kithiga Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening of Kibugu-Mwithi Road-Nginda | Clearing, earthworks, levelling and compaction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening of Kibugu-Mwithi Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murramming of Gwacema-GitweTBC-Kiamutithi Road-Nginda | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murramming of Gwacema-GitweTBC-Kiamutithi Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing of Karau Pry.School-Kamanga’s-Gatugi’s Road-Nginda | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing of Karau Pry.School-Kamanga’s-Gatugi’s Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing of Thambana-kavari-Gacuriri-Kwa mburugua Road-Nginda | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing of Thambana-kavari-Gacuriri-Kwa mburugua Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing of Karau-Kithiga Kathuniri Road-Nginda | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing of Karau-Kithiga Kathuniri Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading,Murramimg,Bush Clearing,Installation of Culverts at Kanyuambora-Chief’s Camp-Gatanyiri-Kivengero-Muvakari Road to Tarmac-9 KMS-Evurore | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading,Murramimg,Bush Clearing,Installation of Culverts at Kanyuambora-Chief’s Camp-Gatanyiri-Kivengero-Muvakari Road to Tarmac-9 KMS-Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4500000 | 4500000 | 4500000 | County treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing,Culvert and Grading of Kindole-Kagaari Kangu to Tarmac-5KMS- Evurore | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing,Culvert and Grading of Kindole-Kagaari Kangu to Tarmac-5KMS- Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing,Culvert and Grading of Kagaari-Ciaikungungu to Kang’ote Road-5 KMS – Evurore | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing,Culvert and Grading of Kagaari-Ciaikungungu to Kang’ote Road-5 KMS – Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing,Culvert and Grading of Mbachi to Kianjoya Pry School Road-2 KMS - Evurore | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing,Culvert and Grading of Mbachi to Kianjoya Pry School Road-2 KMS - Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing and Grading of Kabubua Kanyama-Gatitu to Kiogogo Markets Road-5KMS – Evurore | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing and Grading of Kabubua Kanyama-Gatitu to Kiogogo Markets Road-5KMS – Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | v 1,500,000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Dozing and Grading of Kwa Munyao-Njue Gatumu to ESP Market Road-2KMS - Evurore | Clearing vegetation, excavation, Drift construction | To enhance road passability and improve drainage | Resilient road network | Road | Dozing and Grading of Kwa Munyao-Njue Gatumu to ESP Market Road-2KMS - Evurore |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1800000 | 1800000 | 1800000 | County treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Njoguri-Kanyakiri Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Njoguri-Kanyakiri Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Kithiruri-Kathangari Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Kithiruri-Kathangari Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Ndiuri-Gwakiuboro Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Ndiuri-Gwakiuboro Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Kiriari market-Kiriari day Sec. School Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Kiriari market-Kiriari day Sec. School Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Karuriri-Kiaraga Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Karuriri-Kiaraga Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Kithundiri-Miaturi Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Kithundiri-Miaturi Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murramming of Kamviu-Kiarurigi Road-Ruguru Ngandori | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murramming of Kamviu-Kiarurigi Road-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1800000 | 1800000 | 1800000 | County treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Full Gospel-Gumbuka Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Full Gospel-Gumbuka Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Rupingazi Inn-Werus Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Rupingazi Inn-Werus Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Mutunduri-Kariuki-Kianjokoma Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Mutunduri-Kariuki-Kianjokoma Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Gakwegori-Mortuary-Village Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Gakwegori-Mortuary-Village Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Matangiri-Kinandu-Itabua Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Matangiri-Kinandu-Itabua Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Miangari-Ndimbiri-Kivauri Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Miangari-Ndimbiri-Kivauri Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Gatunduri-Magosa Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Gatunduri-Magosa Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Karurina-Gichegori Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Karurina-Gichegori Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Kimangaru-Kimani Mahoya-Ngavari Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Kimangaru-Kimani Mahoya-Ngavari Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Gichegeri-Itabua Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Gichegeri-Itabua Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Don Bosco-Werus Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Don Bosco-Werus Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Mukunju-John Migate-Kapingazi Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Mukunju-John Migate-Kapingazi Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 500000 | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Njoka Turners-Njeru Munyi-Peter Rango-Kathuri Road-Mbeti North | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Njoka Turners-Njeru Munyi-Peter Rango-Kathuri Road-Mbeti North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Blue Valley,Dallas,Majengo, | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Murraming of Blue Valley,Dallas,Majengo, |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 6000000 | 6000000 | 6000000 | County treasury | N/A | 6000000 | N/A | 6000000 | 100% | 6000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Kangaru and Kathangari Feeder Roads-Kirimari | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Kangaru and Kathangari Feeder Roads-Kirimari |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 |  |  |  | County treasury | N/A | [9 empty] | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kithegi Dispensary-Kangone Road-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kithegi Dispensary-Kangone Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Giekawa Circuit Road-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Giekawa Circuit Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kavevo-Mivukori Road-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kavevo-Mivukori Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kanyangati-Full Gospel Road-Kyandundu Circuit-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kanyangati-Full Gospel Road-Kyandundu Circuit-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kau Village Circuit Road-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kau Village Circuit Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Opening and Grading of Kamunthatha-Gakui and Kamatanga-Gachutheri Road-Kithimu | Site survey, clearing and construction | To open new road corridors and improve existing ones for better conectivity | Newly opened and graded roads providing reliable access to communities | Road | Opening and Grading of Kamunthatha-Gakui and Kamatanga-Gachutheri Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Construction of Gakurungu-Riandu Footbridge Road-Kithimu | Site preparation, excavation and installation | To provide safe and reliable passage for the people around the area | Well constructed footbridge | Road | Construction of Gakurungu-Riandu Footbridge Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 1005 | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Kithegi Factory Circuit-Kithimu |  |  |  | Road | Grading and Murraming of Kithegi Factory Circuit-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Rukira-Gitakari-Kinyoro Road-Kithimu | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Rukira-Gitakari-Kinyoro Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Lower Nduva Access Road-Kithimu | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Lower Nduva Access Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Grading and Murraming of Kyandudu Pry Access Road-Kithimu | Clearing, earthworks, levelling and compaction | To provide a stable and well-drained road formation | A well graded road ready for use and construction | Road | Grading and Murraming of Kyandudu Pry Access Road-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Kiamatuto/Kiegucu/Ikunguru/Kathaka Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Kiamatuto/Kiegucu/Ikunguru/Kathaka Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Ruvuturi/Kiathetu/Kavari/Kiethetu Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Ruvuturi/Kiathetu/Kavari/Kiethetu Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Gatura/Kathangari/Kianjuki Catholic Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Gatura/Kathangari/Kianjuki Catholic Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Gacengi/Githunguthia/Kianyangi/Gaikiro Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Gacengi/Githunguthia/Kianyangi/Gaikiro Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 1005 | N/A | N/A | N/A | N/A | N/A
| Murraming of Muva/Karume/Muchagori-Mrkt/Full Kianjuki Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Muva/Karume/Muchagori-Mrkt/Full Kianjuki Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Kathiiri/Gituri/Kiandathi/Makutano Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Kathiiri/Gituri/Kiandathi/Makutano Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Mutira/Keruri/Kathanjuri/Gicege Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Mutira/Keruri/Kathanjuri/Gicege Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Nthamari/Nguire/Mutira/Gachichori Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Nthamari/Nguire/Mutira/Gachichori Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of St.Mark Karue/Ngai Ndethia/Nguire Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of St.Mark Karue/Ngai Ndethia/Nguire Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Kirurumwe/Mutaravo/Kasarani/Kirugumi Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Kirurumwe/Mutaravo/Kasarani/Kirugumi Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Zoore/ Karue/Kianjeru/Kaguchori Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Zoore/ Karue/Kianjeru/Kaguchori Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1100000 | 1100000 | 1100000 | County treasury | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Jumbiri/Kiamugu/Kevote Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Jumbiri/Kiamugu/Kevote Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming of Kamugere/Kamisa/Mukinyo/Kiandari opening Rd-Gaturi North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming of Kamugere/Kamisa/Mukinyo/Kiandari opening Rd-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Gichuki Valley Canteen Rd-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Gichuki Valley Canteen Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Kairangu Sacco Rd and 1 Culvert-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Kairangu Sacco Rd and 1 Culvert-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Gitakari-Thingingi Rd -Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Gitakari-Thingingi Rd -Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Mugui-Gichuki Rd-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Mugui-Gichuki Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Mururiri/Gogo Rd-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Mururiri/Gogo Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Ndamunge Iriari Director Rd-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Ndamunge Iriari Director Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Gravelling of Rwarari Valley a half Km Rd-Kagaari North | Site preparation, gravelling, grading | To improve road accessibility and reduce travel time | A well-graded and gvavelled road section of in good condition | Road | Gravelling of Rwarari Valley a half Km Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Murraming and Manual Reshaping of Ithuro-Kasarani Rd-Kagaari North | Site identification, supply, watering, shaping and murraming | To improve road accessibility and reduce vehicle operating cost | A well graded road ready for use and construction | Road | Murraming and Manual Reshaping of Ithuro-Kasarani Rd-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Flood Control Drainage-Kirimari | Construction and rehabilitation of storm water drainae channels | To mitigate the adverse impacts of flooding | well controlled drainage water | Road | Flood Control Drainage-Kirimari |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Machine hiring,Dozzer-Kirimari | Construction and rehabilitation of storm water drainae channels | To mitigate the adverse impacts of flooding | well controlled drainage water | Road | Machine hiring,Dozzer-Kirimari |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation /Purchase of Culverts-Kirimari | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation /Purchase of Culverts-Kirimari |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts-Ruguru Ngandori | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts-Ruguru Ngandori |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts-Kagaari North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 76000 | 76000 | 76000 | County treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts at Kyandundu Pry-Mbeti Boundary,Kwa Tugenge Swamp and Kamuthatha Stream-Kithimu | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts at Kyandundu Pry-Mbeti Boundary,Kwa Tugenge Swamp and Kamuthatha Stream-Kithimu |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Culverts-Kyeni South | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Culverts-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Road Maintenance/Culverts-Kyeni North | Resurfacing, cleaning, grass cutting and debris clearing |  | Reduced road maintenance costs in the community | Road | Road Maintenance/Culverts-Kyeni North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 2995629 | 2995629 | 2995629 | County treasury | N/A | 2995629 | N/A | 2995629 | 100% | 2995629 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of Culverts at Kaguchori/Zoori and Kianjeru 900mm -Gaturi North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of Culverts at Kaguchori/Zoori and Kianjeru 900mm -Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Culvert 600mm at Muva,Karue,Kiandathi,Keruri,Kirurumwe, Kathiakari,Kianjeru,Gicagi,Makengi Town/, Kiandathi Catholic-Gaturi North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Culvert 600mm at Muva,Karue,Kiandathi,Keruri,Kirurumwe, Kathiakari,Kianjeru,Gicagi,Makengi Town/, Kiandathi Catholic-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Installation of 900mm Culvert at Ikunguru/Kavari/And Gituri Kirurari/Kirugumi, And Gituri , Gitongoro-Gaturi North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Installation of 900mm Culvert at Ikunguru/Kavari/And Gituri Kirurari/Kirugumi, And Gituri , Gitongoro-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Hire of Machinery-NYS-Mavuria |  |  |  | Road | Hire of Machinery-NYS-Mavuria |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 10000000 | 10000000 | 10000000 | County treasury | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Purchase of culverts for road improvement-Gaturi North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Purchase of culverts for road improvement-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 200000 | 200000 | 200000 | County treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Improve Gichugu Road-Gaturi North | Site survey, excavation, installation and construction | To improve storm water drainage and ensure uninterrupted road access | Durable and erosion free roads | Road | Improve Gichugu Road-Gaturi North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Extention of Iriari Rural Electrification. | Survey, design, installation and transformers and conductors | To enhance access to electricity, improve living standards and support economic activities | Reduced reliance on non-renewable energy sources | Road | Extention of Iriari Rural Electrification. |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Electrification Project NTHAWA | Survey, design, installation and transformers and conductors | To enhance access to electricity, improve living standards and support economic activities | Reduced reliance on non-renewable energy sources | Road | Electrification Project NTHAWA |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Rehabilitation of Civil works-SUB TOTALS | Repair, reshaping and reconstruction | To restore the integrity if the works | Rehabilitated works | Road | Rehabilitation of Civil works-SUB TOTALS |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Research, Feasibility Studies, Project Preparation and Design, Project Supervision-SUB TOTALS | Collection, analysis, site survey | To support the successful implementation of infrastructure and development | Reliable evidence based information | Road | Research, Feasibility Studies, Project Preparation and Design, Project Supervision-SUB TOTALS |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Purchase of a man lift machine to maintain floodlights and streetlights | Procurement, delivery and quality verification | To facilitate easy operation on the power posts | High quality man lift machine secured | Road | Purchase of a man lift machine to maintain floodlights and streetlights |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 8000000 | 8000000 | 8000000 | County treasury | N/A | 8000000 | N/A | 8000000 | 100% | 8000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land for Gwacema-Kithiga Road-Nginda | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land for Gwacema-Kithiga Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land for Kibugu-Mwithi Road-Nginda | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land for Kibugu-Mwithi Road-Nginda |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land for close cut to Kirimiri Forest-Kagaari North | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land for close cut to Kirimiri Forest-Kagaari North |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of land at Kaveti Primary Link Road-Kyeni South | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of land at Kaveti Primary Link Road-Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 1100000 | 1100000 | 1100000 | County treasury | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of land at Kandete linking loop - Kyeni South | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of land at Kandete linking loop - Kyeni South |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land Parcel Mbeti /Gachoka/2125 | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land Parcel Mbeti /Gachoka/2125 |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 4400000 | 4400000 | 4400000 | County treasury | N/A | 4400000 | N/A | 4400000 | 100% | 4400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land Parcel Mbeti /Gachoka/749 | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land Parcel Mbeti /Gachoka/749 |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 9900000 | 9900000 | 9900000 | County treasury | N/A | 9900000 | N/A | 9900000 | 100% | 9900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
| Acquisition of Land for Kagumori-Rupingazi Access Road | Identification, valuation and acquisition | To secure adequate land for the construction and operation of facilities like roads and hospitals | Secured land | Road | Acquisition of Land for Kagumori-Rupingazi Access Road |  |  |  | Road | Road | Road | 2026-01-07 | 2017-01-01 | 30/6/2017 | 30/6/2017 | 5500000 | 5500000 | 5500000 | County treasury | N/A | 5500000 | N/A | 5500000 | 100% | 5500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2015/2016
1 | Conditional Allocation From Road Maintenance Fuel Levy Fund(Maintenance Of County Roads)-(Ishiara-Kirii-Mutuobare road,Kathanjuri-Kegonge-Kathunguri road,Kairo-Gacavari-Kanyuambora rd,Kamugere-Kirimiri-Nduuri road among others) | maintenance of county roads | to keep roads in good and passable conditions | maintained and passable roads | Development | Conditional Allocation From Road Maintenance Fuel Levy Fund(Maintenance Of County Roads)-(Ishiara-Kirii-Mutuobare road,Kathanjuri-Kegonge-Kathunguri road,Kairo-Gacavari-Kanyuambora rd,Kamugere-Kirimiri-Nduuri road among others) | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 |  |  |  | 48754599 | 48754599 | 48754599 | County treasury | N/A | 48754599 | N/A | 48754599 | 100% | 48754599 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2 | Refurbishment of Buildings | refurbishment of buildings | to improve building condition and usability | refurbished and functional buildings | Development | Refurbishment of Buildings | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 9419273 | 9419273 | 9419273 | County treasury | N/A | 9419273 | N/A | 9419273 | 100% | 9419273 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Rehabilitation of residential houses | rehabilitation of residential houses | to improve living conditions and structural safety | rehabilitated and habitable houses | Development | Rehabilitation of residential houses | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1282500 | 1282500 | 1282500 | County treasury | N/A | 1282500 | N/A | 1282500 | 100% | 1282500 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Fencing of Town Hall- Renovation and Extension (Phase 2) | fencing, renovation and extension of town hall | to improve security space and usability of the facility | a fenced renovated and extended town hall | Development | Fencing of Town Hall- Renovation and Extension (Phase 2) | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 7376773 | 7376773 | 7376773 | County treasury | N/A | 7376773 | N/A | 7376773 | 100% | 7376773 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Renovation of Majimbo fire station | renovation of a fire station | to improve the conditions and functionality of the fire station | a renovated and fully functional fire station | Development | Renovation of Majimbo fire station | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Tarmacking Of Dallas Road- Phase II | tarmacking of existing roads for vehicles and pedestrians | to improve road accessibility and enhance safe and efficient transportation | tarmac roads completed with proper drainage | Development | Tarmacking Of Dallas Road- Phase II | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 60000000 | 60000000 | 60000000 | County treasury | N/A | 60000000 | N/A | 60000000 | 100% | 60000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Tarmacking Of Roads In Runyenjes Town-Phase II | tarmacking of existing roads for vehicles and pedestrians | to improve road accessibility and enhance safe and efficient transportation | tarmac roads completed with proper drainage | Development | Tarmacking Of Roads In Runyenjes Town-Phase II | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 22000000 | 22000000 | 22000000 | County treasury | N/A | 22000000 | N/A | 22000000 | 100% | 22000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Dallas Road Phase II | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Dallas Road Phase II | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 20875799 | 20875799 | 20875799 | County treasury | N/A | 20875799 | N/A | 20875799 | 100% | 20875799 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Tarmacking of roads in Runyenjes-Phase II | tarmacking of existing roads for vehicles and pedestrians | to improve road accessibility and enhance safe and efficient transportation | tarmac roads completed with proper drainage | Development | Tarmacking of roads in Runyenjes-Phase II | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 15200000 | 15200000 | 15200000 | County treasury | N/A | 15200000 | N/A | 15200000 | 100% | 15200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Roads and culverts-Gatunduri Sub location | construction of roads and calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Gatunduri Sub location | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2432000 | 2432000 | 2432000 | County treasury | N/A | 2432000 | N/A | 2432000 | 100% | 2432000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Opening of Micegethiu-Nguthi road | opening of the new access road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Micegethiu-Nguthi road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2280000 | 2280000 | 2280000 | County treasury | N/A | 2280000 | N/A | 2280000 | 100% | 2280000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Mbeti South Access Roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Mbeti South Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Mbeti North Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Mbeti North Access roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 4940000 | 4940000 | 4940000 | County treasury | N/A | 4940000 | N/A | 4940000 | 100% | 4940000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Kagaari South Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kagaari South Access roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1900000 | 1900000 | 1900000 | County treasury | N/A | 1900000 | N/A | 1900000 | 100% | 1900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
15 | Kangaara-Kangondi Access road | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kangaara-Kangondi Access road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1626000 | 1626000 | 1626000 | County treasury | N/A | 1626000 | N/A | 1626000 | 100% | 1626000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
16 | Nduva-Gicegeri Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Nduva-Gicegeri Access roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 752000 | 752000 | 752000 | County treasury | N/A | 752000 | N/A | 752000 | 100% | 752000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Kyethiga-Ithangawe Access road | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kyethiga-Ithangawe Access road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 600000 | 600000 | 600000 | County treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | John Matanjuki-Kangaara Access Road | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | John Matanjuki-Kangaara Access Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 600000 | 600000 | 600000 | County treasury | N/A | 600000 | N/A | 600000 |  | 600000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
19 | Kiambere Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kiambere Access roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
20 | Rianjeru road-Mbeti South | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Rianjeru road-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1520000 | 1520000 | 1520000 | County treasury | N/A | 1520000 | N/A | 1520000 | 100% | 1520000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Kwa Gakunju-Kabuguri-Ngaria | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kwa Gakunju-Kabuguri-Ngaria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 834496 | 834496 | 834496 | County treasury | N/A | 834496 | N/A | 834496 | 100% | 834496 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
22 | Kang’ethia-Kiandome | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kang’ethia-Kiandome | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 521360 | 521360 | 521360 | County treasury | N/A | 521360 | N/A | 521360 | 100% | 521360 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Ibutuka-Intake Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ibutuka-Intake Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Kiathara-Shauri Soweto Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiathara-Shauri Soweto Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Kanja Market Access Roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kanja Market Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Karurua-Rutumba-Kiambere-Mutuobare Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Karurua-Rutumba-Kiambere-Mutuobare Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1330760 | 1330760 | 1330760 | County treasury | N/A | 1330760 | N/A | 1330760 | 100% | 1330760 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Newsite-Kasafari-Isacco Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Newsite-Kasafari-Isacco Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1601320 | 1601320 | 1601320 | County treasury | N/A | 1601320 | N/A | 1601320 | 100% | 1601320 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Mboce Drift-Tharawa Kathigari | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mboce Drift-Tharawa Kathigari | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2998781 | 2998781 | 2998781 | County treasury | N/A | 2998781 | N/A | 2998781 | 100% | 2998781 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
29 | Junction Kitoloni-Mukuria-Mwanzo-Mbondoni Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Junction Kitoloni-Mukuria-Mwanzo-Mbondoni Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1971979 | 1971979 | 1971979 | County treasury | N/A | 1971979 | N/A | 1971979 | 100% | 1971979 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Kirithiga Foot Bridge Across Thura River | construction of a foot bridge across a river | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Kirithiga Foot Bridge Across Thura River | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2502465 | 2502465 | 2502465 | County treasury | N/A | 2502465 | N/A | 2502465 | 100% | 2502465 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Thau-Kanjatari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Thau-Kanjatari Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2412884 | 2412884 | 2412884 | County treasury | N/A | 2412884 | N/A | 2412884 | 100% | 2412884 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
32 | Kimangaru-Ithira Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kimangaru-Ithira Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 83927 | 83927 | 83927 | County treasury | N/A | 83927 | N/A | 83927 | 100% | 83927 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Uvarire-Ngunyumu-Gachoriri-Kamumu | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Uvarire-Ngunyumu-Gachoriri-Kamumu | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1247825 | 1247825 | 1247825 | County treasury | N/A | 1247825 | N/A | 1247825 | 100% | 1247825 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
34 | Gitare-Catholic-Kwa Abel | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gitare-Catholic-Kwa Abel | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2571840 | 2571840 | 2571840 | County treasury | N/A | 2571840 | N/A | 2571840 | 100% | 2571840 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
35 | Kiang’ombe Road-Zakayo-Ngarari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiang’ombe Road-Zakayo-Ngarari Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1937702 | 1937702 | 1937702 | County treasury | N/A | 1937702 | N/A | 1937702 | 100% | 1937702 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
36 | Ngurueri Factory Road/Bridge | construction of a bridgeand the road | to improve safety and usability of the bridge, improve accessibility | a complete and functional bridge and road | Development | Ngurueri Factory Road/Bridge | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
37 | Gategi-Ngandi road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gategi-Ngandi road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1074714 | 1074714 | 1074714 | County treasury | N/A | 1074714 | N/A | 1074714 | 100% | 1074714 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
38 | Construction of Gakungugu-Ngunga footbridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Gakungugu-Ngunga footbridge | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1900000 | 1900000 | 1900000 | County treasury | N/A | 1900000 | N/A | 1900000 | 100% | 1900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
39 | Construction of Nduuri-Gikuuri footbridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Nduuri-Gikuuri footbridge | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 228000 | 228000 | 228000 | County treasury | N/A | 228000 | N/A | 228000 | 100% | 228000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
40 | Masiara-Mucuwe bridge | construction of a bridge | to improve safety and usability of the bridge | a complete and functional bridge | Development | Masiara-Mucuwe bridge | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
41 | Construction of Muminji/Gikondi Drift | construction of a drift crossing | to provide a safe crossing over seasonal water channels | a completed and functional drift crossing | Development | Construction of Muminji/Gikondi Drift | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 3268000 | 3268000 | 3268000 | County treasury | N/A | 3268000 | N/A | 3268000 | 100% | 3268000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
42 | Construction of Ntharawe/Thura Drift | construction of a drift crossing | to provide a safe crossing over seasonal water channels | a completed and functional drift crossing | Development | Construction of Ntharawe/Thura Drift | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
43 | Construction of Kamumu Stream drift | construction of a drift crossing | to provide a safe crossing over seasonal water channels | a completed and functional drift crossing | Development | Construction of Kamumu Stream drift | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
44 | Construction of Marivwe/Ngunyumu drift | construction of a drift crossing | to provide a safe crossing over seasonal water channels | a completed and functional drift crossing | Development | Construction of Marivwe/Ngunyumu drift | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
45 | Thau Bridge-Kagaari South | construction of a bridge | to improve safety and usability of the bridge | a complete and functional bridge | Development | Thau Bridge-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 4500000 | 4500000 | 4500000 | County treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
46 | Street lighting installation | installation of street lights | enhance security and efficiency | street light installed | Development | Street lighting installation | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 14250000 | 14250000 | 14250000 | County treasury | N/A | 14250000 | N/A | 14250000 | 100% | 14250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
47 | Installation of High mast flood lights-Siakago | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights-Siakago | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
48 | Installation of High mast flood lights at Kamiu ACK church | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Kamiu ACK church | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
49 | Installation of High mast flood lights at GTI-Iveche junction | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at GTI-Iveche junction | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
50 | Installation of High mast flood lights at Kambo market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Kambo market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
51 | Installation of High mast flood lights at Gakwegori junction | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Gakwegori junction | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
52 | Transformer Project-Kiaguchu,Gaikiro,Muva, Gitumbi-Gaturi North | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project-Kiaguchu,Gaikiro,Muva, Gitumbi-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 4892000 | 4892000 | 4892000 | County treasury | N/A | 4892000 | N/A | 4892000 | 100% | 4892000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
53 | Installation of High mast flood lights at Muchagori/Makengi | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Muchagori/Makengi | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
54 | Installation of High mast flood lights at Rukira and Ndatu Markets | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Rukira and Ndatu Markets | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 |  | 1000000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
55 | Transformers – Kagaari South | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformers – Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 7800000 | 7800000 | 7800000 | County treasury | N/A | 7800000 | N/A | 7800000 | 100% | 7800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
56 | Transformer project-Gitumbiri-Mavuria | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer project-Gitumbiri-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
57 | Transformer booster-Kambaru-Mavuria | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Transformer booster-Kambaru-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
58 | Transformer booster-Kitharu-Mavuria | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Transformer booster-Kitharu-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
59 | Transformer booster-Cavari-Mavuria | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Transformer booster-Cavari-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
60 | Transformer booster-Kagongo-Mavuria | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Transformer booster-Kagongo-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
61 | Transformer project-Kwa Andu Anjiru-Mavuria | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer project-Kwa Andu Anjiru-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
62 | Installation of Culverts( Karurina,Kangurungu and Gatondo-Mukuuri Swamp) | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Installation of Culverts( Karurina,Kangurungu and Gatondo-Mukuuri Swamp) | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 228000 | 228000 | 228000 | County treasury | N/A | 228000 | N/A | 228000 | 100% | 228000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
63 | Installation of High Flood Lights-Kathunguri Market | Installation of High Flood Lights-Kawanjara Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Kathunguri Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
64 | Installation of High mast Flood Light at Mutunduri Market | Installation of High Flood Lights-Kathunguri Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Mutunduri Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
65 | Installation of High mast Flood Light at Sunrise Market | Installation of High mast Flood Light at Mutunduri Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Sunrise Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
66 | Installation of High mast Flood Light at Gerish Market | Installation of High mast Flood Light at Sunrise Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Gerish Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
67 | Installation of High mast Flood Light at Karurina Market | Installation of High mast Flood Light at Gerish Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Karurina Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
68 | Installation of High mast Flood Light at Slaughter Majimbo Market | Installation of High mast Flood Light at Karurina Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Slaughter Majimbo Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
69 | Installation of High mast Flood Light at Kimangaru Market | Installation of High mast Flood Light at Slaughter Majimbo Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kimangaru Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
70 | Installation of High mast Flood Light at Gatunduri Market | Installation of High mast Flood Light at Kimangaru Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Gatunduri Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 369955 | 369955 | 369955 | County treasury | N/A | 369955 | N/A | 369955 | 100% | 369955 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
71 | Installation of High mast Flood Light at Ngariama market | Installation of High mast Flood Light at Gatunduri Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Ngariama market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
72 | Installation of High mast Flood Light at Majengo Market | Installation of High mast Flood Light at Ngariama market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Majengo Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
73 | Installation of High mast Flood Light at Kathangari Market | Installation of High mast Flood Light at Majengo Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kathangari Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
74 | Installation of High mast Flood Light at Kangaru Market | Installation of High mast Flood Light at Kathangari Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kangaru Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
75 | Installation of High mast Flood Light at Irangi Market | Installation of High mast Flood Light at Kangaru Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Irangi Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
76 | Installation of High mast Flood Light at Kivue Market | Installation of High mast Flood Light at Irangi Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kivue Market | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
77 | Installation of High Flood Lights-Other markets | Installation of High mast Flood Light at Kivue Market | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Other markets | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2725466 | 2725466 | 2725466 | County treasury | N/A | 2725466 | N/A | 2725466 | 100% | 2725466 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
78 | Installation of High Flood Lights-Kamugere/Itonguri | Installation of High Flood Lights-Other markets | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Kamugere/Itonguri | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
79 | Installation of Transformer Boost-Gichegori | Installation of High Flood Lights-Kamugere/Itonguri | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of Transformer Boost-Gichegori | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 228000 | 228000 | 228000 | County treasury | N/A | 228000 | N/A | 228000 | 100% | 228000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
80 | Installation of Transformer at Kaugi market/Dispensary | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Installation of Transformer at Kaugi market/Dispensary | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
81 | Installation of Transformer at Kwa Mithamo | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Installation of Transformer at Kwa Mithamo | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
82 | Rehabilitation of County Roads | improvement and upgrading of county roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of County Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 6019388 | 6019388 | 6019388 | County treasury | N/A | 6019388 | N/A | 6019388 |  | 6019388 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
83 | Rehabilitation of Access Roads-Ruguru Ngandori | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Access Roads-Ruguru Ngandori | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 6563740 | 6563740 | 6563740 | County treasury | N/A | 6563740 | N/A | 6563740 | 100% | 6563740 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
84 | Manual road reshaping and machine Contracting-Gaturi North | manual reshaping of roads to improve surface and drainage | to Improve road passability and drainage | reshaped and passable roads | Development | Manual road reshaping and machine Contracting-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
85 | Murraming of Roads of 25 Km -Gaturi North | murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | murramed and passable | Development | Murraming of Roads of 25 Km -Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2280000 | 2280000 | 2280000 | County treasury | N/A | 2280000 | N/A | 2280000 | 100% | 2280000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
86 | Construction of Karitiri coffee factory foot bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Karitiri coffee factory foot bridge | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
87 | Buying/Improvement of Kianjokoma-Gitongoro-Kiegucu-Ikunguru-Gichugu Road | improvement of existing road | to enhance road condition and accessibility | improved and functional road | Development | Buying/Improvement of Kianjokoma-Gitongoro-Kiegucu-Ikunguru-Gichugu Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
88 | Rehabilitation of Access Roads-Runyenjes Central | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Access Roads-Runyenjes Central | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 4940000 | 4940000 | 4940000 | County treasury | N/A | 4940000 | N/A | 4940000 | 100% | 4940000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
89 | Grading and murraming 2KM road-Ishiara Karangare to Kathi | grading and murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and murramed passable roads | Development | Grading and murraming 2KM road-Ishiara Karangare to Kathi | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
90 | Itharari to Cianria access road | construction and upgrading of access roads | to improve road accessibility and traffic movement | a functional access road | Development | Itharari to Cianria access road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
91 | Road Maintenance-Ciamainga and Ciakirururi drifts | maintenance of roads | to keep roads in good and passable conditions | maintained and passable roads | Development | Road Maintenance-Ciamainga and Ciakirururi drifts | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1425000 | 1425000 | 1425000 | County treasury | N/A | 1425000 | N/A | 1425000 | 100% | 1425000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
92 | Grading Gwakaithi catholic-Kamama to Kanyangi road | grading of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and passable roads | Development | Grading Gwakaithi catholic-Kamama to Kanyangi road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
93 | Improvement of Kibugu-Kathiria-Kiori-Nthunguri-Kang’ethia | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kibugu-Kathiria-Kiori-Nthunguri-Kang’ethia | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
94 | Improvement of Magurumari-Nguthi-EWASCO intake-Kiandari Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Magurumari-Nguthi-EWASCO intake-Kiandari Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 456000 | 456000 | 456000 | County treasury | N/A | 456000 | N/A | 456000 | 100% | 456000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
95 | Improvement of Kathuniri-Karumathi-Iriari-Karimari Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kathuniri-Karumathi-Iriari-Karimari Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 532000 | 532000 | 532000 | County treasury | N/A | 532000 | N/A | 532000 | 100% | 532000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
96 | Improvement of Mwara-Magoci-Njagi Kathunguri-Njagi Mwendano-Gatiiguru Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Mwara-Magoci-Njagi Kathunguri-Njagi Mwendano-Gatiiguru Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 608000 | 608000 | 608000 | County treasury | N/A | 608000 | N/A | 608000 | 100% | 608000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
97 | Opening and rehabilitation of rural Access Roads-Nthawa | opening and improvement of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Opening and rehabilitation of rural Access Roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 5320000 | 5320000 | 5320000 | County treasury | N/A | 5320000 | N/A | 5320000 | 100% | 5320000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
98 | Improvement of Kagaari North Access Roads | improvement of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kagaari North Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 6688000 | 6688000 | 6688000 | County treasury | N/A | 6688000 | N/A | 6688000 | 100% | 6688000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
99 | Improvement of Ndutori-Manjiatiri Road | improvement of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Ndutori-Manjiatiri Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1292000 | 1292000 | 1292000 | County treasury | N/A | 1292000 | N/A | 1292000 | 100% | 1292000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
100 | Opening of Makaru Road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Makaru Road-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
101 | Opening of Bodeni-Ndiuri-Kaviu Road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Bodeni-Ndiuri-Kaviu Road-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1368000 | 1368000 | 1368000 | County treasury | N/A | 1368000 | N/A | 1368000 | 100% | 1368000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
102 | Opening of Getua-Kivue road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Getua-Kivue road-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1520000 | 1520000 | 1520000 | County treasury | N/A | 1520000 | N/A | 1520000 | 100% | 1520000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
103 | Opening and Grading of Nguthi-Kandari Road | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening and Grading of Nguthi-Kandari Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1800000 | 1800000 | 1800000 | County treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
104 | Grading of Gicherori-Gacoya bridge-Kioruto Nthunguri-Kangethia-Kiiye river at kwa Mwai | grading of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and passable roads | Development | Grading of Gicherori-Gacoya bridge-Kioruto Nthunguri-Kangethia-Kiiye river at kwa Mwai | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 836000 | 836000 | 836000 | County treasury | N/A | 836000 | N/A | 836000 | 100% | 836000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
105 | Widening, gravelling and murraming of Ngenge-Kavagire/ Soko Mjinga Road | widening gravelling and murraming of a road | to improve road capacity and surface condition | a widened and improved all weather road | Development | Widening, gravelling and murraming of Ngenge-Kavagire/ Soko Mjinga Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1400000 | 1400000 | 1400000 | County treasury | N/A | 1400000 | N/A | 1400000 | 100% | 1400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
106 | Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road | widening gravelling and murraming of a road | to improve road capacity and surface condition | a widened and improved all weather road | Development | Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
107 | BAT Riandu-Mwondu-Kathitu-Riandu-Gikingiri road-Grading and spot Murramming | gravelling and murraming of a road | to improve road surface condition | improved all weather road | Development | BAT Riandu-Mwondu-Kathitu-Riandu-Gikingiri road-Grading and spot Murramming | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1140000 | 1140000 | 1140000 | County treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
108 | Rehabilitation of Kyeni North Access Roads | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Kyeni North Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1520000 | 1520000 | 1520000 | County treasury | N/A | 1520000 | N/A | 1520000 | 100% | 1520000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
109 | Murraming of Kyeni North Access Roads | murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | murramed and passable | Development | Murraming of Kyeni North Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
110 | Roads and culverts-Nembure Sub location | construction of roads and calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Nembure Sub location | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1900000 | 1900000 | 1900000 | County treasury | N/A | 1900000 | N/A | 1900000 | 100% | 1900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
111 | Roads and culverts-Ena Sub location | construction of roads and calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Ena Sub location | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2356000 | 2356000 | 2356000 | County treasury | N/A | 2356000 | N/A | 2356000 | 100% | 2356000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
112 | Installation of culverts for various access roads-Kithimu | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Installation of culverts for various access roads-Kithimu | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 600000 | 600000 | 600000 | County treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
113 | Kyeni South Access Roads | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kyeni South Access Roads | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 5320000 | 5320000 | 5320000 | County treasury | N/A | 5320000 | N/A | 5320000 | 100% | 5320000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
114 | Purchase of culverts- Kyeni North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts- Kyeni North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 190000 | 190000 | 190000 | County treasury | N/A | 190000 | N/A | 190000 | 100% | 190000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
115 | Culverts and general maintenance of roads-Nthawa | intallation of calverts and road maintenance | to improve drainage and prevent road damage and improve connectivity | calverts intalled and road maintained | Development | Culverts and general maintenance of roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 760000 | 760000 | 760000 | County treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
116 | Soko-Uvarire road Culvert | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Soko-Uvarire road Culvert | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
117 | Purchase of culverts- Kagaari North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts- Kagaari North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 76000 | 76000 | 76000 | County treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
118 | Purchase of culverts for road improvement-Gaturi North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts for road improvement-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 152000 | 152000 | 152000 | County treasury | N/A | 152000 | N/A | 152000 | 100% | 152000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
119 | Purchase of culverts for road improvement-Kyeni South | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts for road improvement-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 380000 | 380000 | 380000 | County treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
120 | Installation of culvert at Kandomba stream-Muminji | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Installation of culvert at Kandomba stream-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2204000 | 2204000 | 2204000 | County treasury | N/A | 2204000 | N/A | 2204000 | 100% | 2204000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
121 | Rehabilitation of Civil works | rehabilitation of civil works | to restore infrastructure to functional condition | rehabilitated and functional civil works | Development | Rehabilitation of Civil works | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 7524000 | 7524000 | 7524000 | County treasury | N/A | 7524000 | N/A | 7524000 | 100% | 7524000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
122 | Other Infrastructure and Civil Works | construction of other infrastructure and civil works | to enhance public infrastructure and service delivery | completed and functional infrastructure and civil works | Development | Other Infrastructure and Civil Works | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 7068000 | 7068000 | 7068000 | County treasury | N/A | 7068000 | N/A | 7068000 | 100% | 7068000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
123 | Electrification of Mbondoni Police | electrification of a police post | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Mbondoni Police | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 76000 | 76000 | 76000 | County treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
124 | Electrification of Mbondoni Dispensary | electrification of a dispensary | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Mbondoni Dispensary | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 76000 | 76000 | 76000 | County treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
125 | Electrification of Chief’s Office –Kitololoni | electrification of a chief's office | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Chief’s Office –Kitololoni | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 76000 | 76000 | 76000 | County treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
126 | Electrification of DO’s office –Makima | electrification of a DO's office | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of DO’s office –Makima | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 228000 | 228000 | 228000 | County treasury | N/A | 228000 | N/A | 228000 | 100% | 228000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
127 | Acquisition of land and opening of Kiriari-Kaguma-Karau Road | opening of a road and acquisition of land for public use | to secure land for development of public projects, to ensure efficient transport | land acquired and available for development, road opened | Development | Acquisition of land and opening of Kiriari-Kaguma-Karau Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
128 | Acquisition of land for Gicherori-Mwithi-Kibugu Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Gicherori-Mwithi-Kibugu Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
129 | Acquisition of land for Kwa Cema-Gichangai-Kithiga Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Kwa Cema-Gichangai-Kithiga Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
130 | Acquisition of land for Access roads-Nthawa | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Access roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
131 | Acquisition of land for close cut to Kirimiri forest | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for close cut to Kirimiri forest | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
132 | Acquisition of land at Kagumori | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kagumori | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
133 | Acquisition of land at Kaveti Primary Link Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kaveti Primary Link Road | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1100000 | 1100000 | 1100000 | County treasury | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
134 | Acquisition of land at Kandete linking loop | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kandete linking loop | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
135 | Purchase of Land for Thara Road(Kathuro farm) | purchase of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Purchase of Land for Thara Road(Kathuro farm) | N/A | N/A | N/A | Development | Development | Development | 1/O7/2015 | 2016-01-01 | 2016-06-01 | 2016-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2014/2015
1 | Renovation of Nembure Social Hall | renovation of the social hall | to improve the hall for community use | renovated and functional social hall | Development | Renovation of Nembure Social Hall | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1349851 | 1349851 | 1349851 | County treasury | N/A | 1349851 | N/A | 1349851 | 100% | 1349851 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2 | Fencing of Town Hall- Renovation and Extension (Phase 2) | renovation and extension of town hall | to improve security, space, and usability of the town hall | a fenced , renovated and extended town hall | Development | Fencing of Town Hall- Renovation and Extension (Phase 2) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 24886200 | 24886200 | 24886200 | County treasury | N/A | 24886200 | N/A | 24886200 | 100% | 24886200 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Renovation of Majimbo fire station | renovation of the fire station | to improve the condition and functionality of the fire station | a renovated and fully functional fire station | Development | Renovation of Majimbo fire station | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Dallas Road Phase II | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Dallas Road Phase II | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 50000000 | 50000000 | 50000000 | County treasury | N/A | 50000000 | N/A | 50000000 | 100% | 50000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Tarmacking of roads in Runyenjes-Phase II | tarmacking of existing roads for vehicles and pedestrians | to improve road accessibility and enhance safe and efficient transportation | tarmac roads completed with proper drainage | Development | Tarmacking of roads in Runyenjes-Phase II | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 20000000 | 20000000 | 20000000 | County treasury | N/A | 20000000 | N/A | 20000000 | 100% | 20000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Roads and culverts-Gatunduri Sub location | construction and improvement of roads together with installation of calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Gatunduri Sub location | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3200000 | 3200000 | 3200000 | County treasury | N/A | 3200000 | N/A | 3200000 | 100% | 3200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Opening of Micegethiu-Nguthi road | opening of the new access road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Micegethiu-Nguthi road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Mbeti South Access Roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Mbeti South Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Mbeti North Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Mbeti North Access roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 6500000 | 6500000 | 6500000 | County treasury | N/A | 6500000 | N/A | 6500000 | 100% | 6500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Nduva-Kangaara Access road | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Nduva-Kangaara Access road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Nduva-Gicegeri Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Nduva-Gicegeri Access roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Kiambere Access roads | construction and improvement of access roads | to improve accessibility and connectivity | functional and accessible roads | Development | Kiambere Access roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Rianjeru road-Mbeti South | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Rianjeru road-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Mutus Nyangwa-Gataka Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mutus Nyangwa-Gataka Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1720000 | 1720000 | 1720000 | County treasury | N/A | 1720000 | N/A | 1720000 | 100% | 1720000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
15 | Kwa Gakunju-Kabuguri-Ngaria | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kwa Gakunju-Kabuguri-Ngaria | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1098022 | 1098022 | 1098022 | County treasury | N/A | 1098022 | N/A | 1098022 | 100% | 1098022 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
16 | Mugo Nginyirua-Kwa Francis-Gakurumari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mugo Nginyirua-Kwa Francis-Gakurumari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1076879 | 1076879 | 1076879 | County treasury | N/A | 1076879 | N/A | 1076879 | 100% | 1076879 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Kiunii-Rutune-Gaatema Njagi Primary School Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiunii-Rutune-Gaatema Njagi Primary School Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 339915 | 339915 | 339915 | County treasury | N/A | 339915 | N/A | 339915 | 100% | 339915 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Kithe Social Catholic-Kamwaka Kwa Mrs Mbogo-Kwa Muriithi-Kwa Boss Junction Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kithe Social Catholic-Kamwaka Kwa Mrs Mbogo-Kwa Muriithi-Kwa Boss Junction Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1025012 | 1025012 | 1025012 | County treasury | N/A | 1025012 | N/A | 1025012 | 100% | 1025012 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Kang’ethia-Kiandome | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kang’ethia-Kiandome | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 686000 | 686000 | 686000 | County treasury | N/A | 686000 | N/A | 686000 |  | 686000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
20 | Market Infrastructure-Makutano | construction and improvement of market infrasstructure | to improve trading conditions and support local businesses | improved and functional market facilities | Development | Market Infrastructure-Makutano | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Ibutuka-Intake Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ibutuka-Intake Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
22 | Kathageri-Kathari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kathageri-Kathari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 600110 | 600110 | 600110 | County treasury | N/A | 600110 | N/A | 600110 | 100% | 600110 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Foot Bridge across Thuchi River | construction of a foot bridge across a river | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Foot Bridge across Thuchi River | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2159965 | 2159965 | 2159965 | County treasury | N/A | 2159965 | N/A | 2159965 | 100% | 2159965 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Rukuriri-Thumbiri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Rukuriri-Thumbiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 774652 | 774652 | 774652 | County treasury | N/A | 774652 | N/A | 774652 | 100% | 774652 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Mufu-Kathageri Old Bridge | renovation of an old bridge | to improve safety and usability of the bridge | a renovated and safe bridge | Development | Mufu-Kathageri Old Bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1017374 | 1017374 | 1017374 | County treasury | N/A | 1017374 | N/A | 1017374 | 100% | 1017374 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Mbui Njeru-Nicia Kithura-Naftari-Kiandongo Hospital Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mbui Njeru-Nicia Kithura-Naftari-Kiandongo Hospital Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1414903 | 1414903 | 1414903 | County treasury | N/A | 1414903 | N/A | 1414903 | 100% | 1414903 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Nduuri Market-Ricunjagi-Thaa Nduri-Ndamunge-Gakire Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Nduuri Market-Ricunjagi-Thaa Nduri-Ndamunge-Gakire Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1541068 | 1541068 | 1541068 | County treasury | N/A | 1541068 | N/A | 1541068 | 100% | 1541068 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Nderi Magigito-Mbogori-Muthenge Ina Factory Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Nderi Magigito-Mbogori-Muthenge Ina Factory Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 781956 | 781956 | 781956 | County treasury | N/A | 781956 | N/A | 781956 | 100% | 781956 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
29 | Mukuuri-Kianjokoma Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mukuuri-Kianjokoma Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3100000 | 3100000 | 3100000 | County treasury | N/A | 3100000 | N/A | 3100000 | 100% | 3100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Kiathara-Shauri Soweto Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiathara-Shauri Soweto Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Kanja Market Access Roads | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kanja Market Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
32 | Karurua-Rutumba-Kiambere-Mutuobare Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Karurua-Rutumba-Kiambere-Mutuobare Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1751000 | 1751000 | 1751000 | County treasury | N/A | 1751000 | N/A | 1751000 | 100% | 1751000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Newsite-Kasafari-Isacco Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Newsite-Kasafari-Isacco Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2107000 | 2107000 | 2107000 | County treasury | N/A | 2107000 | N/A | 2107000 | 100% | 2107000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
34 | Mboce Drift-Tharawa Kathigari | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mboce Drift-Tharawa Kathigari | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3945765 | 3945765 | 3945765 | County treasury | N/A | 3945765 | N/A | 3945765 | 100% | 3945765 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
35 | Gaitutu-Gachavari-Kibois Mucali Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gaitutu-Gachavari-Kibois Mucali Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2568182 | 2568182 | 2568182 | County treasury | N/A | 2568182 | N/A | 2568182 | 100% | 2568182 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
36 | Kiboi’s-Murari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiboi’s-Murari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
37 | Gacagori Kwa Mbugua-Kithunguri-Karurumo Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gacagori Kwa Mbugua-Kithunguri-Karurumo Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2639984 | 2639984 | 2639984 | County treasury | N/A | 2639984 | N/A | 2639984 | 100% | 2639984 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
38 | Kagumori-Nyanjara-Kambevo-Kirimari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kagumori-Nyanjara-Kambevo-Kirimari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 855569 | 855569 | 855569 | County treasury | N/A | 855569 | N/A | 855569 | 100% | 855569 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
39 | Ngurukiri-Kivuria-Gacegeru-Mukuria Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ngurukiri-Kivuria-Gacegeru-Mukuria Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2446672 | 2446672 | 2446672 | County treasury | N/A | 2446672 | N/A | 2446672 | 100% | 2446672 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
40 | Mashamba-Makima-Katharane Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mashamba-Makima-Katharane Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1506915 | 1506915 | 1506915 | County treasury | N/A | 1506915 | N/A | 1506915 | 100% | 1506915 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
41 | Junction Kitoloni-Mukuria-Mwanzo-Mbondoni Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Junction Kitoloni-Mukuria-Mwanzo-Mbondoni Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2594722 | 2594722 | 2594722 | County treasury | N/A | 2594722 | N/A | 2594722 | 100% | 2594722 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
42 | Kitoloni-Mburutani Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kitoloni-Mburutani Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 953080 | 953080 | 953080 | County treasury | N/A | 953080 | N/A | 953080 | 100% | 953080 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
43 | Ngiiri-Kavoori Primary School-Junction R28 Kandoma Primary | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ngiiri-Kavoori Primary School-Junction R28 Kandoma Primary | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1011528 | 1011528 | 1011528 | County treasury | N/A | 1011528 | N/A | 1011528 | 100% | 1011528 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
44 | Gathanje-Mianjatiri Primary School Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gathanje-Mianjatiri Primary School Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2000010 | 2000010 | 2000010 | County treasury | N/A | 2000010 | N/A | 2000010 | 100% | 2000010 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
45 | Kirithiga Foot Bridge Across Thura River | construction of a foot bridge across a river | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Kirithiga Foot Bridge Across Thura River | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3292718 | 3292718 | 3292718 | County treasury | N/A | 3292718 | N/A | 3292718 | 100% | 3292718 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
46 | Kwa Mote-Muu River Kwa Andu a Mbogo-Giaburi Makunguru Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kwa Mote-Muu River Kwa Andu a Mbogo-Giaburi Makunguru Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1666321 | 1666321 | 1666321 | County treasury | N/A | 1666321 | N/A | 1666321 | 100% | 1666321 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
47 | Kanyariri-Mugao Primary Siakago Town | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kanyariri-Mugao Primary Siakago Town | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2311690 | 2311690 | 2311690 | County treasury | N/A | 2311690 | N/A | 2311690 | 100% | 2311690 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
48 | Rukira-Magacha-Kuni Primary Junction E751 Rural Kwa Njuguna | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Rukira-Magacha-Kuni Primary Junction E751 Rural Kwa Njuguna | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3470671 | 3470671 | 3470671 | County treasury | N/A | 3470671 | N/A | 3470671 | 100% | 3470671 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
49 | Siakago-Mathai Primary School-Kabachi Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Siakago-Mathai Primary School-Kabachi Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2737000 | 2737000 | 2737000 | County treasury | N/A | 2737000 | N/A | 2737000 | 100% | 2737000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
50 | Kangurungu Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kangurungu Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 122431 | 122431 | 122431 | County treasury | N/A | 122431 | N/A | 122431 | 100% | 122431 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
51 | Muregwa-Ugweri-Jokingina-Kianduru-Kangondi-Kiringa Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Muregwa-Ugweri-Jokingina-Kianduru-Kangondi-Kiringa Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1783500 | 1783500 | 1783500 | County treasury | N/A | 1783500 | N/A | 1783500 | 100% | 1783500 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
52 | Mirangi-Kiamuvea-Kathugu-Maranga Tarmac-Nthagaiya Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mirangi-Kiamuvea-Kathugu-Maranga Tarmac-Nthagaiya Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1890684 | 1890684 | 1890684 | County treasury | N/A | 1890684 | N/A | 1890684 | 100% | 1890684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
53 | Thau-Kanjatari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Thau-Kanjatari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2845900 | 2845900 | 2845900 | County treasury | N/A | 2845900 | N/A | 2845900 | 100% | 2845900 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
54 | Gatondo-Muuri-Swampy Area Road | construction and upgrading of the road in a swampy area | to improve accessibility and ensure all weather road use | a stable and passable road inswampy area | Development | Gatondo-Muuri-Swampy Area Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 112660 | 112660 | 112660 | County treasury | N/A | 112660 | N/A | 112660 | 100% | 112660 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
55 | Kwa Ndogo-River Kapingazi Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kwa Ndogo-River Kapingazi Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 357240 | 357240 | 357240 | County treasury | N/A | 357240 | N/A | 357240 |  | 357240 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
56 | Kimangaru-Ithira Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kimangaru-Ithira Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 110432 | 110432 | 110432 | County treasury | N/A | 110432 | N/A | 110432 | 100% | 110432 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
57 | Mugoya police HD-Kimandu Farm Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mugoya police HD-Kimandu Farm Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 165621 | 165621 | 165621 | County treasury | N/A | 165621 | N/A | 165621 | 100% | 165621 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
58 | Kairuri Mwara Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kairuri Mwara Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 311320 | 311320 | 311320 | County treasury | N/A | 311320 | N/A | 311320 | 100% | 311320 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
59 | Gatiguri-Kairuri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gatiguri-Kairuri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 350610 | 350610 | 350610 | County treasury | N/A | 350610 | N/A | 350610 | 100% | 350610 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
60 | Ngimari –Kamviu Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ngimari –Kamviu Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2142846 | 2142846 | 2142846 | County treasury | N/A | 2142846 | N/A | 2142846 | 100% | 2142846 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
61 | Kigari-Gaciari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kigari-Gaciari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1023826 | 1023826 | 1023826 | County treasury | N/A | 1023826 | N/A | 1023826 | 100% | 1023826 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
62 | Kibugua-Kamama(A)Kamama Gikirima(B) | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kibugua-Kamama(A)Kamama Gikirima(B) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 131100 | 131100 | 131100 | County treasury | N/A | 131100 | N/A | 131100 | 100% | 131100 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
63 | Ratu Main Road Kiangondu Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ratu Main Road Kiangondu Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 848813 | 848813 | 848813 | County treasury | N/A | 848813 | N/A | 848813 | 100% | 848813 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
64 | Mwondu-Kiandundu Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Mwondu-Kiandundu Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 830934 | 830934 | 830934 | County treasury | N/A | 830934 | N/A | 830934 | 100% | 830934 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
65 | Njeru Mwea-Igumo Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Njeru Mwea-Igumo Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1699056 | 1699056 | 1699056 | County treasury | N/A | 1699056 | N/A | 1699056 | 100% | 1699056 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
66 | Muthethania-Kiandundu Primary School Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Muthethania-Kiandundu Primary School Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1700038 | 1700038 | 1700038 | County treasury | N/A | 1700038 | N/A | 1700038 | 100% | 1700038 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
67 | Kithegi-Kiandunda-Gikingiri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kithegi-Kiandunda-Gikingiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2138461 | 2138461 | 2138461 | County treasury | N/A | 2138461 | N/A | 2138461 | 100% | 2138461 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
68 | Kithimu Village Circuit Roads | construction and improvement of village circuit roads | to improve accessibility and connectivity within the village | functional and accessible village circuit roads | Development | Kithimu Village Circuit Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 76174 | 76174 | 76174 | County treasury | N/A | 76174 | N/A | 76174 | 100% | 76174 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
69 | Kavutiri-Kabuge-Kamugere-St Joseph Kevote-Gatitu-Gacigori Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kavutiri-Kabuge-Kamugere-St Joseph Kevote-Gatitu-Gacigori Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2318811 | 2318811 | 2318811 | County treasury | N/A | 2318811 | N/A | 2318811 | 100% | 2318811 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
70 | Ikunguru-Kathiavari-Gichugu-Gichugu-Kiaragana-Karue-Maitha-Kianjokoma-Gitongonoro Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ikunguru-Kathiavari-Gichugu-Gichugu-Kiaragana-Karue-Maitha-Kianjokoma-Gitongonoro Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3428798 | 3428798 | 3428798 | County treasury | N/A | 3428798 | N/A | 3428798 | 100% | 3428798 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
71 | Kathiri-Gaturi-Muchagori-Mufu-Karue-Maitha Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kathiri-Gaturi-Muchagori-Mufu-Karue-Maitha Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1330564 | 1330564 | 1330564 | County treasury | N/A | 1330564 | N/A | 1330564 | 100% | 1330564 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
72 | Muchagori-Muva-Muchagori-Kianjuki Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Muchagori-Muva-Muchagori-Kianjuki Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1654160 | 1654160 | 1654160 | County treasury | N/A | 1654160 | N/A | 1654160 | 100% | 1654160 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
73 | Kevote-Kamugere-Karumba-Karitiri-Gaturumari-Kianjuki Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kevote-Kamugere-Karumba-Karitiri-Gaturumari-Kianjuki Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1610720 | 1610720 | 1610720 | County treasury | N/A | 1610720 | N/A | 1610720 | 100% | 1610720 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
74 | Gatitu-Gachichore-Kamugere-Kevote Gichagi-Makengi | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gatitu-Gachichore-Kamugere-Kevote Gichagi-Makengi | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1313120 | 1313120 | 1313120 | County treasury | N/A | 1313120 | N/A | 1313120 | 100% | 1313120 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
75 | Makengi-Mutira-Gitiri-Kithiri-Karumba-Karumba-Karatiri | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Makengi-Mutira-Gitiri-Kithiri-Karumba-Karumba-Karatiri | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1069172 | 1069172 | 1069172 | County treasury | N/A | 1069172 | N/A | 1069172 | 100% | 1069172 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
76 | Makengi-Mutira Ngai Ndethia-Gatitu-Gichugu-Gatuariba Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Makengi-Mutira Ngai Ndethia-Gatitu-Gichugu-Gatuariba Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2697998 | 2697998 | 2697998 | County treasury | N/A | 2697998 | N/A | 2697998 | 100% | 2697998 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
77 | Makengi Village Circuit road-Muchagori-Macengi-Muthageri-Kavutiri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Makengi Village Circuit road-Muchagori-Macengi-Muthageri-Kavutiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1298287 | 1298287 | 1298287 | County treasury | N/A | 1298287 | N/A | 1298287 | 100% | 1298287 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
78 | Kavutiri-Kabuge-Muthagere Kavutiri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kavutiri-Kabuge-Muthagere Kavutiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1011361 | 1011361 | 1011361 | County treasury | N/A | 1011361 | N/A | 1011361 | 100% | 1011361 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
79 | Kamuti Junction-Mutii | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kamuti Junction-Mutii | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 937870 | 937870 | 937870 | County treasury | N/A | 937870 | N/A | 937870 | 100% | 937870 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
80 | Kiogogo-Ngaru Wereri | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiogogo-Ngaru Wereri | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 850043 | 850043 | 850043 | County treasury | N/A | 850043 | N/A | 850043 | 100% | 850043 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
81 | Uvariri-Nguthi-Kirie-Ngoche | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Uvariri-Nguthi-Kirie-Ngoche | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1641875 | 1641875 | 1641875 | County treasury | N/A | 1641875 | N/A | 1641875 | 100% | 1641875 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
82 | Kanyuambora-Iriri Kanyanguro Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kanyuambora-Iriri Kanyanguro Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 717855 | 717855 | 717855 | County treasury | N/A | 717855 | N/A | 717855 | 100% | 717855 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
83 | C92 Ishiara Kanyangi Primary Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | C92 Ishiara Kanyangi Primary Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 906772 | 906772 | 906772 | County treasury | N/A | 906772 | N/A | 906772 |  | 906772 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
84 | Machara-Gatituri Primary School Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Machara-Gatituri Primary School Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2707440 | 2707440 | 2707440 | County treasury | N/A | 2707440 | N/A | 2707440 | 100% | 2707440 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
85 | Gatongu-Foot Bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Gatongu-Foot Bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3314700 | 3314700 | 3314700 | County treasury | N/A | 3314700 | N/A | 3314700 | 100% | 3314700 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
86 | Kina-Jessee-Njakairi-Full Gospel Church-Kwa Kabui Kwa Ecita Gaturi road Dubai-Kathigari-Mrs Mugo Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kina-Jessee-Njakairi-Full Gospel Church-Kwa Kabui Kwa Ecita Gaturi road Dubai-Kathigari-Mrs Mugo Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1976275 | 1976275 | 1976275 | County treasury | N/A | 1976275 | N/A | 1976275 | 100% | 1976275 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
87 | Ndunduri-Gicindano-Macandamia Tarmac-Kitheru-Catholic Church Tende Primary-Catholic Church Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Ndunduri-Gicindano-Macandamia Tarmac-Kitheru-Catholic Church Tende Primary-Catholic Church Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2096199 | 2096199 | 2096199 | County treasury | N/A | 2096199 | N/A | 2096199 | 100% | 2096199 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
88 | Uchumi Shauri Yako Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Uchumi Shauri Yako Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 865476 | 865476 | 865476 | County treasury | N/A | 865476 | N/A | 865476 | 100% | 865476 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
89 | Uchumi-Kiambuthi Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Uchumi-Kiambuthi Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 845580 | 845580 | 845580 | County treasury | N/A | 845580 | N/A | 845580 | 100% | 845580 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
90 | Njukiri Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Njukiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 498714 | 498714 | 498714 | County treasury | N/A | 498714 | N/A | 498714 | 100% | 498714 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
91 | Kenya Power-Bondeni | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kenya Power-Bondeni | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 892412 | 892412 | 892412 | County treasury | N/A | 892412 | N/A | 892412 | 100% | 892412 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
92 | Kiambuthi-Ngariama Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiambuthi-Ngariama Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 436044 | 436044 | 436044 | County treasury | N/A | 436044 | N/A | 436044 | 100% | 436044 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
93 | Scheme-Mukangu Primary School Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Scheme-Mukangu Primary School Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 874060 | 874060 | 874060 | County treasury | N/A | 874060 | N/A | 874060 | 100% | 874060 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
94 | Dallas Ring Road and Bus Park | construction and upgrading of the road and construction of a bus park | to improve accessibility and traffic movement and a good parking for buses | bus park completed and an upgraded and functional road | Development | Dallas Ring Road and Bus Park | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 25000000 | 25000000 | 25000000 | County treasury | N/A | 25000000 | N/A | 25000000 | 100% | 25000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
95 | Gitare-Catholic-Kwa Abel | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gitare-Catholic-Kwa Abel | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3384000 | 3384000 | 3384000 | County treasury | N/A | 3384000 | N/A | 3384000 | 100% | 3384000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
96 | Kiang’ombe Road-Zakayo-Ngarari Road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Kiang’ombe Road-Zakayo-Ngarari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2449609 | 2449609 | 2449609 | County treasury | N/A | 2449609 | N/A | 2449609 | 100% | 2449609 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
97 | Ngurueri Factory Road/Bridge | construction and upgrading of the road and a bridge | to improve accessibility and traffic movement | an upgraded and functional road and bridge | Development | Ngurueri Factory Road/Bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
98 | Gategi-Ngandi road | construction and upgrading of the road | to improve accessibility and traffic movement | an upgraded and functional road | Development | Gategi-Ngandi road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1414098 | 1414098 | 1414098 | County treasury | N/A | 1414098 | N/A | 1414098 | 100% | 1414098 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
99 | Construction of Gakungugu-Ngunga footbridge | construction and upgrading of the road | to improve accessibility and traffic movement | to improve accessibility and traffic movement | Development | Construction of Gakungugu-Ngunga footbridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
100 | Construction of Nduuri-Gikuuri footbridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Nduuri-Gikuuri footbridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 300000 | 300000 | 300000 | County treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
101 | Masiara-Mucuwe bridge | construction of a bridge | to improve safety and usability of the bridge | a complete and functional bridge | Development | Masiara-Mucuwe bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
102 | Construction of Ntharawe Bridge | construction of a bridge | to improve safety and usability of the bridge | a complete and functional bridge | Development | Construction of Ntharawe Bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
103 | Construction of Muminji/Gikondi Drift | construction and upgrading of the road | to improve accessibility and traffic movement | to improve accessibility and traffic movement | Development | Construction of Muminji/Gikondi Drift | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4300000 | 4300000 | 4300000 | County treasury | N/A | 4300000 | N/A | 4300000 | 100% | 4300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
104 | Construction of Ntharawe/Thura Drift | construction and upgrading of the road | to improve accessibility and traffic movement | to improve accessibility and traffic movement | Development | Construction of Ntharawe/Thura Drift | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
105 | Construction of Kamumu Stream drift | construction and upgrading of the road | to improve accessibility and traffic movement | to improve accessibility and traffic movement | Development | Construction of Kamumu Stream drift | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
106 | Construction of Marivwe/Ngunyumu drift | construction and upgrading of the road | to improve accessibility and traffic movement | to improve accessibility and traffic movement | Development | Construction of Marivwe/Ngunyumu drift | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
107 | Construction of Kirurumwe coffee factory foot bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Kirurumwe coffee factory foot bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
108 | Construction of Ngai Ndethia coffee foot bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Ngai Ndethia coffee foot bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
109 | Construction of Karitiri coffee factory foot bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Karitiri coffee factory foot bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
110 | Construction of Gichugu foot bridge | construction of a foot bridge | to provide safe pedestrian crossing | a completed and functional foot bridge | Development | Construction of Gichugu foot bridge | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
111 | Thau Bridge-Kagaari South | construction of a bridge | to improve safety and usability of the bridge | a complete and functional bridge | Development | Thau Bridge-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4500000 | 4500000 | 4500000 | County treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
112 | Street lighting installation | installation of street lights | enhance security and efficiency | street light installed | Development | Street lighting installation | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 15000000 | 15000000 | 15000000 | County treasury | N/A | 15000000 | N/A | 15000000 | 100% | 15000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
113 | Installation of High mast flood lights-Siakago | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights-Siakago | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
114 | Installation of High mast flood lights at Kamiu ACK church | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Kamiu ACK church | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
115 | Installation of High mast flood lights at GTI-Iveche junction | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at GTI-Iveche junction | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
116 | Installation of High mast flood lights at Kambo market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Kambo market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
117 | Installation of High mast flood lights at Gakwegori junction | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Gakwegori junction | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
118 | Electrification of Police Post and Chief's Camp | installation and upgrading of electrical systems at the police post | to provide reliable and safe power supply | electrical systems intalled, reliable power supply established | Development | Electrification of Police Post and Chief's Camp | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 200000 | 200000 | 200000 | County treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
119 | Transformer Project-Kiaguchu,Gaikiro,Muva, Gitumbi | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project-Kiaguchu,Gaikiro,Muva, Gitumbi | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
120 | Installation of High mast flood lights at Muchagori/Makengi | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast flood lights at Muchagori/Makengi | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
121 | Transformers – Kagaari South | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformers – Kagaari South | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5080000 | 5080000 | 5080000 | County treasury | N/A | 5080000 | N/A | 5080000 | 100% | 5080000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
122 | Transformer project-Mbeti North | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer project-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
123 | Transformer project-Mavuria(Gitumbiri,Karii and Kabuguri markets) | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer project-Mavuria(Gitumbiri,Karii and Kabuguri markets) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
124 | Transformer project - Karuku | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer project - Karuku | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
125 | Transformer Project - Kithaayoni | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project - Kithaayoni | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
126 | Transformer Project - Mwanyani | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project - Mwanyani | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
127 | Transformer Project – Mashambani Market | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project – Mashambani Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
128 | Transformer Project - Ngeca | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Project - Ngeca | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
129 | Transformer Projects – Mbeti South | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Transformer Projects – Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
130 | Construction of parking bays (Phase 1) | construction of parking bays | to improve vehicle parking and traffic management | completed and functional parking bays | Development | Construction of parking bays (Phase 1) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
131 | Appropriate building technology (research &training) | research and training on appropriate building technology | to promote affordable and sustainable construction methods | trained participants and documented building technologies | Development | Appropriate building technology (research &training) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 5000000 | 5000000 | 5000000 | County treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
132 | Installation of Culverts( Karurina,Kangurungu and Gatondo-Mukuuri Swamp) | installation of calverts for road drainage | to improve drainage and prevent road damage | installed and functional calverts | Development | Installation of Culverts( Karurina,Kangurungu and Gatondo-Mukuuri Swamp) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 300000 | 300000 | 300000 | County treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
133 | Installation of High Flood Lights-Runyenjes | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Runyenjes | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3621700 | 3621700 | 3621700 | County treasury | N/A | 3621700 | N/A | 3621700 | 100% | 3621700 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
134 | Installation of High Flood Lights-Kawanjara Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Kawanjara Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
135 | Installation of High Flood Lights-Kathunguri Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Kathunguri Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
136 | Installation of High mast Flood Light at Mutunduri Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Mutunduri Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
137 | Installation of High mast Flood Light at Sunrise Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Sunrise Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
138 | Installation of High mast Flood Light at Gerish Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Gerish Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
139 | Installation of High mast Flood Light at Karurina Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Karurina Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
140 | Installation of High mast Flood Light at Slaughter Majimbo Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Slaughter Majimbo Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
141 | Installation of High mast Flood Light at Kimangaru Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kimangaru Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
142 | Installation of High mast Flood Light at Gatunduri Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Gatunduri Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
143 | Installation of High mast Flood Light at Ngariama market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Ngariama market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
144 | Installation of High mast Flood Light at Majengo Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Majengo Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
145 | Installation of High mast Flood Light at Kathangari Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kathangari Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
146 | Installation of High mast Flood Light at Kangaru Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kangaru Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
147 | Installation of High mast Flood Light at Irangi Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Irangi Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 |  | 500000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
148 | Installation of High mast Flood Light at Kivue Market | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High mast Flood Light at Kivue Market | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
149 | Installation of High Flood Lights-Other markets | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Other markets | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 8800000 | 8800000 | 8800000 | County treasury | N/A | 8800000 | N/A | 8800000 | 100% | 8800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
150 | Installation of High Flood Lights-Kamugere/Itonguri | installation of floodlights at specific areas | to enhance security and operational efficiency | floodlights installed and maintained | Development | Installation of High Flood Lights-Kamugere/Itonguri | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
151 | Installation of Transformer Boost-Njumbiri | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Installation of Transformer Boost-Njumbiri | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 150000 | 150000 | 150000 | County treasury | N/A | 150000 | N/A | 150000 | 100% | 150000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
152 | Installation of Transformer Boost-Iveche | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Installation of Transformer Boost-Iveche | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 300000 | 300000 | 300000 | County treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
153 | Installation of Transformer Boost-Gichegori | installation of transformer booster | to increase power capacity and improve electricity supply | an installed and operational transformer booster | Development | Installation of Transformer Boost-Gichegori | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 300000 | 300000 | 300000 | County treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
154 | Installation of Transformer at Kaugi market/Dispensary | installation of an electric transformer | to improve power supply and distribution | an installed and operational transformer | Development | Installation of Transformer at Kaugi market/Dispensary | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
155 | Rehabilitation of Access Roads-Ruguru Ngandori | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Access Roads-Ruguru Ngandori | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 8636500 | 8636500 | 8636500 | County treasury | N/A | 8636500 | N/A | 8636500 | 100% | 8636500 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
156 | Manual road reshaping-Gaturi North | manual reshaping of roads to improve surface and drainage | to Improve road passability and drainage | reshaped and passable roads | Development | Manual road reshaping-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
157 | Murraming of Roads -Gaturi North | murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | murramed and passable | Development | Murraming of Roads -Gaturi North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
158 | Repair of Uuya drift-Mavuria | repair of a road drift crossing | to restore safe crossing and improve accessibility | repaired and functional drift crossing | Development | Repair of Uuya drift-Mavuria | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
159 | Repair of Kiritiri-Karimari Drift-Mavuria | repair of a road drift crossing | to restore safe crossing and improve accessibility | repaired and functional drift crossing | Development | Repair of Kiritiri-Karimari Drift-Mavuria | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
160 | Buying/Improvement of Gichugu-Kiaragana Road | improvement of existing road | to enhance road condition and accessibility | improved and functional road | Development | Buying/Improvement of Gichugu-Kiaragana Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
161 | Rehabilitation of Access Roads-Runyenjes Central | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Access Roads-Runyenjes Central | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 6500000 | 6500000 | 6500000 | County treasury | N/A | 6500000 | N/A | 6500000 | 100% | 6500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
162 | Grading and murraming 2KM road-Ishiara Karangare to Kathi | grading and murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and murramed passable roads | Development | Grading and murraming 2KM road-Ishiara Karangare to Kathi | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
163 | Itharari to Cianria access road | construction and upgrading of access roads | to improve road accessibility and traffic movement | a functional access road | Development | Itharari to Cianria access road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
164 | Grading Gwakaithi catholic-Kamama to Kanyangi road | grading of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and passable roads | Development | Grading Gwakaithi catholic-Kamama to Kanyangi road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
165 | Improvement of Kibugu-Kathiria-Kiori-Nthunguri-Kang’ethia | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kibugu-Kathiria-Kiori-Nthunguri-Kang’ethia | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
166 | Improvement of Magurumari-Nguthi-EWASCO intake-Kiandari Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Magurumari-Nguthi-EWASCO intake-Kiandari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 600000 | 600000 | 600000 | County treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
167 | Improvement of Kathuniri-Karumathi-Iriari-Karimari Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kathuniri-Karumathi-Iriari-Karimari Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
168 | Improvement of Mwara-Magoci-Njagi Kathunguri-Njagi Mwendano-Gatiiguru Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Mwara-Magoci-Njagi Kathunguri-Njagi Mwendano-Gatiiguru Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
169 | Opening and rehabilitation of rural Access Roads-Nthawa | opening and improvement of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Opening and rehabilitation of rural Access Roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 7000000 | 7000000 | 7000000 | County treasury | N/A | 7000000 | N/A | 7000000 | 100% | 7000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
170 | Improvement of Kagaari North Access Roads | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Kagaari North Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 8800000 | 8800000 | 8800000 | County treasury | N/A | 8800000 | N/A | 8800000 | 100% | 8800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
171 | Improvement of Ndutori-Manjiatiri Road | improvement and upgrading of roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Improvement of Ndutori-Manjiatiri Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1700000 | 1700000 | 1700000 | County treasury | N/A | 1700000 | N/A | 1700000 | 100% | 1700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
172 | Opening of Makaru Road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Makaru Road-Muminji | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
173 | Opening of Bodeni-Ndiuri-Kaviu Road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Bodeni-Ndiuri-Kaviu Road-Muminji | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1800000 | 1800000 | 1800000 | County treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
174 | Opening of Getua-Kivue road-Muminji | opening of a road | to improve accessibility and connectivity | a cleared and accessible road | Development | Opening of Getua-Kivue road-Muminji | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
175 | General road maintenance/bush clearing-Muminji | general road construction | to improve accessibility and transport | a functional and passable road | Development | General road maintenance/bush clearing-Muminji | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
176 | Grading of Gicherori-Gacoya bridge-Kioruto Nthunguri-Kangethia-Kiiye river at kwa Mwai | grading of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and passable roads | Development | Grading of Gicherori-Gacoya bridge-Kioruto Nthunguri-Kangethia-Kiiye river at kwa Mwai | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1100000 | 1100000 | 1100000 | County treasury | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
177 | Widening, gravelling and murraming of Ngenge-Kavagire/ Soko Mjinga Road | widening gravelling and murraming of a road | to improve road capacity and surface condition | a widened and improved all weather road | Development | Widening, gravelling and murraming of Ngenge-Kavagire/ Soko Mjinga Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
178 | Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road | widening gravelling and murraming of a road | to improve road capacity and surface condition | a widened and improved all weather road | Development | Widening, gravelling and murraming of Rukira-Igumo Primary Sch Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4200000 | 4200000 | 4200000 | County treasury | N/A | 4200000 | N/A | 4200000 | 100% | 4200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
179 | BAT Riandu-Mwondu-Kathitu-Riandu-Gikingiriraod-Grading and spot Murramming | grading and murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | graded and murramed passable roads | Development | BAT Riandu-Mwondu-Kathitu-Riandu-Gikingiriraod-Grading and spot Murramming | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
180 | Rehabilitation of Kyeni North Access Roads | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Kyeni North Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
181 | Murraming of Kyeni North Access Roads | murraming of roads to improve the road surface | to enhance road durability and all weather accessibility | murramed and passable | Development | Murraming of Kyeni North Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
182 | Rehabilitation of Access Roads-Mavuria | improvement and upgrading of access roads | to improve road accessibility and traffic movement | an upgraded and functional road | Development | Rehabilitation of Access Roads-Mavuria | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 7000000 | 7000000 | 7000000 | County treasury | N/A | 7000000 | N/A | 7000000 | 100% | 7000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
183 | Roads and culverts-Nembure Sub location | construction of roads and calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Nembure Sub location | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 |  | 2500000 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
184 | Roads and culverts-Ena Sub location | construction of roads and calverts | to improve road accessibility and enhance safe and efficient transportation and prevent flooding | completed roads with installed calverts | Development | Roads and culverts-Ena Sub location | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3100000 | 3100000 | 3100000 | County treasury | N/A | 3100000 | N/A | 3100000 | 100% | 3100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
185 | Installation of culverts for various access roads-Kithimu | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Installation of culverts for various access roads-Kithimu | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
186 | Repair of Culverts Kiritiri Karii road | repair of calverts | to improve drainage and prevent road damage | repaired and functional calverts | Development | Repair of Culverts Kiritiri Karii road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
187 | Kyeni South Access Roads | construction of access roads | to improve accessibility and transport | completed and functional access roads | Development | Kyeni South Access Roads | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 7000000 | 7000000 | 7000000 | County treasury | N/A | 7000000 | N/A | 7000000 | 100% | 7000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
188 | Purchase of culverts- Kyeni North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts- Kyeni North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
189 | Culverts and general maintenance of roads-Nthawa | upgrading of roads and installation of calverts for road drainage | to improve drainage and prevent road damage | upgraded roads and completed and functional calverts | Development | Culverts and general maintenance of roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
190 | Soko-Uvarire road Culvert | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Soko-Uvarire road Culvert | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
191 | Purchase of culverts- Kagaari North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts- Kagaari North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 100000 | 100000 | 100000 | County treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
192 | Purchase of culverts for road improvement-Gaturi North | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts for road improvement-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 200000 | 200000 | 200000 | County treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
193 | Purchase of culverts for road improvement-Kyeni South | purchase of calverts | purchase of calverts to improve drainage and prevent road damage on the roads | purchased calverts ready for intallation | Development | Purchase of culverts for road improvement-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
194 | Installation of culvert at Kandomba stream-Muminji | installation of calverts for road drainage | to improve drainage and prevent road damage | completed and functional calverts | Development | Installation of culvert at Kandomba stream-Muminji | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2, 900,000 | 2, 900,000 | 2, 900,000 | County treasury | N/A | 2, 900,000 | N/A | 2, 900,000 | 100% | 2, 900,000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
195 | Iriari Rural Electrification | extension of electricity to rural areas | to Improve access to electricity in rural communities | connected households and functional power supply | Development | Iriari Rural Electrification | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 3000000 | 3000000 | 3000000 | County treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
196 | Electrification of Mbondoni Police | electrification of a police post | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Mbondoni Police | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 100000 | 100000 | 100000 | County treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
197 | Electrification of Mbondoni Dispensary | electrification of a dispensary | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Mbondoni Dispensary | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 100000 | 100000 | 100000 | County treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
198 | Electrification of Chief’s Office –Kitololoni | electrification of a chief's office | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of Chief’s Office –Kitololoni | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 100000 | 100000 | 100000 | County treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
199 | Electrification of DO’s office –Makima | electrification of a DO's office | to improve lighting security and operations | a connected and functional electricity supply | Development | Electrification of DO’s office –Makima | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 300000 | 300000 | 300000 | County treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
200 | Acquisition of land | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 14413800 | 14413800 | 14413800 | County treasury | N/A | 14413800 | N/A | 14413800 | 100% | 14413800 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
201 | Acquisition of Gravel quarries | acquisition of gravel quarries for road works | to ensure reliable supply of gravel for construction | gravel quarries acquired and available for use | Development | Acquisition of Gravel quarries | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 4913800 | 4913800 | 4913800 | County treasury | N/A | 4913800 | N/A | 4913800 | 100% | 4913800 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
202 | Acquisition of land and opening of Kiriari-Kaguma-Karau Road | opening of a road and acquisition of land for public use | to secure land for development of public projects, to ensure efficient transport | land acquired and available for development, road opened | Development | Acquisition of land and opening of Kiriari-Kaguma-Karau Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
203 | Acquisition of land for Gicherori-Mwithi-Kibugu Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Gicherori-Mwithi-Kibugu Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
204 | Acquisition of land for Kwa Cema-Gichangai-Kithiga Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Kwa Cema-Gichangai-Kithiga Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
205 | Acquisition of land for Access roads-Nthawa | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for Access roads-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
206 | Acquisition of land for close cut to Kirimiri forest | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land for close cut to Kirimiri forest | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
207 | Acquisition of land at Kagumori | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kagumori | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
208 | Acquisition of land at Kaveti Primary Link Road | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kaveti Primary Link Road | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1100000 | 1100000 | 1100000 | County treasury | N/A | 1100000 | N/A | 1100000 | 100% | 1100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
209 | Acquisition of land at Kandete linking loop | acquisition of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Acquisition of land at Kandete linking loop | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
210 | Purchase of Land for Thara Road(Kathuro farm) | purchase of land for public use | to secure land for development of public projects | land acquired and available for development | Development | Purchase of Land for Thara Road(Kathuro farm) | N/A | N/A | N/A | Development | Development | Development | 2014-07-01 | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled