## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Conditional Grant For County Aggregated Industrial Park Programme | Aggregated industrial park to support manufacturing , value additionand SME growth through shared industrial infrastructure | To promote industrialization, job creation and economic growth | Functional industrial park, improved industrial infrastructure, increased manufacturing,employment orpportunities | Tourism | Conditional Grant For County Aggregated Industrial Park Programme |  | County wide |  | Tourism | Tourism | Tourism | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 250000000 | 250000000 | 250000000 | County Treasury | N/A | 250000000 | N/A | 250000000 | 100% | 62500000 | N/A | 187500000 | Ongoing | 25% | N/A | N/A | N/A | N/A | N/A
2 | Conditional Grant For County Aggregated Industrial Park Programme-Counter Funding | Counterpart funding to support implementation of county aggregated industrial park through co financing of infrastructure and operational requirements | To compliment national government funding for timely and effective development of county aggregated industrial park | County counterpart fund provided, accelerated development of the park, improved project implementation and sustainability | Tourism | Conditional Grant For County Aggregated Industrial Park Programme-Counter Funding |  | County wide |  | Tourism | Tourism |  | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 10000000 | 10000000 | 10000000 | County Treasury | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
3 | Construction Of Ishiara Livestock Market | Mordern livestock market to support organized livestock trade and improve market acces | inhance livestock marketing, promote local growth and farmers income | mofern livestock market constructed, increased livestock trade | Development | Construction Of Ishiara Livestock Market |  | Evurore |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
4 | Renovation Of Manyatta Market | upgrading the market and improve trading facilities | enhance market infrastructure and support efficient trade | market facilities renovated, improved trader working condition | Development | Renovation Of Manyatta Market |  | Ruguru Ngandori |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1999005 | N/A | 995 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
5 | Construction Of Muraru Market | construction of the market to provide organiized and improved trading faciities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Construction Of Muraru Market |  | Mbeti South |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Kibugu Market | construction of the market to provide organiized and improved trading faciities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Construction Of Kibugu Market |  | Ruguru Ngandori |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
7 | Construction And Other Civil Works For The Embu Market (Including Relocation Of Traders) | construction of related civil works including temporary relocation of traders during implementation | To modernize Embu market while ensuring continuity of trading activities | market civil works completed, traders temporarily relocated, improved market infrastructure | Development | Construction And Other Civil Works For The Embu Market (Including Relocation Of Traders) |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 3928918 | N/A | 71082 | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A
8 | Rehabilitation Of Kithimu Market | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation Of Kithimu Market |  | Kithimu |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 5288441 | 5288441 | 5288441 | County Treasury | N/A | 5288441 | N/A | 5288441 | 100% | 5235164 | N/A | 53277 | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A
9 | Construction Of Maviani Toilet In Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Maviani Toilet In Mwea |  | Mwea |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
10 | Construction of a Septic Tank for the Kianjokoma Market Toilet In Kagaari North | construction of septic tank and public toilet | enhance hygiene and public health | septic tank constructed, improved sanitation and waste management | Development | Construction of a Septic Tank for the Kianjokoma Market Toilet In Kagaari North |  | Kagaari North |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Mwanyani And Musingini Market Toilets In Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mwanyani And Musingini Market Toilets In Makima |  | Makima |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 699920 | 699920 | 699920 | County Treasury | N/A | 699920 | N/A | 699920 | 100% | 699920 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
12 | Installation Of Floodlights At Kathuriri Market And Checkpoint And Maintenance Of Floodlight Masts In Runyenjes Central | installation and maintainance of floodlights at specific markets | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights At Kathuriri Market And Checkpoint And Maintenance Of Floodlight Masts In Runyenjes Central |  | Runyenjes Central |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1247525 | 1247525 | 1247525 | County Treasury | N/A | 1247525 | N/A | 1247525 | 100% | 1247525 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
13 | Proposed Rehabilitation And Maintenance Of Kiritiri Market In Mavuria | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Proposed Rehabilitation And Maintenance Of Kiritiri Market In Mavuria |  | Mavuria |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 497466 | 497466 | 497466 | County Treasury | N/A | 497466 | N/A | 497466 | 100% | 497466 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
14 | Installation Of Three(3) Solar Floodlights At Mwanzo,Makima and Mashamba Market And Proposed Electrical Works At Makima Market In Makima | installation and maintainance of floodlights at specific markets and finishing the electrical works | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Three(3) Solar Floodlights At Mwanzo,Makima and Mashamba Market And Proposed Electrical Works At Makima Market In Makima |  | Makima |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1595928 | 1595928 | 1595928 | County Treasury | N/A | 1595928 | N/A | 1595928 | 100% | 1595928 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
15 | Installation Of One Solar Floodlight At Rugorwe In Mavuria | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of One Solar Floodlight At Rugorwe In Mavuria |  | Mavuria |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 497352 | 497352 | 497352 | County Treasury | N/A | 497352 | N/A | 497352 | 100% | 497352 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
16 | Installation Of Solar Floodlight at Kerie Market In Muminji | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Solar Floodlight at Kerie Market In Muminji |  | Muminji |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 498400 | N/A | 1600 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
17 | Construction Of Manyatta Market Toilet In Ruguru Ngandori | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Manyatta Market Toilet In Ruguru Ngandori |  | Ruguru Ngandori |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 499997 | 499997 | 499997 | County Treasury | N/A | 499997 | N/A | 499997 | 100% | 499997 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
18 | Installation Of Floodlights in Kune,Kamugu ,Ciambugu In Nthawa | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights in Kune,Kamugu ,Ciambugu In Nthawa |  | Nthawa |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
19 | Construction Of Boda Boda Sheds at Siakago In Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds at Siakago In Nthawa |  | Nthawa |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 300000 | 300000 | 300000 | County Treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
20 | Water Stand In Kathangariri and Mbuvori Markets In Nginda | water stand to provide accesible and safe water | improve access to clean and safe water for residents | water stand constructed, improved access to clean water | Development | Water Stand In Kathangariri and Mbuvori Markets In Nginda |  | Nginda |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 299755 | 299755 | 299755 | County Treasury | N/A | 299755 | N/A | 299755 | 100% | 299755 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
21 | Installation Of Flood Light In Mbeti South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Light In Mbeti South |  | Mbeti South |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
22 | Construction Of Boda Boda Shed In Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed In Mbeti South |  | Mbeti South |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 489937 | N/A | 10063 | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A
23 | Renovation Of Karurumo Market In Kyeni South | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Renovation Of Karurumo Market In Kyeni South |  | Kyeni South |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 200000 | 200000 | 200000 | County Treasury | N/A | 200000 | N/A | 200000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
24 | Installation Of Flood Lights In Kyeni South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Lights In Kyeni South |  | Kyeni South |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 949825 | N/A | 50175 | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A
25 | Installation Of Flood Lights at Mufu Market In Kyeni North | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Lights at Mufu Market In Kyeni North |  | Kyeni North |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 379930 | N/A | 20070 | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A
26 | Construction Of Hawker Stalls In Kirimari | construction of organized stalls | improned trading conditions and support snall scale traders | hawkers stalls constructed, improved trading organisation | Development | Construction Of Hawker Stalls In Kirimari |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 2989900 | N/A | 10100 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
27 | Rehabilitation Of Embu Main Market (Gutter Repairs) In Kirimari | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation Of Embu Main Market (Gutter Repairs) In Kirimari |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 993888 | N/A | 6112 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
28 | Purchase and Installation Of Floodlight Lamps In Kirimari | purchase and installation of floodlights | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Purchase and Installation Of Floodlight Lamps In Kirimari |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4488960 | N/A | 11040 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
29 | Construction of a Shed at the Miraa Market In Kirimari | construction of shaded area in the market | improve msrkrt comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of a Shed at the Miraa Market In Kirimari |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 3995643 | N/A | 4357 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
30 | Construction Of Boda Boda shed At Mwanzo Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda shed At Mwanzo Market-Makima |  | Makima |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
31 | Installation Of Floodlight At Malamuni Market-Makima | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlight At Malamuni Market-Makima |  | Makima |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
32 | Construction Of Toilet At Machang’a Market-Mavuria | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Machang’a Market-Mavuria |  | Mavuria |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
33 | Completion Of Kiritiri Bus Park-Mavuria | completion of ongoing works to make it funtional | to improve public transport organisation and passenger convnvinience | bus park completed, improved transport infrastructure | Development | Completion Of Kiritiri Bus Park-Mavuria |  | Mavuria |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
34 | Installation Of A Floodlight At Ciakavuri-Mavuria | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of A Floodlight At Ciakavuri-Mavuria |  | Mavuria |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 1OO% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
35 | Renovation and Water Connection to the ablution Blocks At the Runyenjes Open Air Market and Mitumba Market-Runyenjes Central | renovation of water connection to the specified area | enhance acces to reliable water and improve facility conditions | renovation works completed, water connection installed , improved service delivery and hygiene | Development | Renovation and Water Connection to the ablution Blocks At the Runyenjes Open Air Market and Mitumba Market-Runyenjes Central |  | Runyenjes Central |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 750000 | 750000 | 750000 | County Treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
36 | Fencing And gate And Electrification Of Newsite Honey Processor | fencing and electrification of new honey processing site | to secure the facility and support efficient honey processing operations | site fenced, electricity connected, increased security and operational capacity | Development | Fencing And gate And Electrification Of Newsite Honey Processor |  | Kiambere |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
37 | Construction Of Karambari Toilet-Muminji | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Karambari Toilet-Muminji |  | Muminji |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
38 | Renovation Of Kanja Market-Kagaari North | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency |  | Renovation Of Kanja Market-Kagaari North |  | Kagaari North |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1999956 | N/A | 44 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
39 | Construction Of Kathangari Market Phase 1-Kirimari | construction and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Construction Of Kathangari Market Phase 1-Kirimari |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A |  | N/A
40 | Relocation Of Runyenjes Market | relocation of the market to a suitable site | to enhance market infrastructure and support efficient trade | market succecfully relocated, improved trading environment | Development | Relocation Of Runyenjes Market |  | Runyenjes Central |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 9000000 | 9000000 | 9000000 | County Treasury | N/A | 9000000 | N/A | 9000000 | 100% | 9000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
41 | Construction Of Toilet At Kibugu Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Kibugu Market |  | Ruguru Ngandori |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
42 | Construction Of Canopy And Maintenance Works At The New Embu Town Market(Canaan) | construction and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Construction Of Canopy And Maintenance Works At The New Embu Town Market(Canaan) |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 3997940 | N/A | 2060 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
43 | Completion Of Works At Kithimu Market | completion of ongoing works to make it funtional | o enhance market infrastructure and support efficient trade | Market rehabilitated, improved trading facilities and increased market efficiency | Development | Completion Of Works At Kithimu Market |  | Kithimu |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 4700000 | 4700000 | 4700000 | County Treasury | N/A | 4700000 | N/A | 4700000 | 100% | 4695100 | N/A | 4900 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
44 | Electrical Works at the New Embu Town Market(Canaan) | installation and upgrading electrical systems in the new market | to provide reliable and safe power supply for the market | electrical systems installed, reliable power supply established, improved market operations | Development | Electrical Works at the New Embu Town Market(Canaan) |  | Kirimari |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1998109 | N/A | 1891 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
45 | Construction Of Toilet At Karaba Market-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Karaba Market-Mwea |  | Mwea |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
46 | Construction Of Boda Boda Shed At Ishiara-Evurore | construction of shade areas for bodaboda riders | to provide safe, organised and comfortable parking fo bodabodas | bodaboda shades constructed, enhanced traffic management at designated area | Development | Construction Of Boda Boda Shed At Ishiara-Evurore |  | Evurore |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 300000 | 300000 | 300000 | County Treasury |  | 300000 | N/A | 300000 | 100% |  | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
47 | Construction Of Toilet At Kanyuambora Market-Evurore | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Kanyuambora Market-Evurore |  | Evurore |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% |  | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
48 | Construction of Kianjokoma Market Toilet In Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Kianjokoma Market Toilet In Kagaari North |  | Kagaari North |  | Development | Development | Development | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 999388 | N/A | 612 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
49 | Opening Of Mount Kenya South Eastern Route | opening and development of the Mt Kenya south eastern route | to enhance acceccibility and boost tourism activities in the region | south eastern route opened, increased tourism and local economic activity | Tourism | Opening Of Mount Kenya South Eastern Route |  | Kagaari North |  | Tourism | Tourism | Tourism | 2023-07-01 | 2023-07-01 | 2024-06-30 | 2024-06-30 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A
2022/2023
1 | BCE Driving Course | Provision of professional driving training | to equip trainees with skills and certification | trained NTSA certified professional drivers | TRADE | BCE Driving Course | N/A | Country Wide | N/A | Trade | Trade | Trade | 2022-07-01 | 2022-07-01 | 2023-06-30 | 2023-06-30 | 592200 | 592000 | 592000 | County Treasury | N/A | 592000 | N/A | 592000 | 100% | 592000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2 | Supply And Delivery Of P.A Systems for Youth Groups in Kirimari | procurement and distribution of public address systems to organised youth groups | to enhance communication, event organisation and income generating activities to youth groups | P.A systems supplied and delivered to targeted youth groups | Development | Supply And Delivery Of P.A Systems for Youth Groups in Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 2023-06-30 | 30/062023 | 1499000 | 1499000 | 1499000 | County Treasury | N/A | 1499000 | N/A | 1499000 | 100% | 1499000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Construction Of Kilia Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Kilia Market Shed | N/A | Mwea | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1998251 | 1998251 | 1998251 | County Treasury | N/A | 1998251 | N/A | 1998251 | 100% | 1998179 | N/A | 72 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
4 | Construction Of Nthingini Market Shed | construction of covered market shade to support traders activities | to provide safe and organized trading environment for traders | completed and functional market shade | Development | Construction Of Nthingini Market Shed | N/A | Evurore | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 998609 | 998609 | 998609 | County Treasury | N/A | 998609 | N/A | 998609 | 100% | 998609 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Construction of Industrial Shed at Newsite | construction of the shade at newsite to support production and processing activities | to provide sheltered and efficient working space for industrial operations | completed and operational industrial shade at newsite | Development | Construction of Industrial Shed at Newsite | N/A | Kiambere | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1986268 | 1986268 | 1986268 | County Treasury | N/A | 1986268 | N/A | 1986268 | 100% | 1986268 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Kamumu Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Kamumu Market Shed | N/A | Evurore | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 998022 | 998022 | 998022 | County Treasury | N/A | 998022 | N/A | 998022 | 100% | 998022 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Construction Of Jua Kali Sheds in Kirimari | construction of shaded areas for jua kali artisians | to provide safe and organized working environment for jua kali artisians | completed and functional jua kali shade | Development | Construction Of Jua Kali Sheds in Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 2999829 | 2999829 | 2999829 | County Treasury | N/A | 2999829 | N/A | 2999829 | 100% | 2999830 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Construction of Boda Boda Shed at Ngunyumu and Ngarweri | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Ngunyumu and Ngarweri | N/A | Evurore | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 398646 | 398646 | 398646 | County Treasury | N/A | 398646 | N/A | 398646 | 100% | 398646 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Construction Of Market Toilet At Nthingini,Mugui,Kiriari And Kathanjuri | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Nthingini,Mugui,Kiriari And Kathanjuri | N/A | Various Wards | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1996731 | 1996731 | 1996731 | County Treasury | N/A | 1996731 | N/A | 1996731 | 100% | 1996731 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Proposed construction of Jua Kali sheds in Kirimari | construction of shaded areas for jua kali artisians | to provide safe and organized working environment for jua kali artisians | completed and functional jua kali shade | Development | Proposed construction of Jua Kali sheds in Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 299830 | 299830 | 299830 | County Treasury | N/A | 299830 | N/A | 299830 | 100% | 299830 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Installation of two Flood Lights in Mbeti North | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation of two Flood Lights in Mbeti North | N/A | Mbeti North | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 798071 | 798071 | 798071 | County Treasury | N/A | 798071 | N/A | 798071 | 100% | 798070 | N/A | 1 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
12 | Construction of Mariari Market Boda Boda Shed | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction of Mariari Market Boda Boda Shed | N/A | Mbeti North | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 249667 | 249667 | 249667 | County Treasury | N/A | 249667 | N/A | 249667 | 100% | 249667 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Electrification of Kithimu/Ndatu Markets | installation and upgrading of electrical systems at the market | to provide reliable and safe power supply for market activities | electrical systems intalled, reliable power supply established, improved market operations | Development | Electrification of Kithimu/Ndatu Markets | N/A | Kithimu | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 292390 | 292390 | 292390 | County Treasury | N/A | 292390 | N/A | 292390 | 100% | 292390 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Rehabilitation Of Kithimu Market | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation Of Kithimu Market | N/A | Kithimu Market | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 20000000 | 20000000 | 20000000 | County Treasury | N/A | 20000000 | N/A | 20000000 | 100% | 14711559 | N/A | 5288441 | Ongoing | 74% | N/A | N/A | N/A | N/A | N/A
15 | Construction of Market Shade at Kabugua Market-Evurore | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shade at Kabugua Market-Evurore | N/A | Evurore | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1499880 | N/A | 120 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Musingini Market Toilets-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Musingini Market Toilets-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Construction Of Hawker Stalls-Kirimari | construction of organized stalls | improned trading conditions and support snall scale traders | hawkers stalls constructed, improved trading organisation | Development | Construction Of Hawker Stalls-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Rehabilitation Of Embu Main Market (Gutter Repairs)- Kirimari | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation Of Embu Main Market (Gutter Repairs)- Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Installation /Electricity Repairs of Flood Lights- Kirimari | installation and electricity repairs of floodlights at specific areas to ensure adequate lighting and safety | enhance visibility, safety and security | floodlights installed and repaired, improved lighting , visibility and safety, enhanced public safety and security | Development | Installation /Electricity Repairs of Flood Lights- Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Market Toilet-Ruguru Ngandori | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet-Ruguru Ngandori | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Installation Of Flood lights at Ena/Kauriro-Kithimu | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood lights at Ena/Kauriro-Kithimu | N/A | Kithimu | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 700000 | 700000 | 700000 | County Treasury | N/A | 700000 | N/A | 700000 | 100% | 697253 | N/A | 2747 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
22 | Installation Of Flood Lights at Mufu Market-Kyeni North | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Lights at Mufu Market-Kyeni North | N/A | Kyeni North | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Installation Of Flood Light at Makima Market-Makima | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Light at Makima Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Installation Of Flood Light at Mwanzo Market-Makima | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Light at Mwanzo Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Installation Of Flood Light at Mashamba Market-Makima | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Light at Mashamba Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Makima Market Shed Lighting-Makima | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Makima Market Shed Lighting-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Construction Of Boda Boda Shed at Mbondoni Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed at Mbondoni Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 250000 | 250000 | 250000 | County Treasury | N/A | 250000 | N/A | 250000 | 100% | 237637 | N/A | 12363 | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A
28 | Construction Of Boda Boda Shed at Gikuru Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed at Gikuru Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 250000 | 250000 | 250000 | County Treasury | N/A | 250000 | N/A | 250000 | 100% | 235004 | N/A | 14996 | Ongoing | 94% | N/A | N/A | N/A | N/A | N/A
29 | Construction Of Mwanyani Market Toilet-Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mwanyani Market Toilet-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 350000 | 350000 | 350000 | County Treasury | N/A | 350000 | N/A | 350000 | 100% | 350000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Construction Of Musingini Market Toilet-Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Musingini Market Toilet-Makima | N/A | Makima | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 350000 | 350000 | 350000 | County Treasury | N/A | 350000 | N/A | 350000 | 100% | 350000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Installation Of Floodlights At Kathangariri,Gicherori,Kangethia and Kathuniri-Nginda | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Floodlights At Kathangariri,Gicherori,Kangethia and Kathuniri-Nginda | N/A | Nginda | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1997600 | N/A | 2400 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
32 | Water Stand In Kathangariri and Mbuvori Markets-Nginda | construction of water stand to provide accecible and safe water to the community | to improve access to clean and safe water | water stand constructed, improved access to clean water | Development | Water Stand In Kathangariri and Mbuvori Markets-Nginda | N/A | Nginda | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 300000 | 300000 | 300000 | County Treasury | N/A | 300000 | N/A | 300000 | 100% | 300000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Construction of Boda Boda Shed-Kagaari South | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed-Kagaari South | N/A | Kagaari South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 800000 | 800000 | 800000 | County Treasury | N/A | 800000 | N/A | 800000 | 100% | 789878 | N/A | 10122 | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A
34 | Construction of a Pit Latrine (Three Door) At Kawanjara-Kagaari south | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of a Pit Latrine (Three Door) At Kawanjara-Kagaari south | N/A | Kagaari South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 599964 | N/A | 36 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
35 | Installation Of Flood Lights-Kyeni South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Lights-Kyeni South | N/A | Kyeni South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
36 | Construction Of Boda Boda Sheds-Kyeni South | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds-Kyeni South | N/A | Kyeni South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1195856 | N/A | 4144 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
37 | Renovation Of Karurumo Market-Kyeni South | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Renovation Of Karurumo Market-Kyeni South | N/A | Kyeni South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 200000 | 200000 | 200000 | County Treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
38 | Installation Of Flood Light-Mbeti South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Light-Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
39 | Construction Of Boda Boda Shed-Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed-Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
40 | Construction Of Kianjokoma Market Toilet-Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Kianjokoma Market Toilet-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
41 | Installation Of Floodlights in Magacha,Kamugo,Ciambugu and Siakago-Nthwa | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights in Magacha,Kamugo,Ciambugu and Siakago-Nthwa | N/A | Nthwa | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
42 | Installation of Flood Light Mast at Kathuriri-Runyenjes Central | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation of Flood Light Mast at Kathuriri-Runyenjes Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
43 | Installation of Flood Light Mast at Check Point-Runyenjes Central | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation of Flood Light Mast at Check Point-Runyenjes Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
44 | Water Connection to Exstisting Ablution Block at Runyenjes Open Air Market and Mitimba Market-Runyenjes Central | Connection of water supply to the specified area | To enhance access to reliable water and improve facility conditions | water connection installed, improved service delivery and hygiene | Development | Water Connection to Exstisting Ablution Block at Runyenjes Open Air Market and Mitimba Market-Runyenjes Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 150000 | 150000 | 150000 | County Treasury | N/A | 150000 | N/A | 150000 | 100% | 150000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
45 | Installation Of Floodlights Mats At Gichiche,Kigaa,Gachagori,Kathuriri and Check point-Runyenjes Central | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights Mats At Gichiche,Kigaa,Gachagori,Kathuriri and Check point-Runyenjes Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 250000 | 250000 | 250000 | County Treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
46 | Construction Of Boda Boda Shed-Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 484747 | N/A | 15253 | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A
47 | Installation Of Flood Light-Mavuira | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Light-Mavuira | N/A | Mavuria | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
48 | Rehabilitation and Maintenance of Kiritiri Market-Mavuria | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation and Maintenance of Kiritiri Market-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
49 | Construction Of Boda Boda Sheds at Siakago-Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds at Siakago-Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2022-07-01 |  | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
50 | Installation Of Solar Floodlight at Kerie Market-Muminji | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Solar Floodlight at Kerie Market-Muminji | N/A | Muminji | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
51 | Construction of a Septic Tank for the Kianjokoma Market Toilet-Kagaari North | construction of septic tank and public toilet | enhance hygiene and public health | septic tank constructed, improved sanitation and waste management | Development | Construction of a Septic Tank for the Kianjokoma Market Toilet-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
52 | Construction And Other Civil Works for The Embu Market (Including relocation of traders) | construction of related civil works including temporary relocation of traders during implementation | To modernize Embu market while ensuring continuity of trading activities | market civil works completed, traders temporarily relocated, improved market infrastructure | Development | Construction And Other Civil Works for The Embu Market (Including relocation of traders) | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
53 | Construction of a Shed at the Miraa Market-Kirimari | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of a Shed at the Miraa Market-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
54 | Construction Of the County Aggregation Industrialization Park | Aggregated industrial park to support manufacturing , value additionand SME growth through shared industrial infrastructure | To promote industrialization, job creation and economic growth | Functional industrial park, improved industrial infrastructure, increased manufacturing,employment orpportunities | Development | Construction Of the County Aggregation Industrialization Park | N/A | Mavuria | N/A | Development | Development | Development | 2022-07-01 | 2022-07-01 | 30/062023 | 30/062023 | 100000000 | 100000000 | 100000000 | County Treasury | N/A | 100000000 | N/A | 100000000 | 100% | 100000000 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
2021/2022
1 | Reflector Jackets And Safety Helmets Programme-Kirimari | provision of reflector jackets and safety helmets to enhance road safety | to reduce road accidents and improve safety for road users | reflector jackets distributed, safety helmets provided, improved road safety awareness and compliance | Development | Reflector Jackets And Safety Helmets Programme-Kirimari | Manyatta | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 999800 | 999800 | 999800 | County treasury | N/A | 999800 | N/A | 999800 | 100% | 999800 | N/A | N/A | Completed | 100% |  | N/A | N/A | N/A | N/A
2 | Construction Of Public Toilet At Kamumu And Ciangera | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Public Toilet At Kamumu And Ciangera | Mbeere North | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 799913 | 799913 | 799913 | County treasury | N/A | 799913 | N/A | 799913 | 100% | 799913 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Construction Of Karii Boda Boda Shed In Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Karii Boda Boda Shed In Mavuria | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Completion Of Kiritiri Market In Mavuria | completion and upgrading of the market | to enhance market infrastructure and support efficient trade | market completed, improved trading facilities and increased market efficiency | Development | Completion Of Kiritiri Market In Mavuria | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Installation Of Flood Light At Kiritiri Buspark In Mavuria | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Light At Kiritiri Buspark In Mavuria | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Kilia Market Shed In Mwea | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Kilia Market Shed In Mwea | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Construction Of A Boda Boda Shed At Mwanzo Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of A Boda Boda Shed At Mwanzo Market-Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Electrification Of Makima Market Shed-Makima | installation and upgrading of electrical systems at the market shade | to provide reliable and safe power supply for market activities | electrical systems intalled, reliable power supply established, improved market operations | Development | Electrification Of Makima Market Shed-Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 100000 | 100000 | 100000 | County treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Construction Of Toilet At Musingini Market-Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Musingini Market-Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 350000 | 350000 | 350000 | County treasury | N/A | 350000 | N/A | 350000 | 100% | 350000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Construction Of A Boda Boda Shed At Makima Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of A Boda Boda Shed At Makima Market-Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Mwanyani Market Toilet In Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mwanyani Market Toilet In Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 350000 | 350000 | 350000 | County treasury | N/A | 350000 | N/A | 350000 | 100% | 350000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Installation Of Floodlight At Marimari Shopping Centre -Kiambere | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlight At Marimari Shopping Centre -Kiambere | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Installation of Floodlight At Newsite- Kiambere | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation of Floodlight At Newsite- Kiambere | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Construction Of Stage Shed –Kagaari North | construction of shaded area to provide shelter for passenger s and operators | to improve comfort, organisation and safety at the stage | stage shade constructed, improved shelter and comfort, enhanced stage organisation and safety | Development | Construction Of Stage Shed –Kagaari North | Mbeere North | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Market Sheds At Muchonoke And Riandu In Nthawa | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Sheds At Muchonoke And Riandu In Nthawa | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 2500000 | 2500000 | 2500000 | County treasury | N/A | 2500000 | N/A | 2500000 | 100% | 980300 | N/A | 1519700 | Ongoing | 39% | N/A | N/A | N/A | N/A | N/A
16 | Completion And Fencing Of Muraru Toilets In Mbeti South |  |  |  | Development | Completion And Fencing Of Muraru Toilets In Mbeti South | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 999983 | 999983 | 999983 | County treasury | N/A | 999983 | N/A | 999983 | 100% | 999983 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Construction Of Mitumba Ablution Block In Runyenjes Central |  |  |  | Development | Construction Of Mitumba Ablution Block In Runyenjes Central | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Installation Of Floodlight-Mbeti South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlight-Mbeti South | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Installation Of Floodlights At Kangari And Check Point-Runyenjes Central | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights At Kangari And Check Point-Runyenjes Central | Manyatta | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 800000 | N/A | 200000 | Ongoing | 80% | N/A | N/A | N/A | N/A | N/A
20 | Installation Of Floodlights –Mbeti North | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlights –Mbeti North | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Construction Of Nthingini Market Shed-Mwea | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Nthingini Market Shed-Mwea | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 400000 | N/A | 600000 | Ongoing | 40% | N/A | N/A | N/A | N/A | N/A
22 | Installation Of Floodlight At Kwa Gichonge –Kyeni South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlight At Kwa Gichonge –Kyeni South | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Construction Of Boda Boda Shed At Rugogwe-Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Rugogwe-Mavuria | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Installation Of Flood Light At Kirie-Muminji | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Flood Light At Kirie-Muminji | Mbeere North | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Roofing Of Jua Kali Market Phase 2-Kithimu | roofing works of jua kali market, improve protection and working condition | to enhance shelter and support efficient operations at the market | market roofing completed, better working environment for traders | Development | Roofing Of Jua Kali Market Phase 2-Kithimu | Manyatta | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 800000 | N/A | 700000 | Ongoing | 53% | N/A | N/A | N/A | N/A | N/A
26 | Karurumo Market Planning-Kyeni South | planning and design of karurumo market to guite organized market development | to ensure orderly, efficient, and sustainable market development | market plan developed, defined market layout and zoning | Development | Karurumo Market Planning-Kyeni South | Runyenjes | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Kitoloni And Mbondoni Market Planning-Makima | planning and design of Kitoloni and Mbondoni market to guite organized market development | to ensure orderly, efficient, and sustainable market development | market plan developed, defined market layout and zoning | Development | Kitoloni And Mbondoni Market Planning-Makima | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1600000 | 1600000 | 1600000 | County treasury | N/A | 1600000 | N/A | 1600000 | 100% | 1600000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Restoration of Market Shed At Mutuobare-Kiambere | restoration and repair of market shade to improve protection for traders and goods | enhance shelter and improve trading environment | market shade restored, improved protection from weather,better trading conditions | Development | Restoration of Market Shed At Mutuobare-Kiambere | Mbeere South | N/A | N/A | Development | Development | Development | 2021-07-01 | 2021-07-01 | 30/06/20222 | 30/06/20222 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2020/2021
1 | Construction Of Liberty Mama Mboga Sheds-Kirimari | construction of sheds for mama mboga traders at liberty area | to provide a safe ,organized and weather protected trading space for mama mboga venders | completed and functional mama mboga shedds at liberty | Development | Construction Of Liberty Mama Mboga Sheds-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 499786 | N/A | 214 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
2 | Construction Of KRA Boda Boda Sheds-Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Construction Of KRA Boda Boda Sheds-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 600100 | N/A | 99900 | Ongoing | 86% | N/A | N/A | N/A | N/A | N/A
3 | Construction Of Oil Libya Boda Boda Sheds-Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Oil Libya Boda Boda Sheds-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | 699468 | N/A | 532 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
4 | Roofing Of Jua Kali Boda Boda Sheds And FloodlightsKithimu | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Roofing Of Jua Kali Boda Boda Sheds And FloodlightsKithimu | N/A | Kithimu | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 2499255 | 2499255 | 2499255 | County treasury | N/A | 2499255 | N/A | 2499255 | 100% | 2499255 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Construction Of Market Shed At Kilia -Mwea | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Kilia -Mwea | N/A | Mwea | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 |  | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Boda Boda Shed At Makima Market-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Makima Market-Makima | N/A | Makima | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 249574 | N/A | 426 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
7 | Construction Of Market Toilet At Kianjokoma-Emikel Women Enterprises Ltd | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Kianjokoma-Emikel Women Enterprises Ltd | N/A | Kagaari North | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 498147 | 498147 | 498147 | County treasury | N/A | 498147 | N/A | 498147 | 100% | 498148 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Market Shed At Newsite And Bodaboda Shed At Mutuobare-Tili Heights Limited | construction of market and bodaboda shades at designated areas | to provide safe, organized and weather protected spaces for traders and bodaboda operators | completed and functional market and bodaboda shades | Development | Market Shed At Newsite And Bodaboda Shed At Mutuobare-Tili Heights Limited | N/A | Kiambere | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1249482 | 1249482 | 1249482 | County treasury | N/A | 1249482 | N/A | 1249482 | 100% | 1249482 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Construction Of Mitumba Market Toilet-Moskany Construction Solution | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mitumba Market Toilet-Moskany Construction Solution | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 699880 | 699880 | 699880 | County treasury | N/A | 699880 | N/A | 699880 | 100% | 699880 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Construction Of Boda Boda Sheds-Seacon Enterprises Ltd | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds-Seacon Enterprises Ltd | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 799901 | 799901 | 799901 | County treasury | N/A | 799901 | N/A | 799901 | 100% | 799901 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Market Shed And Water Tank Platform At Kiritiri Market-Kaki Tiles Ltd | construction of market shed and raised platform for intallation of water tank | to provide a sheltered trading area and a reliable water storage for market use | completed market shed and constructed water tank platform | Development | Market Shed And Water Tank Platform At Kiritiri Market-Kaki Tiles Ltd | N/A | Mavuria | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 998957 | 998957 | 998957 | County treasury | N/A | 998957 | N/A | 998957 | 100% | 998957 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Ngiiri Market Shed-Evload Contractors Ltd | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Ngiiri Market Shed-Evload Contractors Ltd | N/A | Muminji | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1999434 | 1999434 | 1999434 | County treasury | N/A | 1999434 | N/A | 1999434 | 100% | 1999434 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Construction Of Siakago Stage Toilet-Seantam And Associates Co. Ltd | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Siakago Stage Toilet-Seantam And Associates Co. Ltd | N/A | Nthawa | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 549659 | 549659 | 549659 | County treasury | N/A | 549659 | N/A | 549659 | 100% | 549659 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Construction Of Market Shed At Riandu,Boda Boda Sheds At Mwondu,Kamburu,Ciambugu And Siakago-Calvidas Merchants Ltd | construction of market and bodaboda shades at designated areas | to provide safe, organized and weather protected spaces for traders and bodaboda operators | completed and functional market and bodaboda shades | Development | Construction Of Market Shed At Riandu,Boda Boda Sheds At Mwondu,Kamburu,Ciambugu And Siakago-Calvidas Merchants Ltd | N/A | Nthawa | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1899989 | 1899989 | 1899989 | County treasury | N/A | 1899989 | N/A | 1899989 | 100% | 1899980 | N/A | 9 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
15 | Installation Of Modern Floodlights In Mashinani | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Modern Floodlights In Mashinani | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1198280 | 1198280 | 1198280 | County treasury | N/A | 1198280 | N/A | 1198280 | 100% | 1198280 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Toilet And Waste Bin At Manyatta Market | construction of public sanitation facility icluding a waste disposal bin | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene, installed waste bin | Development | Construction Of Toilet And Waste Bin At Manyatta Market | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1396700 | 1396700 | 1396700 | County treasury | N/A | 1396700 | N/A | 1396700 | 100% | 1396700 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Installation of 3 Floodlights at Mbeti South | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation of 3 Floodlights at Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 1494578 | 1494578 | 1494578 | County treasury | N/A | 1494578 | N/A | 1494578 | 100% | 1494578 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Installation Of 2 Floodlights at Gatitu and Mwangaza-Nthawa | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of 2 Floodlights at Gatitu and Mwangaza-Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 995930 | 995930 | 995930 | County treasury | N/A | 995930 | N/A | 995930 | 100% | 995930 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Market Maintenance-Kagaari North | routine repair and upkeep of market infrastructure and facility | to ensure a clean, safe and functional market environment | well maintained and operational market facilities | Development | Market Maintenance-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 999630 | 999630 | 999630 | County treasury | N/A | 999630 | N/A | 999630 | 100% | 999630 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
20 | Jua Kali Empowerment Programme-Kirimari | implementation of capacity building and support initiative for jua kali artisians | to enhance skills, productivity, and income oportunities for jua kali operators | empowered jua kali artisians with improved skills and tools | Development | Jua Kali Empowerment Programme-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 900000 | 900000 | 900000 | County treasury | N/A | 900000 | N/A | 900000 | 100% | 899100 | N/A | 900 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
21 | Driving Course For Kirimari Ward | Provision of vocational driving training services to trainees | to equip learners with professional driving skills and certification | trained and certified drivers | Investment | Driving Course For Kirimari Ward | N/A | Kirimari | N/A | Investment | Investment | Investment | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 990000 | 990000 | 990000 | County treasury | N/A | 990000 | N/A | 990000 | 100% | 990000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
22 | Vocational training services; Driving course | Provision of vocational driving training services to trainees | to equip learners with professional driving skills and certification | trained and certified drivers | Investment | Vocational training services; Driving course | N/A | Mavuria | N/A | Investment | Investment | Investment | 2020-07-01 | 2020-07-01 | 2021-06-30 | 2021-06-30 | 495000 | 495000 | 495000 | County treasury | N/A | 495000 | N/A | 495000 | 100% | 495000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2019/2020
1 | Construction Of Market Sheds | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Sheds | N/A | County Wide | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 20000000 | 20000000 | 20000000 | County treasury | N/A | 20000000 | N/A | 20000000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
2 | Construction of a Proposed Market Shed at Mbondoni Makima | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of a Proposed Market Shed at Mbondoni Makima | N/A | Makima | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1989887 | 1989887 | 1989887 | County treasury | N/A | 1989887 | N/A | 1989887 | 100% | 1989887 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Construction of Market Shed at Meka Market Mbeti South. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shed at Meka Market Mbeti South. | N/A | Mbeti South | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 495796 | 495796 | 495796 | County treasury | N/A | 495796 | N/A | 495796 | 100% | 495796 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Construction of Market Shed at Karurina Gaturi South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Mitumba Shed Runyenje Central | N/A | Gaturi South | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1964113 | 1964113 | 1964113 | County treasury | N/A | 1964113 | N/A | 1964113 | 100% | 1964113 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Construction of Mitumba Shed Runyenje Central | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Mitumba Shed Runyenje Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1938186 | 1938186 | 1938186 | County treasury | N/A | 1938186 | N/A | 1938186 | 100% | 1938186 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Boda Boda Sheds-Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds-Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1200000 | 1200000 | 1200000 | County treasury | N/A | 1200000 | N/A | 1200000 | 100% | 299611 | N/A | 900389 | Ongoing | 25% | N/A | N/A | N/A | N/A | N/A
7 | Construction Of Boda Boda Sheds At Mwondu- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Mwondu- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Construction Of Boda Boda Sheds At Kambaru- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Kambaru- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A |  | N/A | N/A
9 | Construction Of Boda Boda Sheds At Magacha- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Magacha- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
10 | Construction Of Boda Boda Sheds At Ciambugu- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Ciambugu- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Boda Boda Sheds At Siakago Stage- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Siakago Stage- Nthawa | N/A |  | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 |  | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Clothes Market Sheds At Kiritiri-Mavuria | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Clothes Market Sheds At Kiritiri-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
13 | Construction Of Machang’a Market Toilet-Mavuria | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Machang’a Market Toilet-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 484416 | N/A | 15584 | Ongoing | 96% | N/A | N/A | N/A | N/A | N/A
14 | Construction Of Boda Boda Sheds -Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds -Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 799901 | N/A | 200099 | Ongoing | 79% | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Market Toilet At Manyatta Market-Ruguru Ngandori | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Manyatta Market-Ruguru Ngandori | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 400000 | 400000 | 400000 | County treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Mega Boda Boda Shed At Kiritiri-Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Mega Boda Boda Shed At Kiritiri-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 998957 | 998957 | 998957 | County treasury | N/A | 998957 | N/A | 998957 | 100% | 998957 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Market Maintenance-Kagaari North | routine repair, cleaning, and upkeep of market facilities | to ensure safe, clean , and functional market environment | well maintained and operational market facilities | Development | Market Maintenance-Kagaari North | N/A | Kirimari | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 999630 | 999630 | 999630 | County treasury | N/A | 999630 | N/A | 999630 | 100% | 999630 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Construction Of Market Toilet At Kianjokoma - Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Kianjokoma - Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 498148 | 498148 | 498148 | County treasury | N/A | 498148 | N/A | 498148 | 100% | 498148 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Construction Of Market Shed At Riandu Market- Nthawa | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Riandu Market- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 899980 | 899980 | 899980 | County treasury | N/A | 899980 | N/A | 899980 | 100% | 899980 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Market Shed At Newsite-Kiambere | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Newsite-Kiambere | N/A | Kiambere | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 999482 | 999482 | 999482 | County treasury | N/A | 999482 | N/A | 999482 | 100% | 999482 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Construction Of Boda Boda Shed At Mutuobare- Kiambere | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Mutuobare- Kiambere | N/A | Kiambere | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
22 | Construction Of Boda Boda Shed At Nthingini-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Nthingini-Mwea | N/A | Mwea | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 249574 | 249574 | 249574 | County treasury | N/A | 249574 | N/A | 249574 | 100% | 249574 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Construction Of Boda Boda Shed At Mugwanjogu Market-Evurore | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Mugwanjogu Market-Evurore | N/A | Evurore | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 198263 | 198263 | 198263 | County treasury | N/A | 198263 | N/A | 198263 | 100% | 198263 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Construction Of Karurumo Market Shed(Joyri Solutions) | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Karurumo Market Shed(Joyri Solutions) | N/A | Kyeni South | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1795664 | 1795664 | 1795664 | County treasury | N/A | 1795664 | N/A | 1795664 | 100% | 1795664 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Construction Of Ngiiri Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Ngiiri Market Shed | N/A | Muminji | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1999434 | 1999434 | 1999434 | County treasury | N/A | 1999434 | N/A | 1999434 | 100% | 1999434 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Roofing Of Mutuobare Market Shed(Vivi Ltd) | installation of roofing for an existing market shed | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing Of Mutuobare Market Shed(Vivi Ltd) | N/A | Kiambere | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 2499394 | 2499394 | 2499394 | County treasury | N/A | 2499394 | N/A | 2499394 | 100% | 2499394 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Construction Of Mbonzuki and Iria Itune Market Toilets-Hasbakari General Supplies | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mbonzuki and Iria Itune Market Toilets-Hasbakari General Supplies | N/A | Mwea | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1197538 | 1197538 | 1197538 | County treasury | N/A | 1197538 | N/A | 1197538 | 100% | 1197538 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Construction Of Bridge At Mwea Game Reserve-Tides Investments | construction of a bridge within the reserve to improve access and connectivity | to facilitate saf and efficient movement of people and vehicles across the reserve | completed and operational bridge at the reserve | Tourism | Construction Of Bridge At Mwea Game Reserve-Tides Investments | N/A | Mwea | N/A | Tourism | Tourism | Tourism | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 3495660 | 3495660 | 3495660 | County treasury | N/A | 3495660 | N/A | 3495660 | 100% | 3495660 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
29 | Construction Of Boda Boda Shed at Mbeti South Ward | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed at Mbeti South Ward | N/A | Mbeti South | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 359979 | 359979 | 359979 | County treasury | N/A | 359979 | N/A | 359979 | 100% | 359979 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Installation and repair of floodlight | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation and repair of floodlight | N/A | County Wide | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 494299 | 494299 | 494299 | County treasury | N/A | 494299 | N/A | 494299 | 100% | 494299 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Completion of Manyatta Market Shed.Ngandori Ward Ruguru. | completion of shaded area in the market | improve market comfort and support efficient trading | market shade completed, improved trading environment | Development | Completion of Manyatta Market Shed.Ngandori Ward Ruguru. | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 3960031 | 3960031 | 3960031 | County treasury | N/A | 3960031 | N/A | 3960031 | 100% | 3960031 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
32 | Maintenance of Mwea Game Reserve Circuit Roads | routine repair and upkeep of circuit roads within the reserve | to ensure safe, smooth and accessible roads for visitors and park operations | well maintained and operational cercuit roads within the reserve | Tourism | Maintenance of Mwea Game Reserve Circuit Roads | N/A | Mwea | N/A | Tourism | Tourism | Tourism | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 3595153 | 3595153 | 3595153 | County treasury | N/A | 3595153 | N/A | 3595153 | 100% | 3595153 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Construction of a Bridge at Mwea Game Reserve | construction of a bridge within the reserve to improve access and connectivity | to facilitate saf and efficient movement of people and vehicles across the reserve | completed and operational bridge at the reserve | Tourism | Construction of a Bridge at Mwea Game Reserve | N/A | Mwea | N/A | Tourism | Tourism | Tourism | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 3882533 | 3882533 | 3882533 | County treasury | N/A | 3882533 | N/A | 3882533 | 100% | 3882533 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
34 | Construction of a Wastebin at Manyatta -Ngandori Ward | construction and installation of waste bins in the designated area | to improve waste management, sanitation , and cleanliness in the community | constructed and functional waste bins intalled at targeted locations | Development | Construction of a Wastebin at Manyatta -Ngandori Ward | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 996700 | 996700 | 996700 | County treasury | N/A | 996700 | N/A | 996700 | 100% | 996700 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
35 | Vocational Training Service-Driving Course | Provision of vocational driving training services to trainees | to equip learners with professional driving skills and certification | trained and certified drivers | Investment | Vocational Training Service-Driving Course | N/A | County Wide | N/A | Investment | Investment | Investment | 01/72019 | 01/72019 | 2020-06-30 | 2020-06-30 | 1990000 | 1990000 | 1990000 | County treasury | N/A | 1990000 | N/A | 1990000 | 100% | 1990000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2018/2019
1 | Driving License (Boda Boda) Programme-Ruguru Ngandori | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving License (Boda Boda) Programme-Ruguru Ngandori | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 498000 | N/A | 2000 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
2 | Driving License Programme-Kirimari | provision of driving training and facilitation of driving license acquisition | to promote road safety and ensure legal compliance among drivers | trained and licensed drivers | Investment | Driving License Programme-Kirimari | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 600000 | 600000 | 600000 | County treasury | N/A | 600000 | N/A | 600000 | 100% | 592000 | N/A | 8000 | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A
3 | Tents And Chairs For Special Groups-Muminji | supply and distribution of tents and chairs to special groups | to support social, economic and community activities of special groups | tents and chairs supplied to targeted special groups | Development | Tents And Chairs For Special Groups-Muminji | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 450000 | 450000 | 450000 | County treasury | N/A | 450000 | N/A | 450000 | 100% | 994500 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Boda Boda Licences-Mavuria | facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Licences-Mavuria | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 800000 | 800000 | 800000 | County treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Boda Boda Driving Courses-Nthawa | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Driving Courses-Nthawa | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 798000 | 798000 | 798000 | County treasury | N/A | 798000 | N/A | 798000 | 100% | 798000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Tents(2x100 Seater) And Chairs (150)To Special Group(Kinyaga Welfare And Orphans)-Kiambere | supply and distribution of tents and chairs to special groups | to support social, economic and community activities of special groups | tents and chairs supplied to targeted special groups | Development | Tents(2x100 Seater) And Chairs (150)To Special Group(Kinyaga Welfare And Orphans)-Kiambere | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 495000 | 495000 | 495000 | County treasury | N/A | 495000 | N/A | 495000 | 100% | 495000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Driving Course-Gaturi South | provision of driving training and facilitation of driving license acquisition | to promote road safety and ensure legal compliance among drivers | trained and licensed drivers | Investment | Driving Course-Gaturi South | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Driving Course-Kyeni South | provision of driving training and facilitation of driving license acquisition | to promote road safety and ensure legal compliance among drivers | trained and licensed drivers | Investment | Driving Course-Kyeni South | N/A | N/A | N/A | Investment | Investment | Investment | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Boda Boda Empowerment Programme (Reflector Jackets)-Kirimari | procurement and distribution of reflector jackets to bodaboda operators | to enhance visibility safety and complience with road safety regulations | reflector jackets issued to bodaboda riders | Development | Boda Boda Empowerment Programme (Reflector Jackets)-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 350000 | 350000 | 350000 | County treasury | N/A | 350000 | N/A | 350000 | 100% | 350000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Development Of Mwea Game Reserve | implementation of infrastructure and facility improvements within the reserve | to enhance conservation, tourism and visitor experience | improved and developed facilities within the reserve | Development | Development Of Mwea Game Reserve | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 4498618 | 4498618 | 4498618 | County treasury | N/A | 4498618 | N/A | 4498618 | 100% | 4498618 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Market Shed At Karaba-Mwea | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Karaba-Mwea | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | 999328 | N/A | 500672 | Ongoing | 66% | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Gategi Market Toilet-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Gategi Market Toilet-Mwea | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 499728 | N/A | 272 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
13 | Construction Of Miraa Shed At Muraru Market-Mbeti South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Miraa Shed At Muraru Market-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
14 | Construction Of Miraa Shed At Gachuriri Market-Mbeti South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Miraa Shed At Gachuriri Market-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Toilet At Gachoka-Gachuriri Junction- Mbeti South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Gachoka-Gachuriri Junction- Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 499496 | N/A | 504 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Toilet At Meka Market - Mbeti South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Meka Market - Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 500000 | 500000 | 500000 | County treasury | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
17 | Completion Of Muraru Market Toilets-Mbeti South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Completion Of Muraru Market Toilets-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 299,959 | 299,959 | 299,959 | County treasury | N/A | 299,959 | N/A | 299,959 | 100% | 299,959 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Construction Of Boda Boda Sheds –Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds –Mbeti South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 |  |  |  | County treasury | N/A |  | N/A |  |  |  | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
19 | Construction Of A Boda Boda Shed At Mariari Market-Kiambere | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of A Boda Boda Shed At Mariari Market-Kiambere | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 250000 | 250000 | 250000 | County treasury | N/A | 250000 | N/A | 250000 | 100% | 242881 | N/A | 7119 | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Mitumba Sheds At Karingari Market-Gaturi South | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Mitumba Sheds At Karingari Market-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
21 | Construction Of An Enforcement Centre At Ugweri Market-Kagaari South | construction of a facility to support enforcement and regulatory operations | to enhance law enforcement efficiency and service delivery | completed and operational enforcement center | Development | Construction Of An Enforcement Centre At Ugweri Market-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 3550000 | 3550000 | 3550000 | County treasury | N/A | 3550000 | N/A | 3550000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
22 | Construction Of Jua Kali Artisans Sheds And Toilet-Kithimu | construction of shaded areas for jua kali artisians and a public sanitation facility | to provide safe and organized working environment for jua kali artisans and promote good hygiene | completed and functional jua kali shade, public toilet constructed | Development | Construction Of Jua Kali Artisans Sheds And Toilet-Kithimu | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 1898932 | N/A | 101068 | Ongoing | 94% | N/A | N/A | N/A | N/A | N/A
23 | Construction Of Bus Park Toilet-Mavuria | construction of toilet facilities within the bus park | to improve sanitation and hygiene for passengers and operators | completed and functional buspark toilet facility | Development | Construction Of Bus Park Toilet-Mavuria | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499832 | 499832 | 499832 | County treasury | N/A | 499832 | N/A | 499832 | 100% | 499832 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Bus Park Levelling -Mavuria | earthworks and levelling of bus parks | to create safe, stable and well drained surface for public transport operations | leveled and usable bus park area | Development | Bus Park Levelling -Mavuria | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499264 | 499264 | 499264 | County treasury | N/A | 499264 | N/A | 499264 | 100% | 499264 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Installation Of Floodlight At Kauraciri-Mavuria | installation of floodlights at specific areas | to enhance security and operational efficiency in the market | floodlights installed and maintained, improved market visibility and safety, enhanced market operations | Development | Installation Of Floodlight At Kauraciri-Mavuria | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 476939 | 476939 | 476939 | County treasury | N/A | 476939 | N/A | 476939 | 100% | 476939 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Proposed Roofing Of New Soko Mjinga Market - Behind Naivas - 1st Payment | installation of roofing for an existing market shed | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Proposed Roofing Of New Soko Mjinga Market - Behind Naivas - 1st Payment | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2498732 | 2498732 | 2498732 | County treasury | N/A | 2498732 | N/A | 2498732 | 100% | 2498732 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Proposed Construction Of Kirimari Market Mitumba Shed - 1st Payment | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Proposed Construction Of Kirimari Market Mitumba Shed - 1st Payment | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2499684 | 2499684 | 2499684 | County treasury | N/A | 2499684 | N/A | 2499684 | 100% | 2499684 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Constrcution of 2 No. Boda Boda Sheds at Kimangaru and Gatunduri-Mbeti North Ward | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Constrcution of 2 No. Boda Boda Sheds at Kimangaru and Gatunduri-Mbeti North Ward | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499980 | 499980 | 499980 | County treasury | N/A | 499980 | N/A | 499980 | 100% | 499980 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
29 | Installation Of Electricity At Gategi And Makutano Markets | installation and upgrading of electrical systems at the market | to provide reliable and safe power supply for market activities | electrical systems intalled, reliable power supply established, improved market operations | Development | Installation Of Electricity At Gategi And Makutano Markets | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 449287 | 449287 | 449287 | County treasury | N/A | 449287 | N/A | 449287 | 100% | 449287 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Renovation works of a toilet block at Makutano market-Mwea ward | renovation of public sanitation facility | enhance public health and sanitation standerds | public toilet renovated, improved sanitation and hygiene | Development | Renovation works of a toilet block at Makutano market-Mwea ward | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 299950 | 299950 | 299950 | County treasury | N/A | 299950 | N/A | 299950 | 100% | 299950 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Construction of a market shed at Kanyuambora market | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of a market shed at Kanyuambora market | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2498344 | 2498344 | 2498344 | County treasury | N/A | 2498344 | N/A | 2498344 | 100% | 2498344 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
32 | Construction of a toilet block at siakago market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of a toilet block at siakago market | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 453113 | 453113 | 453113 | County treasury | N/A | 453113 | N/A | 453113 | 100% | 453113 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Proposed construction of 2 No. Bodaboda Sheds at Kiogogo & Kwamukiria | shaded areas for bodaboda riders | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Proposed construction of 2 No. Bodaboda Sheds at Kiogogo & Kwamukiria | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499940 | 499940 | 499940 | County treasury | N/A | 499940 | N/A | 499940 | 100% | 499940 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
34 | Construction Of Karingari Market Shed –Gaturi South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Karingari Market Shed –Gaturi South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1997845 | 1997845 | 1997845 | County treasury | N/A | 1997845 | N/A | 1997845 | 100% | 1997845 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
35 | Installation Of Market Flood Light At Minandari-Gaturi South | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Market Flood Light At Minandari-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499750 | 499750 | 499750 | County treasury | N/A | 499750 | N/A | 499750 | 100% | 499750 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
36 | Installation Of Flood Lights At Dubai Market-Gaturi South | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Lights At Dubai Market-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499750 | 499750 | 499750 | County treasury | N/A | 499750 | N/A | 499750 | 100% | 499750 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
37 | Installation Of Flood Lights At Kairungu Market-Gaturi South | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Flood Lights At Kairungu Market-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499755 | 499755 | 499755 | County treasury | N/A | 499755 | N/A | 499755 | 100% | 499755 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
38 | Construction Of Siakago Market Sheds-Nthawa | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Siakago Market Sheds-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2991547 | 2991547 | 2991547 | County treasury | N/A | 2991547 | N/A | 2991547 | 100% | 2991547 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
39 | Construction Of Ngiiri Market Sheds-Muminji | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Ngiiri Market Sheds-Muminji | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 983726 | 983726 | 983726 | County treasury | N/A | 983726 | N/A | 983726 | 100% | 983726 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
40 | Construction Of Shoe Shine Shed-Kirimari | construction of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Construction Of Shoe Shine Shed-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1499996 | 1499996 | 1499996 | County treasury | N/A | 1499996 | N/A | 1499996 | 100% | 1499996 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
41 | Construction Of Jua Kali Books Vendor Sheds-Kirimari | construction of shaded areas for jua kali artisians | to provide safe and organized working environment for jua kali artisians | completed and functional jua kali shade | Development | Construction Of Jua Kali Books Vendor Sheds-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 599082 | 599082 | 599082 | County treasury | N/A | 599082 | N/A | 599082 | 100% | 599082 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
42 | Construction Of Hawkers Market-Kirimari | construction of organized stalls | improned trading conditions and support snall scale traders | hawkers stalls constructed, improved trading organisation | Development | Construction Of Hawkers Market-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 3499989 | 3499989 | 3499989 | County treasury | N/A | 3499989 | N/A | 3499989 | 100% | 3499989 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
43 | Construction Of Toilet At Mitumba Market-Kirimari | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Mitumba Market-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 998703 | 998703 | 998703 | County treasury | N/A | 998703 | N/A | 998703 | 100% | 998703 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
44 | Renovation Of Existing Shoe Shiner Shed-Kirimari | renovation of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Renovation Of Existing Shoe Shiner Shed-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 249406 | 249406 | 249406 | County treasury | N/A | 249406 | N/A | 249406 | 100% | 249406 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
45 | Construction Of Hawkers Shed At Kyeni Hotel | construction of hawkers shed at the specified area | improned trading conditions and support snall scale traders | hawkers shed constructed, improved trading organisation | Development | Construction Of Hawkers Shed At Kyeni Hotel | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 799066 | 799066 | 799066 | County treasury | N/A | 799066 | N/A | 799066 | 100% | 799066 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
46 | Construction Of Boda Boda Sheds At Mama Ngina Street Junction-Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Mama Ngina Street Junction-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 799959 | 799959 | 799959 | County treasury | N/A | 799959 | N/A | 799959 | 100% | 799959 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
47 | Construction Of Mukono Miraa Shed-Nthawa | shaded areas for miraa operators | safe and comfortable environment for miraa traders | shed constructed, improved trading organization | Development | Construction Of Mukono Miraa Shed-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 798312 | 798312 | 798312 | County treasury | N/A | 798312 | N/A | 798312 | 100% | 798312 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
48 | Construction Of Siakago Stage Shoe Shine Shed-Nthawa | construction of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Construction Of Siakago Stage Shoe Shine Shed-Nthawa | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 797744 | 797744 | 797744 | County treasury | N/A | 797744 | N/A | 797744 | 100% | 797744 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
49 | Construction Of Toilet At Kilia,Kamingo And Kaduzoh Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Kilia,Kamingo And Kaduzoh Mwea | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499937 | 499937 | 499937 | County treasury | N/A | 499937 | N/A | 499937 | 100% | 499937 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
50 | Construction Of Market Toilet At Mbonzuki-Mwea-Boden Contractors Ltd | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Mbonzuki-Mwea-Boden Contractors Ltd | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 497849 | 497849 | 497849 | County treasury | N/A | 497849 | N/A | 497849 | 100% | 497849 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
51 | Fencing Of Rukira Market-Kithimu | fencing of the specifie market area | to organize safe working environment in the market | market fenced, security of traders improved | Development | Fencing Of Rukira Market-Kithimu | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 996672 | 996672 | 996672 | County treasury | N/A | 996672 | N/A | 996672 | 100% | 996672 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
52 | Construction Of Market Shed At Ishiara-Evurore | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Ishiara-Evurore | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2445837 | 2445837 | 2445837 | County treasury | N/A | 2445837 | N/A | 2445837 | 100% | 2445837 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
53 | Construction Of Boda Boda Sheds At Mukono And Mbuga-Nthawa-Seacon Enterprises | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Mukono And Mbuga-Nthawa-Seacon Enterprises | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499944 | 499944 | 499944 | County treasury | N/A | 499944 | N/A | 499944 | 100% | 499944 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
54 | Construction Of Mbui Njeru Market Toilet-Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mbui Njeru Market Toilet-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 |  |  |  | County treasury | N/A |  | N/A |  |  |  | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
55 | Construction Of Mukuuri Market Toilet-Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mukuuri Market Toilet-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 496398 | 496398 | 496398 | County treasury | N/A | 496398 | N/A | 496398 | 100% | 496398 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
56 | Construction Of Market Shed Kanyuambora-Evurore | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed Kanyuambora-Evurore | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2244693 | 2244693 | 2244693 | County treasury | N/A | 2244693 | N/A | 2244693 | 100% | 2244693 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
57 | Roofing Of The Green Market-Kirimari | roofing for an existing market | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing Of The Green Market-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 3690060 | 3690060 | 3690060 | County treasury | N/A | 3690060 | N/A | 3690060 | 100% | 3690060 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
58 | Completion Of Mitumba Market-Kirimari | completion of the existing mitumba market | improve market comfort and support efficient trading | mitumba market completed, improved trading environment | Development | Completion Of Mitumba Market-Kirimari | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 3498038 | 3498038 | 3498038 | County treasury | N/A | 3498038 | N/A | 3498038 | 100% | 3498038 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
59 | Construction Of Karurumo Market Toilets-Kyeni South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Karurumo Market Toilets-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 499664 | 499664 | 499664 | County treasury | N/A | 499664 | N/A | 499664 | 100% | 499664 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
60 | Roofing Of Soko Mjinga Behind Naivas | roofing for an existing market | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing Of Soko Mjinga Behind Naivas | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 498960 | 498960 | 498960 | County treasury | N/A | 498960 | N/A | 498960 | 100% | 498960 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
61 | Construction Of New Soko Mjinga Behind Naivas | construction of the new market in the specified area | improved market environment to support small businesses | new market constructed | Development | Construction Of New Soko Mjinga Behind Naivas | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 1899877 | 1899877 | 1899877 | County treasury | N/A | 1899877 | N/A | 1899877 | 100% | 1899877 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
62 | Construction Of Market Shed At Kanyuambora | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Kanyuambora | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2043920 | 2043920 | 2043920 | County treasury | N/A | 2043920 | N/A | 2043920 | 100% | 2043920 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
63 | Rehabilitation of Boundary Wall at Embu Green Market | rehabilitation of boundary wall and upgrading of the market | to enhance market infrastructure and support efficient trade and security | market boundary wallrehabilitated, improved trading security and increased market efficiency | Development | Rehabilitation of Boundary Wall at Embu Green Market | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 980009 | 980009 | 980009 | County treasury | N/A | 980009 | N/A | 980009 | 100% | 980009 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
64 | Construction of Ishiara Livestock Market Sheds-Evurore | construction of shaded area in the livestock market | improve market comfort and support efficient trading | livestock market shade constructed, improved trading environment | Development | Construction of Ishiara Livestock Market Sheds-Evurore | N/A | N/A | N/A | Development | Development | Development | 2018-07-01 | 2018-07-01 | 2019-06-30 | 2019-06-30 | 2485358 | 2485358 | 2485358 | County treasury | N/A | 2485358 | N/A | 2485358 | 100% | 2485358 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2017/2018
1 | Class I(Machine Operator)-Mavuria | skilled personnel for operating machinery | to operate and maintain merchinery equipment to support project implementation | fully and operational machine operator | Investment | Class I(Machine Operator)-Mavuria | N/A | Mavuria | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
2 | Driving Licenses (Boda Boda and Vehicles For 150 Students)-Evurore | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving Licenses (Boda Boda and Vehicles For 150 Students)-Evurore | N/A | Evurore | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1450000 | 1450000 | 1450000 | County secretary | N/A | 1450000 | N/A | 1450000 | 100% | 1440000 | N/A | 10000 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
3 | Driving Licenses (Boda Boda and Vehicles)-Kagaari North | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving Licenses (Boda Boda and Vehicles)-Kagaari North | N/A | Kagaari North | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1000000 | 1000000 | 1000000 | County secretary | N/A | 1000000 | N/A | 1000000 | 100% | 992200 | N/A | 7800 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
4 | Driving Course-Gaturi North | provision of driving training and facilitation of driving license acquisition | to promote road safety and ensure legal compliance among drivers | trained and licensed drivers | Investment | Driving Course-Gaturi North | N/A | Gaturi North | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1000000 | 1000000 | 1000000 | County secretary | N/A | 1000000 | N/A | 1000000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
5 | Empowerment Programme (Motorbikes)-Gaturi North | procurement and distribution of reflector jackets to bodaboda operators | to enhance visibility safety and complience with road safety regulations | reflector jackets issued to bodaboda riders | Investment | Empowerment Programme (Motorbikes)-Gaturi North | N/A | Gaturi North | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1000000 | 1000000 | 1000000 | County secretary | N/A | 1000000 | N/A | 1000000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
6 | Driving Course-Kyeni South | provision of driving training and facilitation of driving license acquisition | to promote road safety and ensure legal compliance among drivers | trained and licensed drivers | Investment | Driving Course-Kyeni South | N/A | Kyeni South | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2190000 | 2190000 | 2190000 | County secretary | N/A | 2190000 | N/A | 2190000 | 100% | 1190000 | N/A | 1000000 | Ongoing | 54% | N/A | N/A | N/A | N/A | N/A
7 | Driving Licenses (Boda Boda)-Kirimari | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving Licenses (Boda Boda)-Kirimari | N/A | Kirimari | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 600000 | 600000 | 600000 | County secretary | N/A | 600000 | N/A | 600000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
8 | Driving Licenses (Boda Boda)-Mbeti North. | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving Licenses (Boda Boda)-Mbeti North. | N/A | Mbeti North | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 994000 | 994000 | 994000 | County secretary | N/A | 994000 | N/A | 994000 | 100% | 994000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Driving Licenses (Boda Boda)-Gaturi South | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Driving Licenses (Boda Boda)-Gaturi South | N/A | Gaturi South | N/A | Investment | Investment | Investment | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1500000 | 1500000 | 1500000 | County secretary | N/A | 1500000 | N/A | 1500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
10 | Maintenance of Markets | routine maintainance of markets | to improve the conditions and usability of market facilities through regular maintenance | market facilities maintained and repaired | Development | Maintenance of Markets | N/A | County Wide | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1300000 | 1300000 | 1300000 | County secretary | N/A | 1300000 | N/A | 1300000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
11 | Construction of Market Sheds at Kanyuambora | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds at Kanyuambora | N/A | Evurore | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2500000 | 2500000 | 2500000 | County secretary | N/A | 2500000 | N/A | 2500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Boda Boda Sheds -Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds -Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
13 | Construction Of Market Toilet At Wango-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Wango-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
14 | Construction Of Market Toilet At Kilia-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Kilia-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Market Toilet At Mbonzuki-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Mbonzuki-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
16 | Construction of Boda Boda Sheds At Kamviu,Kibugua,Kiriari,Kithunguriri,Keria And Gaciigi-Ruguru Ngandori | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds At Kamviu,Kibugua,Kiriari,Kithunguriri,Keria And Gaciigi-Ruguru Ngandori | N/A | Ruguru-Ngandori | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 600000 | 600000 | 600000 | County secretary | N/A | 600000 | N/A | 600000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
17 | Construction Of Market Shed At Miandari-Kagaari North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Miandari-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2000000 | 2000000 | 2000000 | County secretary | N/A | 2000000 | N/A | 2000000 | 100% | 1999997 | N/A | 3 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
18 | Construction Of Boda Boda Shed At Mwanzo-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Mwanzo-Makima | N/A | Makima | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 120000 | 120000 | 120000 | County secretary | N/A | 120000 | N/A | 120000 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
19 | Roofing Of The Green Market-Kirimari | roofing for an existing market | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing Of The Green Market-Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 4239027 | 4239027 | 4239027 | County secretary | N/A | 4239027 | N/A | 4239027 | 100% | 0 | N/A |  |  |  | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Rukira Open Air Market Sheds, Toilet And Fencing-Kithimu | construction of open air market sheds a public toilet and perimeter fencing at kithimu market | to enhance market infrastructure by providing aadequate trading space proper sanitation and improved security | open air market sheds constructed, public toilet facility built, perimeter fencing installed | Development | Construction Of Rukira Open Air Market Sheds, Toilet And Fencing-Kithimu | N/A | Kithimu | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 4000000 | 4000000 | 4000000 | County secretary | N/A | 4000000 | N/A | 4000000 | 100% | 3299028 | N/A | 700972 | Ongoing | 82% | N/A | N/A | N/A | N/A | N/A
21 | Roofing Of Mutuobare Market-Kiambere | roofing for an existing market | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing Of Mutuobare Market-Kiambere | N/A | Kiambere | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2800000 | 2800000 | 2800000 | County secretary | N/A | 2800000 | N/A | 2800000 | 100% | 2799486 | N/A | 514 | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A
22 | Completion Of Toilet At Kianjokoma-Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Completion Of Toilet At Kianjokoma-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1000000 | 1000000 | 1000000 | County secretary | N/A | 1000000 | N/A | 1000000 | 100% | 1451682 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Completion Of Siakago Toilet | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Completion Of Siakago Toilet | N/A | Nthawa | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 453113 | 453113 | 453113 | County secretary | N/A | 453113 | N/A | 453113 | 100% | 453113 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Construction Of Toilet Block At Ishiara Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet Block At Ishiara Market | N/A | Evurore | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 499947 | 499947 | 499947 | County secretary | N/A | 499947 | N/A | 499947 | 100% | 499947 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Installation Of Market Floodlight At Kavutiri Market | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation Of Market Floodlight At Kavutiri Market | N/A | Gaturi North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 488376 | 488376 | 488376 | County secretary | N/A | 488376 | N/A | 488376 | 100% | 488376 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Construction Of Makutano ESP Market Phase 2 | construction of the specified market phase 2 | to enhance market capacity and functionality through the development | makutano ESP market constructed | Development | Construction Of Makutano ESP Market Phase 2 | N/A | Kyeni North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 499960 | 499960 | 499960 | County secretary | N/A | 499960 | N/A | 499960 | 100% | 499960 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Completion Of Muraru Market Toilet | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Completion Of Muraru Market Toilet | N/A | Mbeti South | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 499925 | 499925 | 499925 | County secretary | N/A | 499925 | N/A | 499925 | 100% | 499925 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Construction Of Bus Stage shed At Ishiara Market | construction of bus stage shed at the specified area | to enhance public transport infrastructure by providing safe and weather protected waiting space for passengers | bus stage shed constructed | Development | Construction Of Bus Stage shed At Ishiara Market | N/A | Evurore | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 610000 | 610000 | 610000 | County secretary | N/A | 610000 | N/A | 610000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
29 | Construction Of Market Shed At Mbeti North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Mbeti North | N/A | Mbeti North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 366000 | 366000 | 366000 | County secretary | N/A | 366000 | N/A | 366000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
30 | Construction Of Market shed At Ishiara | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market shed At Ishiara | N/A | Evurore | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2539000 | 2539000 | 2539000 | County secretary | N/A | 2539000 | N/A | 2539000 |  | 3099961 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
31 | Construction Of Perimeter Wall At Kiritiri Market Phase 2 | construction of perimeter wall at the market to enhance security | to improve security and control access to the market through completion of the perimeter wall | perimeter wall constructed | Development | Construction Of Perimeter Wall At Kiritiri Market Phase 2 | N/A | Mavuria | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 1200000 | 1200000 | 1200000 | County secretary | N/A | 1200000 | N/A | 1200000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
32 | Construction Of Kirimari Mitumba Sheds Phase 2 | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Kirimari Mitumba Sheds Phase 2 | N/A | Kirimari | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 2499684 | 2499684 | 2499684 | County secretary | N/A | 2499684 | N/A | 2499684 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
33 | Construction Of Boda Boda sheds At Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda sheds At Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 481075 | N/A | 18925 | Ongoing |  | N/A | N/A | N/A | N/A | N/A
34 | Construction of Market Toilet At Mbui Njeru-Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilet At Mbui Njeru-Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 500000 | 500000 | 500000 | County secretary | N/A | 500000 | N/A | 500000 | 100% | 999985 | N/A | N/A | Completed |  | N/A | N/A | N/A | N/A | N/A
35 | Renovation Of Market Toilet At Makutano-Mwea | Renovation of public sanitation facility | enhance public health and sanitation standerds | public toilet renovated, improved sanitation and hygiene | Development | Renovation Of Market Toilet At Makutano-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2017-07-01 | 2017-07-01 | 31/06/2018 | 31/06/2018 | 300000 | 300000 | 300000 | County secretary | N/A | 300000 | N/A | 300000 | 100% | 0 | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A
2016/2017
1 | Boda Boda youth driving licence project-Gaturi North | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda youth driving licence project-Gaturi North | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 6994000 | 1 |  | County treasury | N/A | 6994000 | N/A |  | 0% | 0 |  |  | Ongoing |  | N/A | N/A | N/A | N/A | N/A
2 | Boda Boda Youth Driving Licence Project-Mbeti South | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Youth Driving Licence Project-Mbeti South | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 900000 |  |  | County treasury | N/A | 900000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
3 | Boda Boda Youth Driving Licence Project-Mwea | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Youth Driving Licence Project-Mwea | N/A | N/A | N/A | Investment |  |  | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1998000 |  |  | County treasury | N/A | 1998000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
4 | Boda Boda Youth Driving Licence Project – Kagaari North | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Youth Driving Licence Project – Kagaari North | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1498000 |  |  | County treasury | N/A | 1498000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
5 | Boda Boda Youth Driving Licence Project – Kyeni South | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Youth Driving Licence Project – Kyeni South | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1500000 |  |  | County treasury | N/A | 1500000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
6 | Boda Boda Youth Driving Licence Project – mbeti North | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Boda Boda Youth Driving Licence Project – mbeti North | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
7 | Construction of Toilets Plus drainage at Karurina Market | construction of public sanitation facility and drainage | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilets Plus drainage at Karurina Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
8 | Construction of Toilet-Mukuuri Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet-Mukuuri Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
9 | Construction of Newsite Public Toilet-Kiambere | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Newsite Public Toilet-Kiambere | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499746.55 |  |  | County treasury | N/A | 499746.55 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
10 | Construction of Nembure Bus Stage waiting Shed-Gaturi South | construction of bus stage shed at the specified area | to enhance public transport infrastructure by providing safe and weather protected waiting space for passengers | bus stage shed constructed | Development | Construction of Nembure Bus Stage waiting Shed-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1094054.8 |  |  | County treasury | N/A | 1094054.8 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
11 | Construction of Kivwe Bus Stage waiting Shed-Gaturi South | construction of bus stage shed at the specified area | to enhance public transport infrastructure by providing safe and weather protected waiting space for passengers | bus stage shed constructed | Development | Construction of Kivwe Bus Stage waiting Shed-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 599852 |  |  | County treasury | N/A | 599852 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
12 | Construction of Market Toilets-Mbeti South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilets-Mbeti South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1000000 |  |  | County treasury | N/A | 1000000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
13 | Construction of Market Toilet at Nthingini-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilet at Nthingini-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
14 | Construction of Market Toilet at Mbonzuki Dispensary-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilet at Mbonzuki Dispensary-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1197537.6 |  |  | County treasury | N/A | 1197537.6 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
15 | Construction of Market Toilet at Iria-Itune-Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilet at Iria-Itune-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
16 | Construction of Makima Market Drainage-Makima | construction of drainage at the market | enhance public health and sanitation standerds | drainage constructed, improved sanitation and hygiene | Development | Construction of Makima Market Drainage-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1999849.15 |  |  | County treasury | N/A | 1999849.15 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
17 | Construction of Mbondoni Market Toilet-Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Mbondoni Market Toilet-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 999989.5 |  |  | County treasury | N/A | 999989.5 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
18 | Construction of Mwanzo Market Toilet-Makima | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Mwanzo Market Toilet-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499878.8 |  |  | County treasury | N/A | 499878.8 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
19 | Construction of Kiriari and Kithunguriri Market Toilets-Ruguru Ngandori | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Kiriari and Kithunguriri Market Toilets-Ruguru Ngandori | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1199962 |  |  | County treasury | N/A | 1199962 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
20 | Construction of Market Toilet(Mitumba)-Kirimari | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Market Toilet(Mitumba)-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 4497445 |  |  | County treasury | N/A | 4497445 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
21 | Gutters and Drainage at Kithimu Open Air Market | construction of gutters and drainage at the market | enhance public health and sanitation standerds | drainage and gutters constructed | Development | Gutters and Drainage at Kithimu Open Air Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 600000 |  |  | County treasury | N/A | 600000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
22 | Construction of Soko Mjinga Toilet-Evurore | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Soko Mjinga Toilet-Evurore | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1047663.1 |  |  | County treasury | N/A | 1047663.1 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
23 | Construction of Toilet Block at Ishiara Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet Block at Ishiara Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499947.24 |  |  | County treasury | N/A | 499947.24 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
24 | Construction of Toilet Block at Wakaria Market Mwea | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet Block at Wakaria Market Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
25 | Completion of Kanyariri Toilet Mbeti South | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Completion of Kanyariri Toilet Mbeti South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
26 | Construction of market toilet at Ena | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Modern market toilet at Majimbo-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499873 |  |  | County treasury | N/A | 499873 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
27 | Construction of Modern market toilet at Majimbo-Mbeti North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Modern market toilet at Majimbo-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499960 |  |  | County treasury | N/A | 499960 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
28 | Construction of Modern market toilet at Kambo-Mbeti North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Modern market toilet at Kambo-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499960 |  |  | County treasury | N/A | 499960 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
29 | Construction of Modern market toilet at Kimangaru-Mbeti North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Modern market toilet at Kimangaru-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499960 |  |  | County treasury | N/A | 499960 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
30 | Construction of Modern Shoe Shiner Stalls-Co-operative Bank | construction of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Construction of Modern Shoe Shiner Stalls-Co-operative Bank | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 531250 |  |  | County treasury | N/A | 531250 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
31 | Construction of Modern Shoe Shiner Shades-Kirimari | construction of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Construction of Modern Shoe Shiner Shades-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 3849953 |  |  | County treasury | N/A | 3849953 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
32 | Construction of Karingari market sheds | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Karingari market sheds | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1449603.5 |  |  | County treasury | N/A | 1449603.5 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
33 | Construction of Mukuuri market shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Mukuuri market shed | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1299986.9 |  |  | County treasury | N/A | 1299986.9 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
34 | Construction of Kathanjuri Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Kathanjuri Market Shed | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 699920 |  |  | County treasury | N/A | 699920 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
35 | Construction of Market Sheds in Runyenjes | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds in Runyenjes | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2999939 |  |  | County treasury | N/A | 2999939 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
36 | Erection of LED floodlights at Gitare Markets | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Erection of LED floodlights at Gitare Markets | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 770 |  |  | County treasury | N/A | 770 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
37 | Construction of Ishiara Market Shed-Retention | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Ishiara Market Shed-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 199990.7 |  |  | County treasury | N/A | 199990.7 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
38 | Construction of Majimbo Market Shed-Retention | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Majimbo Market Shed-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 228000 |  |  | County treasury | N/A | 228000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
39 | Construction of Manyatta Market Shed-Retention | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Manyatta Market Shed-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 199968.1 |  |  | County treasury | N/A | 199968.1 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
40 | Construction of Manyatta Market Shed at Kianjokoma Market-Retention | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Manyatta Market Shed at Kianjokoma Market-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 199999.1 |  |  | County treasury | N/A | 199999.1 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
41 | Roofing of Embu Mitumba stalls-Kirimari | roofing for an existing mitumba stalls | to protect traders and goods from weather elements | roofed and weather protected mitumba shed | Development | Roofing of Embu Mitumba stalls-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 18752688.2 |  |  | County treasury | N/A | 18752688.2 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
42 | Construction of Embu Hawker's stalls-Kirimari | construction of organized stalls | improned trading conditions and support snall scale traders | hawkers stalls constructed, improved trading organisation | Development | Construction of Embu Hawker's stalls-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1998726.4 |  |  | County treasury | N/A | 1998726.4 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
43 | Markets Infrastructure Maintenance | routine repair, cleaning, and upkeep of market facilities | to ensure safe, clean , and functional market environment | well maintained and operational market facilities | Development | Markets Infrastructure Maintenance | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
44 | Boda Boda Shed-Ena | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Boda Boda Shed-Ena | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
45 | Construction of Boda Boda Shed-Issaco-Kiambere | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed-Issaco-Kiambere | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
46 | Construction of Boda Boda Shed-Karura-Kiambere | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed-Karura-Kiambere | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
47 | Construction of Boda Boda Sheds at Gatunduri and Kairungu-Gaturi South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds at Gatunduri and Kairungu-Gaturi South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 299378.31 |  |  | County treasury | N/A | 299378.31 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
48 | Construction of Boda Boda Shed at Iria-Itune Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Iria-Itune Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 150000 |  |  | County treasury | N/A | 150000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
49 | Construction of Boda Boda Shed at Kikumini Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Kikumini Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 150000 |  |  | County treasury | N/A | 150000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
50 | Construction of Boda Boda Shed at Gitaraka Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Gitaraka Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 150000 |  |  | County treasury | N/A | 150000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
51 | Construction of Boda Boda Shed at Mbonzuki Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Mbonzuki Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 149271.75 |  |  | County treasury | N/A | 149271.75 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
52 | Construction of Boda Boda Shed at Gategi Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Gategi Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 150000 |  |  | County treasury | N/A | 150000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
53 | Construction of Boda Boda Shed at Karuku Market-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Karuku Market-Mwea | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 149437 |  |  | County treasury | N/A | 149437 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
54 | Construction of Boda Boda Shed at Ndune-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Ndune-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 100000 |  |  | County treasury | N/A | 100000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
55 | Construction of Boda Boda Shed at Kakawa-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Kakawa-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 100000 |  |  | County treasury | N/A | 100000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
56 | Construction of Boda Boda Shed at Kitoloni-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Kitoloni-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 99571.6 |  |  | County treasury | N/A | 99571.6 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
57 | Construction of Boda Boda Shed at Gikuri-Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Gikuri-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
58 | Construction of Boda Boda Shed at Karurumo-Kyeni South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Karurumo-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 99433.8 |  |  | County treasury | N/A | 99433.8 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
59 | Construction of Boda Boda Shed at Kathanjuri -Kyeni South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Kathanjuri -Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 100000 |  |  | County treasury | N/A | 100000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
60 | Construction of Boda Boda Shed at Kathunguri -Kyeni South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Kathunguri -Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 100000 |  |  | County treasury | N/A | 100000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
61 | Construction of Boda Boda Sheds at Kirigi, Mukangu,Kiriari and Kithunguriri-Ruguru Ngandori | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds at Kirigi, Mukangu,Kiriari and Kithunguriri-Ruguru Ngandori | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 27408 |  |  | County treasury | N/A | 27408 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
62 | Uograding Of Karurumo Market-Kyeni South | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Uograding Of Karurumo Market-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1498819.6 |  |  | County treasury | N/A | 1498819.6 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
63 | Upgrading Of Kathunguri Market-Kyeni South | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Upgrading Of Kathunguri Market-Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
64 | Construction of Market Sheds-Mbuvori-Nginda | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds-Mbuvori-Nginda | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 998671.95 |  |  | County treasury | N/A | 998671.95 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
65 | Construction of Boda Boda Sheds at Kathangari and Bonanza-Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds at Kathangari and Bonanza-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 9504 |  |  | County treasury | N/A | 9504 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
66 | Construction of Mitumba-Phase 2-Runyenjes Central | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Mitumba-Phase 2-Runyenjes Central | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 999997 |  |  | County treasury | N/A | 999997 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
67 | Construction of Market Shed at Ugweri-Kagaari South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shed at Ugweri-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2397667.74 |  |  | County treasury | N/A | 2397667.74 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
68 | Construction of Market Shed at Ena -Kagaari South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shed at Ena -Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2394418.1 |  |  | County treasury | N/A | 2394418.1 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
69 | Construction of Market Stage Shed at Ugweri-Kagaari South | construction of shaded area in the market stage | improve market comfort and support efficient trading | market stage shade constructed, improved trading environment | Development | Construction of Market Stage Shed at Ugweri-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 400000 |  |  | County treasury | N/A | 400000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
70 | Construction of Market Stage Shed at Ena -Kagaari South | construction of shaded area in the market stage | improve market comfort and support efficient trading | market stage shade constructed, improved trading environment | Development | Construction of Market Stage Shed at Ena -Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 400000 |  |  | County treasury | N/A | 400000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
71 | Construction of Market Stage Shed at Kiringa-Kagaari South | construction of shaded area in the market stage | improve market comfort and support efficient trading | market stage shade constructed, improved trading environment | Development | Construction of Market Stage Shed at Kiringa-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 399999 |  |  | County treasury | N/A | 399999 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
72 | Construction of Toilet at Kavangua-Kagaari South | construction of toilet facilities | to improve sanitation and hygiene | complete and functional toilet facility | Development | Construction of Toilet at Kavangua-Kagaari South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499999.5 |  |  | County treasury | N/A | 499999.5 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
73 | Jua kali Shoe Shiners Sheds at Kathageri and Makutano-Kyeni North | construction of shaded areas for jua kali shoe shiners | to provide safe and organised working environment for jua kali shoe shiners | completed and functional jua kali shoe shiners shed | Development | Jua kali Shoe Shiners Sheds at Kathageri and Makutano-Kyeni North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 488376 |  |  | County treasury | N/A | 488376 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
74 | Market Shelters at Makutano-Kyeni North | construction of shaded area in the market | improve market comfort and support efficient trading | market shelters constructed, improved trading environment | Development | Market Shelters at Makutano-Kyeni North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 997438.75 |  |  | County treasury | N/A | 997438.75 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
75 | Construction of Modern Shed at Kambo-Mbeti North | construction of shaded area in the market | improve market comfort and support efficient trading | market shelters constructed, improved trading environment | Development | Construction of Modern Shed at Kambo-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1999999 |  |  | County treasury | N/A | 1999999 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
76 | Construction of Modern Shed at Kimangaru-Mbeti North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Modern Shed at Kimangaru-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2000000 |  |  | County treasury | N/A | 2000000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
77 | Construction of Ten (10)Boda Boda Sheds-Mbeti North | construction of ten shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Ten (10)Boda Boda Sheds-Mbeti North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1997290.8 |  |  | County treasury | N/A | 1997290.8 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
78 | Construction of Market and Miraa Sheds at Ndatu Market-Kithimu | construction of market and shaded areas for miraa operators | safe and comfortable environment for miraa traders and a market for other businesses | shed constructed, improved trading organization, market constructed | Development | Construction of Market and Miraa Sheds at Ndatu Market-Kithimu | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2499999 |  |  | County treasury | N/A | 2499999 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
79 | Construction of Boda Boda Shed at Micegethiu-Muminji | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Micegethiu-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 99990 |  |  | County treasury | N/A | 99990 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
80 | Construction of Boda Boda Shed at Cieria/Ngiiri-Muminji | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Cieria/Ngiiri-Muminji | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 99990 |  |  | County treasury | N/A | 99990 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
81 | Construction of Boda Boda Shed at Itiira Gitundumo -Muminji | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Itiira Gitundumo -Muminji | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 99990 |  |  | County treasury | N/A | 99990 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
82 | Construction of Boda Boda Shed at Mbet South. | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Mbet South. | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
83 | Construction of Market Sheds at Kianjokoma Market-Kagaari North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds at Kianjokoma Market-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1999990 |  |  | County treasury | N/A | 1999990 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
84 | Construction of Market Sheds at Mugui Market-Kagaari North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds at Mugui Market-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1997100 |  |  | County treasury | N/A | 1997100 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
85 | Construction of Market Sheds at Kanja Market-Kagaari North | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds at Kanja Market-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1499570.5 |  |  | County treasury | N/A | 1499570.5 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
86 | Construction of Boda Boda Sheds at Miandari,Nduuri and Munyutu-Kagaari North | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds at Miandari,Nduuri and Munyutu-Kagaari North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 299541 |  |  | County treasury | N/A | 299541 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
87 | Construction of Boda Boda Sheds at Kwa Murindi,Karii,Machang’a,Kiritiri(Beekeepers, Bus park), Rugogwe. Gikiiro and Munathiri-Mavuria | construction of shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Sheds at Kwa Murindi,Karii,Machang’a,Kiritiri(Beekeepers, Bus park), Rugogwe. Gikiiro and Munathiri-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 3698347 |  |  | County treasury | N/A | 3698347 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
88 | Electrification(Power Connections) of Market Sheds | installation and upgrading of electrical systems at the market sheds | to provide reliable and safe power supply for market activities | electrical systems intalled, reliable power supply established, improved market operations | Development | Electrification(Power Connections) of Market Sheds | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 580319 |  |  | County treasury | N/A | 580319 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
89 | Electrification(Power Connections) of Kianjokoma and Mugui Market Sheds | installation and upgrading of electrical systems at the market sheds | to provide reliable and safe power supply for market activities | electrical systems intalled, reliable power supply established, improved market operations | Development | Electrification(Power Connections) of Kianjokoma and Mugui Market Sheds | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 494044 |  |  | County treasury | N/A | 494044 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
90 | General market maintenance-Kagaari North(Kianjokoma mitumba sheds) | rehabilitation and upgrading of the mitumba sheds and the markets | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | General market maintenance-Kagaari North(Kianjokoma mitumba sheds) | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 759325 |  |  | County treasury | N/A | 759325 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
91 | Roofing of Embu fresh produce Market-Kirimari | roofing for an existing market | to protect traders and goods from weather elements | roofed and weather protected market shed | Development | Roofing of Embu fresh produce Market-Kirimari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 7577039 |  |  | County treasury | N/A | 7577039 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
92 | Majimbo Fresh Produce | construction of the market to provide organiized and improved trading facilities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Majimbo Fresh Produce | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
93 | Construction of Kiritiri Fresh Market Produce | construction of the market to provide organiized and improved trading facilities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Construction of Kiritiri Fresh Market Produce | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 6500098 |  |  | County treasury | N/A | 6500098 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
94 | Kevote Market Phase 1 | construction of the market to provide organiized and improved trading facilities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Kevote Market Phase 1 | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 4035354 |  |  | County treasury | N/A | 4035354 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
95 | Mt. Kenya Infrastructure and Civil works | infrastructure and civil works to improve access, safety and facilities | enhance transportation, utilities, and structural facilities to support local community | improved roads, drainage systems and durable civil structures | Development | Mt. Kenya Infrastructure and Civil works | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
96 | Construction of bodaboda sheds-Other Markets | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of bodaboda sheds-Other Markets | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
97 | Milk Collecting Sheds(10)-Gaturi North | construction of milk collecting sheds | improve milk hygiene, efficiency and aggregation for farmers | functional ilk collecting sheds | Development | Milk Collecting Sheds(10)-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
98 | Construction of Sheds for Kithimu Open Air Market | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Sheds for Kithimu Open Air Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 3400000 |  |  | County treasury | N/A | 3400000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
99 | Livestock Yards development(Mutuobare,Ishiara,Kithimu) | development of livestock yards with proper handling, holding, and management facilities | improve livestock management, animal welfare and market efficiency | fully equipped livestock yards | Development | Livestock Yards development(Mutuobare,Ishiara,Kithimu) | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
100 | Trade house Building (From Alcohol Fund) | construction of trade house to host commercial and business operations | provide a centralized and modern space for trade and business operations | completed trade house building | Development | Trade house Building (From Alcohol Fund) | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 4734945.8 |  |  | County treasury | N/A | 4734945.8 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
101 | Men Group Pilot project-Egg Incubators-Gaturi north-SUB TOTALS | pilot project introducing egg incubators for mens group | enhance income generation and skill in poultry farming through improved hatching technology | operational egg incubators and trained mens groups with increased chick production | Development | Men Group Pilot project-Egg Incubators-Gaturi north-SUB TOTALS | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 356400 |  |  | County treasury | N/A | 356400 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
102 | Physical Planning newsite market-Kiambere-SUB TOTALS | physical planning and layout design for newsite market area | ensure orderly development, efficient space use and improved market operations | approved physical plan with designated stalls, acces routes and service areas | Development | Physical Planning newsite market-Kiambere-SUB TOTALS | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
103 | Grading and Murraming Kithimu Market Access roads-Kithimu | grading and murraming market access | improved accessibility drainage and userbility of the market space | leveled and murramed market surfaces with improved access and reduced dust and mud | Development | Grading and Murraming Kithimu Market Access roads-Kithimu | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
104 | Carwash Machine(5)-Gaturi North | procurement and installation of carwash machine | improve effficiency service quality and income generation in carwash operations | fully installed and operational carwash machine | Development | Carwash Machine(5)-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
105 | Motorbike (7) for Youth Group-Gaturi North | provision of 7 mortobikes to youth groups | enhance transportation business activities and income generation for youth | 7 fullu functional mortobikes allocated to youth groups | Development | Motorbike (7) for Youth Group-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1499300 |  |  | County treasury | N/A | 1499300 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
106 | Aqua Trade(Fishing Boats)-Mavuria | provision of fishing boats to support aquaculture | boost fish production income and livelihood for local communities | operational fishing boats | Development | Aqua Trade(Fishing Boats)-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 3000000 |  |  | County treasury | N/A | 3000000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
107 | Kiritiri Livestock Yard-Mavuria | construction and development of a livestock yard | improve livestock handling, welfare and market efficiency | functional livestock yard | Development | Kiritiri Livestock Yard-Mavuria | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 4249899 |  |  | County treasury | N/A | 4249899 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
108 | Construction of Boda Boda shed at Kithimu West Market | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Kithimu West Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
109 | Construction of Boda Boda shed at Weru’s Junction | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Weru’s Junction | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
110 | Construction of Boda Boda shed at Gachuriri, Kangungi, Muraru,Mecca, Nganduri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Gachuriri, Kangungi, Muraru,Mecca, Nganduri | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 599305 |  |  | County treasury | N/A | 599305 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
111 | Construction of Boda Boda shed at Runyenjes | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Runyenjes | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
112 | Construction of Market Sheds-Makima | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds-Makima | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 3993938 |  |  | County treasury | N/A | 3993938 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
113 | Construction of Market Sheds-Kanyuambora | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Sheds-Kanyuambora | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1492755 |  |  | County treasury | N/A | 1492755 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
114 | Improvement of Access road at Karurumo Market | upgrading and improving of access road | facilitate easier safer and faster movement of people and goods | improved and durable access roads with better surface an drainage | Development | Improvement of Access road at Karurumo Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1499416 |  |  | County treasury | N/A | 1499416 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
115 | Improvement of Kirimari Market | upgading market infrastructure and facilities | create a cleaner safer and more efficient trading environment | renovated market | Development | Improvement of Kirimari Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499500 |  |  | County treasury | N/A | 499500 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
116 | Construction of Boda Boda Shed at Nduta, Rukira and Miani | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda Shed at Nduta, Rukira and Miani | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 28200 |  |  | County treasury | N/A | 28200 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
117 | Proposed Construction of Boda Boda Sheds at Makutano, Karaba, Gategi and Wango-Retention | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Proposed Construction of Boda Boda Sheds at Makutano, Karaba, Gategi and Wango-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 39597.7 |  |  | County treasury | N/A | 39597.7 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
118 | Construction of Kathageri Market Sheds-Retention | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Kathageri Market Sheds-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 198998 |  |  | County treasury | N/A | 198998 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
119 | Roofing of Kirimari Mitumba Market Sheds-Retention | roofing for an existing mitumba market sheds | to protect traders and goods from weather elements | roofed and weather protected mitumba market sheds | Development | Roofing of Kirimari Mitumba Market Sheds-Retention | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 599751.5 |  |  | County treasury | N/A | 599751.5 | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
120 | Retention release for the construction of Mitumba Sheds at Kirimari Market | retention release for the completion of mitumba sheds | ensure full payment of retained funds to finalize construction and hand over functional sheds | completed and functional mitumba sheds | Development | Retention release for the construction of Mitumba Sheds at Kirimari Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 199872 |  |  | County treasury | N/A | 199872 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
121 | Construction of Boda Boda shed at Ngiiri,Kathanje and Kirie | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Ngiiri,Kathanje and Kirie | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 299329 |  |  | County treasury | N/A | 299329 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
122 | Construction of Toilet Block at Mbondoni Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet Block at Mbondoni Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
123 | Construction of Toilet at Makima Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet at Makima Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
124 | Construction of Toilet at Karaba Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet at Karaba Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 497756 |  |  | County treasury | N/A | 497756 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
125 | Construction of Toilet Block at Ngiiri Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet Block at Ngiiri Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 528787 |  |  | County treasury | N/A | 528787 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
126 | Construction of Toilet Block at Mutuobare Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Toilet Block at Mutuobare Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 698054.9 |  |  | County treasury | N/A | 698054.9 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
127 | Construction of Livestock Market at Karaba | construction of a dedicated livestock market | provide a structured safe and efficient space for livestock trade | fully constructed livestock market | Development | Construction of Livestock Market at Karaba | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1999492 |  |  | County treasury | N/A | 1999492 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
128 | Construction of Karaba Livestock Toilet | construction of a toilet for karaba livestock market | improved sanitation and hygiene | functional livestock market toilet | Development | Construction of Karaba Livestock Toilet | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 319960 |  |  | County treasury | N/A | 319960 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
129 | Construction of Kathageri Market Toilet | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Kathageri Market Toilet | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 341596.8 |  |  | County treasury | N/A | 341596.8 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
130 | Construction of Kiritiri Livestock Market | construction of a toilet for kiritiri livestock market | improved sanitation and hygiene | functional livestock market toilet | Development | Construction of Kiritiri Livestock Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1499995 |  |  | County treasury | N/A | 1499995 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
131 | Repair of Wachoro Jua Kali Wall and Construction of Makutano Livestock Shed | repair of of the jua kali wall and construction of livestock shade | strengthen market infrastructure for jua kali traders and improve market comfort for the livestock traders | jua kali wall repaired'livestock shed constructed | Development | Repair of Wachoro Jua Kali Wall and Construction of Makutano Livestock Shed | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1656468 |  |  | County treasury | N/A | 1656468 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
132 | Construction of Ishiara Livestock Market Toilet | construction of a toilet for Ishiara livestock market | improved sanitation and hygiene | functional livestock market toilet | Development | Construction of Ishiara Livestock Market Toilet | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
133 | Construction of Mugui Market Toilet muchagori | construction of public sanitation facility in the market | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of Mugui Market Toilet muchagori | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 228000 |  |  | County treasury | N/A | 228000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
134 | Construction of Siakago bus park Modern Toilet | construction of toilet facilities within the bus park | to improve sanitation and hygiene for passengers and operators | completed and functional buspark toilet facility | Development | Construction of Siakago bus park Modern Toilet | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 999908.4 |  |  | County treasury | N/A | 999908.4 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
135 | Construction of 2 Shoe Shiner sheds and 1 Boda-boda at Runyenjes | construction of 2 shaded areas for shoe shiners and provision of 1 bodaboda | to provide safe and organised working environment for shoe shiners promote transport | completed and functional shoe shiners shed bodaboda provided | Development | Construction of 2 Shoe Shiner sheds and 1 Boda-boda at Runyenjes | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
136 | Construction of Boda Boda shed at Makengi | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Makengi | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
137 | Construction of Boda Boda shed at Muchagori | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Muchagori | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 214000 |  |  | County treasury | N/A | 214000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
138 | Construction of Boda Boda shed at Kavutiri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Kavutiri | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 214000 |  |  | County treasury | N/A | 214000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
139 | Renovation works at embu Fresh Priduce Market Wall | renovation of the walls of the market | strengthen market infrastructure and create and secure envirionment for traders and customers | repaired and rainforced market walls | Development | Renovation works at embu Fresh Priduce Market Wall | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
140 | Construction of Karingari Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Karingari Market Shed | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1270621.2 |  |  | County treasury | N/A | 1270621.2 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
141 | Construction of Boda Boda shed at Kanyariri, Siakago, Magacha, Nthawa and Muchonoke Markets | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Boda Boda shed at Kanyariri, Siakago, Magacha, Nthawa and Muchonoke Markets | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
142 | Construction of Four(4) Egg Incubators-Gaturi North | construction and intallation of four egg incubators | increased hatchery capacity and improved poultry production | for fully operational egg incubators | Development | Construction of Four(4) Egg Incubators-Gaturi North | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 227600 |  |  | County treasury | N/A | 227600 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
143 | Construction of market toilet at Kevote | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction of market toilet at Kevote | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
144 | Construction of Ramp and Drainage at Siakago market | construction of ramp drainage at the market | improved water flow reduce erosion and protect surrounding infrastructure of the market | functional ramp drainage system | Development | Construction of Ramp and Drainage at Siakago market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 499621 |  |  | County treasury | N/A | 499621 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
145 | Renovation of Makutano ESP Fresh Produce | renovation of the market to improve infrastructure and facilities | enhance market functionality | upgraded market with better overall facilities | Development | Renovation of Makutano ESP Fresh Produce | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 1199858.67 |  |  | County treasury | N/A | 1199858.67 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
146 | Erection of LED floodlights at Kamumu Market | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Erection of LED floodlights at Kamumu Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 600000 |  |  | County treasury | N/A | 600000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
147 | Murraming of Gategi Bus Park and Drainage | murraming of the bus park to improve surface and accessibility | enhance vehicle movement | levelled and murramed bus park | Development | Murraming of Gategi Bus Park and Drainage | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2292306 |  |  | County treasury | N/A | 2292306 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
148 | MSE and Industrial Development policy | formulation of policy for MSE | guide growth, and support MSEs and industries for economic development | comprehensive MSE and industrial development policy framework for implementation | Development | MSE and Industrial Development policy | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 969760 |  |  | County treasury | N/A | 969760 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
149 | Construction of Market shed at Kigumo Kyeni South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market shed at Kigumo Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
150 | Construction of Market shed at Karurumo Kyeni South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market shed at Karurumo Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
151 | Construction of drainage at Karurumo Kyeni South | construction of ramp drainage at the market | improved water flow reduce erosion and protect surrounding infrastructure of the market | functional ramp drainage system | Development | Construction of drainage at Karurumo Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
152 | Improvement of Karurumo market Kyeni South | routine repair, cleaning, and upkeep of market facilities | to ensure safe, clean , and functional market environment | well maintained and operational market facilities | Development | Improvement of Karurumo market Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
153 | Construction of a Bus stage Shed at Karurumo Kyeni South | shaded areas for bus stage | safe and comfortable waiting area for bus passengers | shades construcred, enhanced traffic management at designated areas | Development | Construction of a Bus stage Shed at Karurumo Kyeni South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
154 | Construction of Market shed at Muraru Mbeti South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market shed at Muraru Mbeti South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
155 | Construction of Three Boda boda Sheds at Rwika, Gachoka Kiamuringa Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction of Three Boda boda Sheds at Rwika, Gachoka Kiamuringa Mbeti South | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
156 | Acquisition of Land for expansion of Muraru Market | acquisition of land for expanding market | secure suitable land to support organized market development and future growth | legally acquired and ready to develop market land | Development | Acquisition of Land for expansion of Muraru Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
157 | Acquisition of Market Land at Kiritiri | acquisition of land for expanding market | secure suitable land to support organized market development and future growth | legally acquired and ready to develop market land | Development | Acquisition of Market Land at Kiritiri | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
158 | Acquisition of Market Land at Kasavari | acquisition of land for expanding market | secure suitable land to support organized market development and future growth | legally acquired and ready to develop market land | Development | Acquisition of Market Land at Kasavari | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2130000 |  |  | County treasury | N/A | 2130000 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
159 | Improvement of Makima Market | routine repair, cleaning, and upkeep of market facilities | to ensure safe, clean , and functional market environment | well maintained and operational market facilities | Development | Improvement of Makima Market | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
160 | Embu-Meru Bus park | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Embu-Meru Bus park | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 7992882 |  |  | County treasury | N/A | 7992882 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
161 | Kiritiri bus park | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Kiritiri bus park | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 5995225.7 |  |  | County treasury | N/A | 5995225.7 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
162 | Iria Itune Bus Park | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Iria Itune Bus Park | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2000000 |  |  | County treasury | N/A | 2000000 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
163 | Runyenjes Bus Park | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Runyenjes Bus Park | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
164 | Siakago Bus park | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Siakago Bus park | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2999379.05 |  |  | County treasury | N/A | 2999379.05 | N/A | [5 empty] | Ongoing |  | N/A | N/A | N/A | N/A | N/A
165 | Kibugu Bus Park Integrated project | construction of a bus park to organize public transport operations | provide safe accessible and efficient space for buses passengers and vendors | fullu constructed bus park | Development | Kibugu Bus Park Integrated project | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 2999998 |  |  | County treasury | N/A | 2999998 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
166 | Mt. Kenya South Tourism Circuit- Heavy Grading | heavy grading of roads in the specified area to improve accessibility | enhance tourist movement safety and connectivity within the circuit | well graded roads providing smoother and safer access to key tourist sites | Tourism | Mt. Kenya South Tourism Circuit- Heavy Grading | N/A | N/A | N/A | Tourism | Tourism | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
167 | Mwea National Reserve - Roads Murraming and Banda's Construction | murraming of roads within the reserve and construction of banda | enhance mobility tourism experience and infrastructure within the reserve | durable murramed roads and fully constructed bandas | Development | Mwea National Reserve - Roads Murraming and Banda's Construction | N/A | N/A | N/A | Development | Development | Development | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 |  |  |  | County treasury | N/A |  | N/A | [7 empty] | N/A | N/A | N/A | N/A | N/A
168 | Training of groups on ovop business management seminar | training groups | training them on ovop business management | fully trained groups on business management | Investment | Training of groups on ovop business management seminar | N/A | N/A | N/A | Investment | Investment | Investment | 1/072016 | 1/072016 | 31/06/2017 | 31/06/2017 | 561300 |  |  | County treasury | N/A | 561300 | N/A | [5 empty] | Completed |  | N/A | N/A | N/A | N/A | N/A
2015/2016
1 | Construction Of Toilets-Kianjokoma Stage | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilets-Kianjokoma Stage | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
2 | Construction Of Toilet At Ugweri Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilet At Ugweri Market | N/A | Central | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 424667.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
3 | Construction Of Toilets At Manyatta Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Toilets At Manyatta Market | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 480912.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
4 | Construction Of Market Shed Slab For Kiritiri Market | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed Slab For Kiritiri Market | N/A | Mavuria | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3999988.7 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
5 | Construction Of Kiritiri Market Phase 1 - Roofing | roofing the new market | to protect traders and goods from weather elements | roofed and weather protected market | Development | Construction Of Kiritiri Market Phase 1 - Roofing | N/A | Mavuria | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3324519 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Kathageri Market Shed. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Kathageri Market Shed. | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1989980 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
7 | Construction Of Ishiara Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Ishiara Market Shed | N/A | Evurori | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999907 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
8 | Construction Of Manyatta Market Shed And Refuse Bin. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Manyatta Market Shed And Refuse Bin. | N/A | Kimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999681 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
9 | Roofing Of Kirimari Mitumba Market | roofing of the mitumba market | to protect traders and goods from weather elements | roofed and weather protected market | Development | Roofing Of Kirimari Mitumba Market | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3278017.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
10 | Improvement Of Market Shed At Makutano Market | improvement of the existing market shed | improve market comfort and support efficient trading | market shade improvised, improved trading environment | Development | Improvement Of Market Shed At Makutano Market | N/A | Mwea | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 499119 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Manyatta Market Shed And Refuse Bin. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Manyatta Market Shed And Refuse Bin. | N/A | Kimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999681 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Market Shed Kianjokoma Market | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed Kianjokoma Market | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999990 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
13 | Roofing Of Kibugu Mitumba Sheds | roofing for an existing mitumba market sheds | to protect traders and goods from weather elements | roofed and weather protected mitumba market sheds | Development | Roofing Of Kibugu Mitumba Sheds | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 2510472.15 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
14 | Livestock Yards Development(Mutuobare ,Ishiara,Kithimu) | evelopment of the livestock yards | provide a structured safe and efficient space for livestock | fully developed livestock yard | Development | Livestock Yards Development(Mutuobare ,Ishiara,Kithimu) | N/A | Kiambere, Evurore & Kithimu | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 6961559 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Livestock Market Kithimu | construction of a dedicated livestock market | provide a structured safe and efficient space for livestock trade | fully constructed livestock market | Development | Construction Of Livestock Market Kithimu | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1495914.4 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Mutuobare Livestock Shed Market, Fencing, And Gates. | construction of shaded area in the livestock market | improve market comfort and support efficient trading | livestock market shade constructed, improved trading environment | Development | Construction Of Mutuobare Livestock Shed Market, Fencing, And Gates. | N/A | Kiambere | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1867941 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
17 | Rehabilitarion Of Market Shed Ishiara | rehabilitation and upgrading of the market shed | to enhance market shed infrastructure and support efficient trade | market shed rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitarion Of Market Shed Ishiara | N/A | Evorori | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1994775 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
18 | Construction Of Ishiara Livestock Shed Market, Fencing, And Gates. | construction of shaded area in the livestock market | improve market comfort and support efficient trading | livestock market shade constructed, improved trading environment | Development | Construction Of Ishiara Livestock Shed Market, Fencing, And Gates. | N/A | Evurori | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1339275 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
19 | Hosting Miss Tourism Activities In Embu | hosting tourism activities | hosting miss tourism in embu | miss tourism hosted well | Tourism | Hosting Miss Tourism Activities In Embu | N/A | County Hq | N/A | Tourism | Tourism | Tourism | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3405040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Wachoro Juakali Wall And Livestock Shed At Makutano . | construction of of the jua kali wall and construction of livestock shade | strengthen market infrastructure for jua kali traders and improve market comfort for the livestock traders | jua kali wall consreucted livestock shed constructed | Development | Construction Of Wachoro Juakali Wall And Livestock Shed At Makutano . | N/A | Mwea | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1699990 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
21 | Renovation Of Former Plgos Offices, To Accommodate Trade And Industrialization & Investment | renovations of the plgos offices | god offices for accomodatio of trade industrialization and investment | plgos offices renovated | Development | Renovation Of Former Plgos Offices, To Accommodate Trade And Industrialization & Investment | N/A | Manyatta | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1688380 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
22 | Roofing Of Of Embu Mitumba Sheds Kirimari | roofing for an existing mitumba market sheds | to protect traders and goods from weather elements | roofed and weather protected mitumba market sheds | Development | Roofing Of Of Embu Mitumba Sheds Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 683655.3 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
23 | Bodaboda Youth Driving Licences Project (Gaturi N) | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Investment | Bodaboda Youth Driving Licences Project (Gaturi N) | N/A | Gaturi North | N/A | Investment | Investment | Investment | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 700000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
24 | Bodaboda Sheds-Kanyariri,Siakago And Riandu Markets | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Bodaboda Sheds-Kanyariri,Siakago And Riandu Markets | N/A | Nthawa | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 278226 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
25 | Construction Of Majimbo Market Shed. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Majimbo Market Shed. | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 2280000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
26 | Kiritiri Market Shed Construction | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Kiritiri Market Shed Construction | N/A | Mavuria | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 4361188 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
27 | Construction Of Bodaboda Sheds-Kibugu Market | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Sheds-Kibugu Market | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 94120 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
28 | Construction Of A Shoes Shiners Shed At Kirimari Shell. | construction of shaded areas for shoe shiners | to provide safe and organised working environment for shoe shiners | completed and functional shoe shiners shed | Development | Construction Of A Shoes Shiners Shed At Kirimari Shell. | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 91362 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
29 | Construction Of Bodaboda Sheds-Gaturi Market | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Sheds-Gaturi Market | N/A | Gaturi | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 95040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
30 | Construction Of Bodaboda Sheds-Gakwegori Market | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Sheds-Gakwegori Market | N/A | Gatuti South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 90040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
31 | Construction Of Bodaboda Sheds-Kathageri Market | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Sheds-Kathageri Market | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 95040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
32 | Construction Of Bodaboda Sheds-Makutano Market-Kyeni North | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Sheds-Makutano Market-Kyeni North | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 91362 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
33 | Live Coverage Of State Of The County Address And Three Days Advertisement | coverage of state of county address | covering state of county adress and advertisement | state address covered , advertisement done | Tourism | Live Coverage Of State Of The County Address And Three Days Advertisement | N/A | County | N/A | Tourism | Tourism | Tourism | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1740000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
34 | Provision Of Consultancy Services For Miss Tourism Embu County | consultunsy services for miss tourism | provision of consultunsy services to miss tourism embu | professional consultant to miss tourism embu | Tourism | Provision Of Consultancy Services For Miss Tourism Embu County | N/A | County Wide | N/A | Tourism | Tourism | Tourism | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 2605900 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
35 | Installation Of Signages In Various Tourism Sites | signages in various sites | to install signages in various tourist sites | signages installed in various sites | Tourism | Installation Of Signages In Various Tourism Sites | N/A | All Wards | N/A | Tourism | Tourism | Tourism | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999995 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
36 | Environmental Impact Assessment For Mt. Kenya Route. | assessement of various environment impacts | environmental impact for the mt kenya route | environmental impact for the mt kenya route assesed | Development | Environmental Impact Assessment For Mt. Kenya Route. | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1972000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
37 | Market Land Purchase -Muraru | purchase of land for expanding market | secure suitable land to support organized market development and future growth | legally acquired and ready to develop market land | Development | Market Land Purchase -Muraru | N/A | Mbeti South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 976170 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
38 | Purchase Of Market Land For Kyeni/ Kigumo/5104. | purchase of land for expanding market | secure suitable land to support organized market development and future growth | legally acquired and ready to develop market land | Development | Purchase Of Market Land For Kyeni/ Kigumo/5104. | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1500000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
39 | Liquor Bill Development Expenses | development of liquor bill expenses | to develop liquor bill expenses | liquor bill expenses developed | Development | Liquor Bill Development Expenses | N/A | County Hq | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1252000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
40 | Subscription Fees For The County | fee for the county | subscription fee for the county given | subscription fee for the county acquired | Development | Subscription Fees For The County | N/A | County Hq | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 232000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
41 | Development Policy | policy development | to develop a policy | policy developed | Development | Development Policy | N/A | County Hq | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 999200 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
42 | Improvement Of Toilet At Muraru Market, Water Born Market Toilets. | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Improvement Of Toilet At Muraru Market, Water Born Market Toilets. | N/A | Mbeti South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 494374.6 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
43 | Contruction Of Bodaboda Shed At Makutano, Karaba, Gategi &Wango | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Makutano, Karaba, Gategi &Wango | N/A | Karaba | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 395977 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
44 | Contruction Of Bodaboda Shed At Makima | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Makima | N/A | Makima | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 97695 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
45 | Contruction Of Bodaboda Shed At Kathageri B. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Kathageri B. | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 95040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
46 | Contruction Of Bodaboda Shed At Kamugane | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Kamugane | N/A | Nthawa | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 96889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
47 | Contruction Of Bodaboda Shed At Kangethia. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Kangethia. | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 95040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
48 | Contruction Of Bodaboda Shed At Kathangariri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Kathangariri | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 95040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
49 | Contruction Of Bodaboda Shed At Ugweri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Ugweri | N/A | Kagaari South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 96889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
50 | Contruction Of Bodaboda Shed At Sunrise | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Sunrise | N/A | Mbeti North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 85591.65 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
51 | Contruction Of Bodaboda Shed At Kathageri A. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Kathageri A. | N/A | Kyeni North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 94820 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
52 | Contruction Of Bodaboda Shed At Ena. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Ena. | N/A | Kagaari South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 96889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
53 | Contruction Of Bodaboda Shed At Gatunduri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Gatunduri | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 90040 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
54 | Contruction Of Bodaboda Shed At Mutuovare. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Mutuovare. | N/A | Kiambere | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 96889 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
55 | Contruction Of Bodaboda Shed At Makutato Kyeni | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Makutato Kyeni | N/A | Kyeni South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 94120 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
56 | Construction On Market Toilets At Ishiara Livestock Market. | construction of a toilet for Ishiara livestock market | improved sanitation and hygiene | functional livestock market toilet | Development | Construction On Market Toilets At Ishiara Livestock Market. | N/A | Evurori | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 139942 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
57 | Contruction Of Bodaboda Shed At Rukuriri | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Shed At Rukuriri | N/A | Gaturi North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 94120 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
58 | Construction On Market Toilets At Ishiara Bus Park | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction On Market Toilets At Ishiara Bus Park | N/A | Evurore | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 499461.2 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
59 | Rehabilitation Of Kimangaru Livestock Market. | rehabilitation and upgrading of the livestock market | to enhance livestock market infrastructure and support efficient trade | livestock market rehabilitated, improved trading facilities and increased market efficiency | Development | Rehabilitation Of Kimangaru Livestock Market. | N/A | Mbeti North | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 499078 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
60 | Contruction Of Bodaboda Sheds At Miani, Ndatu And Rukira. | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Contruction Of Bodaboda Sheds At Miani, Ndatu And Rukira. | N/A | Kithimu | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 282000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
61 | Repairs Of First Bus Park Of Embu Town | repair of embu bus park | repairing of first bus park of embu | bus park repaired | Development | Repairs Of First Bus Park Of Embu Town | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1498256 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
62 | Constuction Of Bodaboda Sheds At Karerema Nad Sokomjinga | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Constuction Of Bodaboda Sheds At Karerema Nad Sokomjinga | N/A | Evurore | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 499722 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
63 | Market Improvement At Ena/ Ugweri Market | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Market Improvement At Ena/ Ugweri Market | N/A | Kagaari South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 492251.8 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
64 | Contruction Of Toilet Block At Kanyuambora Market | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Contruction Of Toilet Block At Kanyuambora Market | N/A | Evurore | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 499550 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
65 | Construction Of Bodaboda Shed At Mutuobare | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Shed At Mutuobare | N/A | Kiambere | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 91432.15 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
66 | Training And Licencing Of 54 Boda Boda Riders. | provision of mortocycle riding training and facilitation of driving licence acquisition for bodaboda operators | to enhance road safety and legal compliance among bodaboda riders | trained , tested, and licensed bodaboda riders | Development | Training And Licencing Of 54 Boda Boda Riders. | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 325000 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
67 | Fencing Of Kibugu Market | construction of of the market wall | strengthen market infrastructure for traders and protection | market wall constructed | Development | Fencing Of Kibugu Market | N/A | Nginda | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 472839 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
68 | Construction Of Bodaboda Shed At Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Bodaboda Shed At Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 199137.45 | N/A | N/A | Completed | 100% | N/A | N/A | N/A | N/A | N/A
69 | Mrkt Maint | construction of the market to provide organiized and improved trading facilities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Mrkt Maint | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 165300 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
70 | Markets | construction of the market to provide organiized and improved trading facilities | to support efficient trade and promote local economic development | market constructed, improved trading infrastructure, increased commercial activity | Development | Markets | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 67000 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
71 | Street Lighting | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Street Lighting | N/A | Kirimari | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 48255 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
72 | Bodaboda Shades | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Bodaboda Shades | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 165300 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
73 | Boda Boda Sheds | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Boda Boda Sheds | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 43000 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
74 | Livestock Yard | construction and development of a livestock yard | improve livestock handling, welfare and market efficiency | functional livestock yard | Development | Livestock Yard | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 165300 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
75 | Boda Boda Sheds | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Boda Boda Sheds | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 85865.15 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
76 | Bada Boda Shed Kivwe | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Bada Boda Shed Kivwe | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 91362 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
77 | Market Improvement | upgading market infrastructure and facilities | create a cleaner safer and more efficient trading environment | renovated market | Development | Market Improvement | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 400454.6 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
78 | Market Improvement | upgading market infrastructure and facilities | create a cleaner safer and more efficient trading environment | renovated market | Development | Market Improvement | N/A |  | N/A | Development | Development | Development | 2014-07-01 | 2014-07-01 | 31/06/2015 | 31/06/2015 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 492831.8 | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A
2014/2015
1 | Construction of a Proposed Market Shed at Mbondoni Makima | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of a Proposed Market Shed at Mbondoni Makima | N/A | Makima | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1989887 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
2 | Construction of Market Shed at Meka Market Mbeti South. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shed at Meka Market Mbeti South. | N/A | Mbeti South | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 495796 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
3 | Construction of Market Shed at Karurina Gaturi South | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Market Shed at Karurina Gaturi South | N/A | Gaturi South | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1964113 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
4 | Construction of Mitumba Shed Runyenje Central | construction of shaded area in the market for mitumba | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction of Mitumba Shed Runyenje Central | N/A | Runyenjes Central | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1938186 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
5 | Construction Of Boda Boda Sheds-Mbeti South | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds-Mbeti South | N/A | Mbeti South | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 299611 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
6 | Construction Of Boda Boda Sheds At Mwondu- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Mwondu- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 250000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
7 | Construction Of Boda Boda Sheds At Kambaru- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Kambaru- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 250000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
8 | Construction Of Boda Boda Sheds At Ciambugu- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Ciambugu- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 250000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
9 | Construction Of Boda Boda Sheds At Siakago Stage- Nthawa | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds At Siakago Stage- Nthawa | N/A |  | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 250000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
10 | Construction Of Machang’a Market Toilet-Mavuria | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Machang’a Market Toilet-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 484416 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
11 | Construction Of Boda Boda Sheds -Kirimari | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Sheds -Kirimari | N/A | Kirimari | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 799901 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
12 | Construction Of Market Toilet At Manyatta Market-Ruguru Ngandori | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Manyatta Market-Ruguru Ngandori | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 400000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
13 | Construction Of Mega Boda Boda Shed At Kiritiri-Mavuria | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Mega Boda Boda Shed At Kiritiri-Mavuria | N/A | Mavuria | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 998957 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
14 | Market Maintenance-Kagaari North | rehabilitation and upgrading of the market | to enhance market infrastructure and support efficient trade | market rehabilitated, improved trading facilities and increased market efficiency | Development | Market Maintenance-Kagaari North | N/A | Kirimari | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 999630 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
15 | Construction Of Market Toilet At Kianjokoma - Kagaari North | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Market Toilet At Kianjokoma - Kagaari North | N/A | Kagaari North | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 498148 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
16 | Construction Of Market Shed At Riandu Market- Nthawa | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Riandu Market- Nthawa | N/A | Nthawa | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 899980 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
17 | Construction Of Market Shed At Newsite-Kiambere | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Market Shed At Newsite-Kiambere | N/A | Kiambere | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 999482 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
18 | Construction Of Boda Boda Shed At Mutuobare- Kiambere | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Mutuobare- Kiambere | N/A | Kiambere | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 250000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
19 | Construction Of Boda Boda Shed At Nthingini-Mwea | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Nthingini-Mwea | N/A | Mwea | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 249574 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
20 | Construction Of Boda Boda Shed At Mugwanjogu Market-Evurore | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed At Mugwanjogu Market-Evurore | N/A | Evurore | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 198263 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
21 | Construction Of Karurumo Market Shed(Joyri Solutions) | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Karurumo Market Shed(Joyri Solutions) | N/A | Kyeni South | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1795664 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
22 | Construction Of Ngiiri Market Shed | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Construction Of Ngiiri Market Shed | N/A | Muminji | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1999434 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
23 | Roofing Of Mutuobare Market Shed(Vivi Ltd) | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Roofing Of Mutuobare Market Shed(Vivi Ltd) | N/A | Kiambere | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 2499394 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
24 | Construction Of Mbonzuki and Iria Itune Market Toilets-Hasbakari General Supplies | construction of public sanitation facility | enhance public health and sanitation standerds | public toilet constructed, improved sanitation and hygiene | Development | Construction Of Mbonzuki and Iria Itune Market Toilets-Hasbakari General Supplies | N/A | Mwea | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1197538 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
25 | Construction Of Bridge At Mwea Game Reserve-Tides Investments | construction of a bridge within the reserve to improve access and connectivity | to facilitate saf and efficient movement of people and vehicles across the reserve | completed and operational bridge at the reserve | Development | Construction Of Bridge At Mwea Game Reserve-Tides Investments | N/A | Mwea | N/A | Tourism | Tourism | Tourism | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3495660 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
26 | Construction Of Boda Boda Shed at Mbeti South Ward | shaded areas for bodaboda riders | safe and comfortable parking for bodabodas | shades construcred, enhanced traffic management at designated areas | Development | Construction Of Boda Boda Shed at Mbeti South Ward | N/A | Mbeti South | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 359979 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
27 | Installation and repair of floodlight | installation of floodlights at specific areas | safe and comfortable parking for bodabods | shades construcred, enhanced traffic management at designated areas | Development | Installation and repair of floodlight | N/A | County Wide | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 494299 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
28 | Completion of Manyatta Market Shed.Ngandori Ward Ruguru. | construction of shaded area in the market | improve market comfort and support efficient trading | market shade constructed, improved trading environment | Development | Completion of Manyatta Market Shed.Ngandori Ward Ruguru. | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3960031 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
29 | Maintenance of Mwea Game Reserve Circuit Roads | routine repair and upkeep of circuit roads within the reserve | to ensure safe, smooth and accessible roads for visitors and park operations | well maintained and operational cercuit roads within the reserve | Development | Maintenance of Mwea Game Reserve Circuit Roads | N/A | Mwea | N/A | Tourism | Tourism | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3595153 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
30 | Construction of a Bridge at Mwea Game Reserve | construction of a bridge within the reserve to improve access and connectivity | to facilitate saf and efficient movement of people and vehicles across the reserve | completed and operational bridge at the reserve | Investment | Construction of a Bridge at Mwea Game Reserve | N/A | Mwea | N/A | Tourism | Tourism | Tourism | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 3882533 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
31 | Construction of a Wastebin at Manyatta -Ngandori Ward | construction and installation of waste bins in the designated area | to improve waste management, sanitation , and cleanliness in the community | constructed and functional waste bins intalled at targeted locations | Development | Construction of a Wastebin at Manyatta -Ngandori Ward | N/A | Ruguru Ngandori | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 996700 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
32 | Construction And Civil Works | construction of related civil works including temporary relocation of traders during implementation | To modernize Embu market while ensuring continuity of trading activities | market civil works completed, traders temporarily relocated, improved market infrastructure | Development | Construction And Civil Works | N/A |  | N/A | Development | Development | Development | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 38742327 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
33 | Vocational Training Service-Driving Course | Provision of vocational driving training services to trainees | to equip learners with professional driving skills and certification | trained and certified drivers | Investment | Vocational Training Service-Driving Course | N/A | County Wide | N/A | Investment | Investment | Investment | 2013-07-01 | 2013-07-01 | 31/06/2014 | 31/06/2014 | N/A | N/A | N/A | County treasury | N/A | N/A | N/A | N/A | N/A | 1990000 | N/A | N/A | Ongoing | N/A | N/A | N/A | N/A | N/A | N/A
Report prepared by:
Designation:
Signature:
Date:
Report approved by:
Designation:
Signature:
Date:
[18 empty] | 1 | [6 empty] | 0% | 0 |  | 1

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled