## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Rain water harvesting | Catchment area, filtering system and storage tank | To provide public schools and institutions with clean water | Clean and safe water harvested for non-portable uses | Water | Rain water harvest | County wide | County wide |  | Water | Water | Water | 30/6/2015 | 1/7/0/14 | 30/6/2015 | 30/6/2015 | 100000000 | 100000000 | 100000000 | County Treasury | N/A | 100000000 | N/A | 100000000 | 100% | 100000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
2 | Gatende water project | pipe laying, tanks installations | To provide public schools and institutions with clean water | water available in public schools and the community | Water | Gatende water project |  | Gatende |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
3 | Nthingini piped water project | pipe laying, tanks installations | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Nthingini piped water project |  | Nthingini |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | YES | project was opperational | opperational
4 | Purchase of water pipes Runyenjes | procurement, quality assurance | To ensure effective water supply system to public institutions | Clean and reliable water available for domestic use | Water | Purchase of water pipes Runyenjes |  |  |  | Water | Water | Water | 30/6/2015 | 1/7/1014 | 30/6/2015 | 30/6/2015 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | No | N/A | Yes | project was opperational | opperational
5 | Makima piped water project | pipe laying, tanks installations | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Makima piped water project |  | Makima |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
6 | Ndune Borehole project | Land clearing, drilling | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Ndune Borehole project |  | Ndune |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
7 | Mbondoni Borehole project | Land clearing, drilling | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Mbondoi Borehole project |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
8 | utithini Borehole project | Land clearing, drilling | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Utithini Borehole project |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
9 | Kalisa Borehole project | Land clearing, drilling | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Kalisa Borehole project | Kalisa Borehole project |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
10 | Kitheru Borehole project | Land clearing, drilling | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Kitheru Borehole project |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 100000 | 100000 | 100000 | County Treasury | N/A | 100000 | N/A | 100000 | 100% | 100000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
11 | Mbeti south water project | pipe laying, tanks installations | To provide public schools and institutions with clean water | Clean and reliable water available for domestic use | Water | Mbeti south water project |  | Mbeti south |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
12 | Construction of Eco-toilet Karurina | Brick laying, excavation and construction of the superstructure and substructure | To omprove sanotation, hygine, and public health | Improved health outcomes | Water | Construction of Eco-toilet Karurina |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
13 | Public toilets (renovation and development) | Brick laying, repair of broken structure | To provide public schools and institutions with safe and clean rest rooms | Improved health outcomes | Water | Public toilets renovation and development |  | County wide |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
14 | Completion of irrigation schemes(Kiambindu,Iriari,Runga,Itabua,Muthatari,Wakaria) | Water control gates, drainage systems and distribution networks | To enhance agricultural productivity, ensure food security | Irrigation schemes constructed | Water | Completion of irrigation schemes |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 35626820 | 35626820 | 35626820 | County Treasury | N/A | 35626820 | N/A | 35626820 | 100% | 35626820 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
15 | Rupingazi- Weru irrigation Scheme Survey and Kithimu irrigation Water Project | Water control gates, drainage systems and distribution networks | To enhance agricultural productivity, ensure food security | Irrigation scheme approved and water available in public institutions | Water | Weru irrigation schenme survey and new Kithimu water project |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
16 | Completion of stalled water harvesting structures(Earth dams) | Digging, pipe laying | To provide enough water to the public institutions | Earth Dams constructed | Water | Completion of stalled water harvesting structures |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 5000000 | 5000000 | 5000000 | County Treasury | N/A | 5000000 | N/A | 5000000 | 100% | 5000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
17 | Fencing and desilting of karuriri Dam | Removing vegitation from canals | To prevent waste damping and encroachment | Strong fencce established | Water | Fencing and desilting of Karuriri dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 900000 | 900000 | 900000 | County Treasury | N/A | 900000 | N/A | 900000 | 100% | 900000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
18 | Desilting gangara/Kamucira dam | Removal of accumulated sediments,debris | Enhanced water availability | Gangara dam Desilted | Water | Desilting Gangara/Kamucira dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
19 | Desilting of Muvaruri dam | Removal of accumulated sediments,debris | Enhanced water availability | Muvaruri Dam desilted | Water | Desilting Muvaruri dam |  | Mavuria |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
20 | Desilting of ciakaviu kiambiti dam | Removal of accumulated sediments,debris | Enhanced water availability | Ciakaviu-kiambiti dam desilted | Water | desilting Ciakaviu-kiambiti dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
21 | Desilting of kirambari earth dam | Removal of accumulated sediments,debris | Enhanced water availability | Kirambari earth dam desilted | Water | Desilting kiambara earth dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
22 | Werus irrigation scheme | Water control gates, drainage systems and distribution networks | To enhance agricultural productivity, ensure food security | irrigation scheme constructed | Water | Weru irrigation scheme |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
23 | Mbeere south Dam | Digging,pipe laying | provide the public with enough water to use | Water available in every school and community | Water | Mbeere south Dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
24 | Rehabilitation of earth dam Mavuria | Reshaping, reparing the spillway | To restore the structure integrity, storage capacity | Water available for domestic, agricultural and demestic use | Water | Rehabilitation of earth dam Mavuria |  | Mavuria |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
25 | Desilting of earth dams kiambere | Removal of accumulated sediments,debris | Enhanced water availability | Water available for domestic, agricultural and demestic use | Water | Desilting kiambere earth dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 5600000 | 5600000 | 5600000 | County Treasury | N/A | 5600000 | N/A | 5600000 | 100% | 5600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
26 | Desilting of makima earth dam | Removal of accumulated sediments,debris | Enhanced water availability | Water available for domestic, agricultural and demestic use | Water | Desilting makima earth dam |  | Makima |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
27 | construction of itiira Gitua dam | land clearing, digging,pipe laying | provide the public with enough water to use | water available in public schools and the community | Water | Construction of Itiira Gitua Dam |  |  |  | Water | Water | Water | 30/6/2015/ | 2014-01-07 | 30/6/2014 | 30/6/2015 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
28 | Construction of Kivue catchment dam | Digging, pipe laying | provide the public with enough water to use | water available in public schools and the community | water | construction of Kivue catchment dam |  |  |  | Water | Water | Water | 30/6/2015 | 2014-01-07 | 30/6/2015 | 30/6/2015 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
29 | Ugweri Market-Ndumani Kasafari Pipeline | Digging, pipe laying | provide water to public institutions and to the community | water available in public institutions and in the community | Water | Ugweri market- ndumni kasafiri pipeline |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6.2016 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
30 | Kigaa water project | pipe laying, tanks installations | provide water to public institutions and to the community | water availale in public institution and in the community | Water | Kigaa water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
31 | Retune-Kirimari water project | pipe laying, tanks installations | provide water to public institutions and to the public | water available in public institutions and in the community | Water | Retune-Kirimari water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
32 | kararitiri water project | pipe laying, tanks installations | provide water to public institutions and to the public | water available in the public institutions and to the public | Water | kararitiri water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
33 | Iriamurai-Kathuuri water project | pipe laying, tanks installations | provide water to public institutions and to the public | water available in the public institutions and to the public | Water | iriamuria-Kathuuri water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
34 | Expansion of EWASCO Water pipeline kiambi | purchase of pipes,digging, pipe laying | To spread water to public schools and institutions | water available in the public institutions and to the public | Water | Expansion of EWASCO water pipeline kiambi |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
35 | Extension of EWASCO water pipeline Gachuri-makima water project | Design, procurement, and installation of additional pipeline sections | To improve access to clean water and reliable water | Reduced waterbone diseases,and available water to local regions | Water | Extension of EWASCO water pipeline Gachuri-makima |  | Makima |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
36 | Completion of kithimu Doestic water project | Installation of storage tanks, water treatment units | To ensure reliable, safe, and adequate water for the public institutions | Reduced waterbone diseases,and available water to local regions | Water | Completion of kithimu Domestic water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
37 | Kigaa-Gicheche-Gichera water project | pipe laying, tanks installations | provide water to public institutions and to the community | water available in public institutions and in the community | Water | Kigaa-Gicheche-Gichera water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational | s
38 | Mutunduri-Gatituri-karurina-itabua water project | pipe laying, tanks installations | provide water to public institutions and to the community | water available in public institutions and in the community | Water | Mutunduri-gatituri-Karurina-Itabua water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
39 | water pipes and tanks delivery | procuement, transportation, installation of quality water pipes and tanks | Enhance water supply infrastructure | clean water available for domestic, agricultural and institutonal use | Water | Water pipes and tanks delivery |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 5500000 | 5500000 | 5500000 | County Treasury | N/A | 5500000 | N/A | 5500000 | 100% | 5500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
40 | Nduuri-Ria Njagi-Kamugere-kamugu water project | pipe laying, tanks installations | provide water to public institutions and to the community | water availabli in public institutions and community | Water | Nduuri-Ria Njagi-Kamegere-Kamugu water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
41 | Kamumu-Kiathambu-kabubua Kanyama-Kiogogo water project | pipe laying, tanks installations | provide water to public institutions and to the community | water available in piblic institutions and community | Water | Kamumu-Kiathambu-Kabubu Kanyama-Kiogogo water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/206 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
42 | mashamba-mwea water project | pipe laying, tanks installations | provide water to public institutions and to the community | water available in public institutions and in the community | Water | Mashamba-mwea water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 4500000 | 4500000 | 4500000 | County Treasury | N/A | 4500000 | N/A | 4500000 | 100% | 4500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
43 | Gaturi North water project | pipe laying, tanks installations | provide water to public institutions and to the community | water available in public institutions and in the community | Water | Gaturi norht water project |  |  |  | Water | Water | Water | 30/6/2016 | 2016-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
44 | Mathirigakenda-kabuguri water project | pipe laying, tanks installations | proide water to public institutions and to the community | water available in public institutions and in the community | Water | Mathirigakenda kabuguri water project |  |  |  | Water | Water | Water | 30/6/2016 | 2016-01-07 | 30/6/2016 | 30/6/2016 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
45 | Kirambari-Getua water project | pipe laying, tanks installations | Provide water to the public institutions and to the community | water available in pulic institutions and in the communty | Water | Kirambari-Gateu water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
46 | Rain water harvesting (storage tanks)(water for children) | Catchment area, filtering system and storage tank | To design and implement a system that collects, stores, and utilizes rain water efficiently | Water harvested and stored for domestic and emergency use | Water | Rain water harvest |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 15200000 | 15200000 | 15200000 | County Treasury | N/A | 15200000 | N/A | 15200000 | 100% | 15200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
47 | Karaba-gategi-Riakanau water project | pipe laying, tanks installations | Provide water to public institutions and to the community | water available in the public institutions and to the public | Water | Karaba-Gategi Raikanau water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 7600000 | 7600000 | 7600000 | County Treasury | N/A | 7600000 | N/A | 7600000 | 100% | 7600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
48 | purchase of water pipes Runyenjes | procurement, transportation | To supply water to public schools and institutions | water available in the public institutions and to the public | Water | Purchase of water pipes Runyenjes |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 760000 | 760000 | 760000 | County Treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
49 | Ndune Bore hole Project | Land clearing, drilling | To supply water to public schools and institutions | Clean and reliable water available for domestic use | Water | Ndune Borehole project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 76000 | 76000 | 76000 | County Treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
50 | Mbondoni Bore hole Project | Drilling, installation of storage tanks | To supply water to public schools and institutions | Clean and reliable water available for domestic use | Water | Mbondoni bore hole |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 76000 | 76000 | 76000 | County Treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
51 | Utithini Bore Hole Project | Drilling, installation of storage tanks | To supply water to public schools and institutions | Clean and reliable water available for domestic use | Water | Utithini Borehole project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 76000 | 76000 | 76000 | County Treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
52 | Kalisa Bore Hole Project | Drilling, installation of storage tanks | To supply water to public schools and institutions | Clean and reliable water available for domestic use | Water | Kalisa Borehole project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 76000 | 76000 | 76000 | County Treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
53 | Kithecu Bore Hole Project | Drilling, installation of storage tanks | To supply water to public schools and institutions | Clean and reliable water available for domestic use | Water | kithecu bore hole project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 76000 | 76000 | 76000 | County Treasury | N/A | 76000 | N/A | 76000 | 100% | 76000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
54 | Mbeti South Water Project | pipe laying, tanks installations | Provide water to public schools and institutions | water available in public schools and the community | Water | Mbeti south water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 3040000 | 3040000 | 3040000 | County Treasury | N/A | 3040000 | N/A | 3040000 | 100% | 3040000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
55 | Provision of water to Karaari,Kanthenge,Gitumbi,Kwa andu a Mbogo,Kiananu villages | pipe laying, tanks installations | Provide water to public schools and institutions | water available in the public institutions and to the public | Water | Provision of water to Karaari,Kanthenge,Gitumbi,Kwa andu a Mbogo,Kiananu villages |  |  |  | Water | Water | Water | 30/6/2016 | 2016-01-07 | 30/6/2016 | 30/6/2016 | 2280000 | 2280000 | 2280000 | County Treasury | N/A | 2280000 | N/A | 2280000 | 100% | 2280000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
56 | Construction of Eco Toilet -Karurina | Digging, brick laying | To provide public schools and institutions with clean and safe rest rooms | Toilets constructed | Water | Construction of Eco-toilet Karurina |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 456000 | 456000 | 456000 | County Treasury | N/A | 456000 | N/A | 456000 | 100% | 456000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
57 | Purchase of Pipes for Gichegeri water project | procurement, transportation | to supply water to public schools and institutions | pipes bought | Water | purchase of pipes for Gichegeri water project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 380000 | 380000 | 380000 | County Treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
58 | Construction of Itiira Kanjikeru Dams | Brick laying and site preparation | To provide public schools, institutions and the community with reliable water | Dams constructed | Water | Construction of Itiira Kanjikeru Dams |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1140000 | 1140000 | 1140000 | County Treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
59 | Construction of Karimari Dam | Brick laying, site preparation | To provide public schools, institutions and the community with reliable water | Reliable water avaliable for domestic and irrigation use | Water | Construction of Karimari dam |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 637500 | 637500 | 637500 | County Treasury | N/A | 637500 | N/A | 637500 | 100% | 637500 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
60 | Provision of piped water for Itiira Secondary School and water kiosk | pipe laying, tanks installations and kiosk construction | To ensure durable and corrosion resistant water supply network | Safe and clean water easily accessible | Water | Provision of piped water for Itiira Secondary School and water kiosk |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
61 | Provision of piped water to Rukuriri Village and Water Kiosk | pipe laying, tank installation | To ensure durable and corrosion resistant water supply network | Water kiosk constructed and tanks installed | Water | Provision of piped water to Rukuriri Village and Water Kiosk |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
62 | Public Toilets Renovations And Development | Painting, brick laying | provide public institutions and school with clean rest rooms and help remain hygine | Public toilets developed | Water | Public toilets renovation and development |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 800000 | 800000 | 800000 | County Treasury | N/A | 800000 | N/A | 800000 | 100% | 800000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
63 | Construction of 10m3 Tank in Kyeni South and Kyeni North | Diging, pipe laying, painting | To provide public schools and institutions with reliable water | Tanks constructed | Water | Construction of 10m3 Tank in Kyeni South and Kyeni North | Kyeni |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 5392950 | 5392950 | 5392950 | County Treasury | N/A | 5392950 | N/A | 5392950 | 100% | 5392950 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
64 | Rehabilitation Of Tanks-Kyeni North And Kyeni South | painting, cleaning and repair of broken equipment | Ensure that the water being used is safe and clean | Tanks rehabilitated | Water | Rehabilitation of Tanks- Kyeninorth and south | Kyeni |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1800000 | 1800000 | 1800000 | County Treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
65 | Repair Of Strategic Bore Holes(Kamweli, Gitaraka,Makawani boreholes | Rehabilitation, cleaning | Restore access to safe and clean water | Borehole repaired | Water | Repair Of Strategic Bore Holes(Kamweli, Gitaraka,Makawani boreholes |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 152000 | N/A | 152000 | 100% | 152000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
66 | Purchase of water pipes-Kagaari North | procurement, transportation | to supply water to public schools and institutions | pipes bought | Water | Purchase of water pipes-Kagaari North |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1,800,000 | 1800000 | 1800000 | County Treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
67 | Domestic Water Pipes-Kyeni South | procurement, transportation | to supply water to public schools and institutions | pipes bought | Water | Domestic Water Pipes-Kyeni South |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 152000 | 152000 | 152000 | County Treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
68 | Pipes for Rutune-Karimari irrigation project | procurement, transportation | To supply water to the irrigation scheme | pipes bought | Water | Pipes for Retune-Karimari irrigation project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 380000 | 380000 | 380000 | County Treasury | N/A | 380000 | N/A | 380000 | 100% | 380000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
69 | Water pipes-Gaturi North | procurement, transportation | to supply water to public schools and institutions | pipes bought | Water | Water pipes-Gaturi north |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 760000 | 760000 | 760000 | County Treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
70 | Purchase of water pipes-Kagaari North | procurement, transportation | to supply water to public schools and institutions | pipes bought | Water | Purchase of water pipes-Kagaari North |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 304000 | 304000 | 304000 | County Treasury | N/A | 304000 | N/A | 304000 | 100% | 380000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
71 | Completion of JICA Water Project | Pipe laying, Construction | to supply water to public schools and institutions | water available in piblic institutions and community | Water | Completion of JICA Water Project |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 52250000 | 52250000 | 52250000 | County Treasury | N/A | 52250000 | N/A | 52250000 | 100% | 304000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
72 | Purchase of UPVC pipes for water projects in Embu county. | procurement, transportation | To provide access to clean and safe water for public schools and institutions | Timely delivery of UPVC pipes for all designated water projects | Water | Purchase of UPVC pipes for water projects in Embu county. | County wide | County wide |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 40562603 | 40562603 | 40562603 | County Treasury | N/A | 40562603 | N/A | 40562603 | 100% | 40562603 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
73 | Construction of water chambers, supply of pipes fittings for Embu county water projects. | construction, supply of water pipe fittings | To increase water infastructure lifespan | Improved water flow regulation and control | Water | Construction of water chambers, supply of pipes fittings for Embu county water projects. | County wide | County wide |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 1654275 | 1654275 | 1654275 | County Treasury | N/A | 1654275 | N/A | 1654275 | 100% | 1654275 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
74 | Water Project for Ngambari Primary School | Pipe laying, Installation of tanks | To provide students with clean water and a reliable one | water available for the students to use | Water | Water Project for Ngambari Primary School |  |  |  | Water | Water | Water | 30/6/2016 | 2015-01-07 | 30/6/2016 | 30/6/2016 | 760000 | 760000 | 760000 | County Treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
75 | Mbaruari Kiosk-Kwa Kavoi-Kandomba Water Project( buying pipes) | Construction, pipe laying | To provide a n accesible station where the community will be getting water | Water easily accessible | Water | Mbaruari Kiosk-Kwa Kavoi-Kandomba Water Project( buying pipes) |  |  |  | Water | Water | Water | 30/6/2016 | 1/7/1025 | 30/6/2016 | 30/6/2016 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
76 | Rain water harvesting (storage tanks) (water for children) | Tank installation, | To provide a sustainable and climate-resilient water source | Reliable water harvested | Water | Rain water harvesting (storage tanks) (water for children) |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 19400000 | 19400000 | 19400000 | County Treasury | N/A | 19400000 | N/A | 19400000 | 100% | 19400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
77 | Kalisa bore hole repair-Makima | Tank installation, | To avail clean and reliable water to public schools and institutions | Borehole repaired and water available for public school and institutions | Water | Kalisa bore hole repair-Makima |  | Makima |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 200000 | 200000 | 200000 | County Treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
78 | Ndune bore hole repair-Makima | Drilling site preparation, and pipoe laying | To avail clean and reliable water to public schools and institutions | Borehole repaired and water available for public school and institutions | water | Ndune bore hole repair-makima |  | Makima |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 200000 | 200000 | 200000 | County Treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
79 | Mbeti South Water Project | pipe laying, tank installation | To provide public schools with clean water for use | water available for the students and community to use | Water | Mbeti south water project |  | mbeti |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 7384000 | 7384000 | 7384000 | County Treasury | N/A | 7384000 | N/A | 7384000 | 100% | 7384000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
80 | Provision of water to Karaari,Kanthenge,Gitumbi,Kwa andu a Mbogo,Kiananu villages | pipe laying, tank installation | To provide public schools with clean water for use | water available for the public schools and village members to use | Water | Provision of water to Karaari,Kanthenge,Gitumbi,Kwa andu a Mbogo,Kiananu villages |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2280000 | 2280000 | 2280000 | County Treasury | N/A | 2280000 | N/A | 2280000 | 100% | 2280000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
81 | Construction of Itiira Kanjikeru Dams | Digging, brick laying | To provide reliable and sustainable water storage facility | Increased water storage capacity | Water | Construction of Itiira Kanjikeru Dams |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1140000 | 1140000 | 1140000 | County Treasury | N/A | 1140000 | N/A | 1140000 | 100% | 1140000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
82 | Automation of Kariguri Borehole-Kiambere | Automation of the borehole water supply system | To improve efficiency and reliabilty of the borehole | Automated and efficient bore hole operation | Water | Automation of Kariguri Borehole-Kiambere |  | Kiambere |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 820537.6 | 820537.6 | 820537.6 | County Treasury | N/A | 820537.6 | N/A | 820537.6 | 100% | 820537.6 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | Yes | Precautions taken and risks managed | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
93 | Karambari Kangiri Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Karambari Kangiri Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2999840 | 2999840 | 2999840 | County Treasury | N/A | 2999840 | N/A | 2999840 | 100% | 2999840 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
84 | Getua Kwa Mukiri Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Getua Kwa Mukiri Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2998317 | 2998317 | 2998317 | County Treasury | N/A | 2998317 | N/A | 2998317 | 100% | 2998317 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
85 | Karimari Earth Dam-Muminji | Diggging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Karimari Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2946846 | 2946846 | 2946846 | County Treasury | N/A | 2946846 | N/A | 2946846 | 100% | 2946846 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
86 | Kivue Kamangi Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Kivue Kamangi Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2953450.5 | 2953450.5 | 2953450.5 | County Treasury | N/A | 2953450.5 | N/A | 2953450.5 | 100% | 2953450.5 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
87 | Ivindi Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Ivindi Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2985780 | 2985780 | 2985780 | County Treasury | N/A | 2985780 | N/A | 2985780 | 100% | 2985780 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
88 | Kamukunga/Kamuturi Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Kamukunga/Kamuturi Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2890650 | 2890650 | 2890650 | County Treasury | N/A | 2890650 | N/A | 2890650 | 100% | 2890650 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
89 | Itiira Ciaitunduguru Earth Dam-Muminji | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Itiira Ciaitunduguru Earth Dam-Muminji |  | Muminji |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2286157.9 | 2286157.9 | 2286157.9 | County Treasury | N/A | 2286157.9 | N/A | 2286157.9 | 100% | 2286157.9 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
90 | Kikulani Earth Dam-Makima | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Kikulani Earth Dam-Makima |  | Makima |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 999831.9 | 999831.9 | 999831.9 | County Treasury | N/A | 999831.9 | N/A | 999831.9 | 100% | 999831.9 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
91 | Mbaci-Kianjoya Area Earth Dam-Evurore | Digging, construction | To provide an effective water storage facility | Increased water storage capacity | Water | Mbaci-Kianjoya Area Earth Dam-Evurore |  | Evurore |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3391551 | 3391551 | 3391551 | County Treasury | N/A | 3391551 | N/A | 3391551 | 100% | 3391551 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
92 | Provision of piped water for Itiira Secondary School and water kiosk | Pipe laying, Construction and tank installation | To provide a reliable and affordable water services | Increased access to clean water services | Water | Provision of piped water for Itiira Secondary School and water kiosk |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 80000 | 80000 | 80000 | County Treasury | N/A | 80000 | N/A | 80000 | 100% | 80000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
93 | Provision of piped water to Rukuriri Village and Water Kiosk | Pipe laying, Construction | To provide a reliable and affordable water services | Increased access to clean water services | Water | Provision of piped water to Rukuriri Village and Water Kiosk |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 600000 | 600000 | 600000 | County Treasury | N/A | 600000 | N/A | 600000 | 100% | 600000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
94 | Ugweri Market - Ndumari - Kasafari Pipeline | Procurement, pipe laying | To improve distribution of clean water | Improved access to clean water for public schools and intitutions | Water | Ugweri Market - Ndumari - Kasafari Pipeline |  | Ndumari |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
95 | Kigaa Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Kigaa Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
96 | Rutune-Karimari Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Rutune-Karimari Water Project |  | Karimari Water Project |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
97 | Kararitiri Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Kararitiri Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
98 | Iriamurai-Kathuuri Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Iriamurai-Kathuuri Water Project |  | Kathuuri Water Project |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
99 | Expansion Of EWASCO Water Pipeline Kiambi | pipe laying, digging | To ensure reliable, safe, and adequate water for the public institutions | Increased access to clean water | Water | Expansion Of EWASCO Water Pipeline Kiambi |  | Kiambi |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
100 | Extension Of EWASCO Water Pipeline Gachuriri - Makima Water Project | Digging, pipe laying | To extend water supply network | Expanded access to safe and reliable water | Water | Extension Of EWASCO Water Pipeline Gachuriri - Makima Water Project |  | makima |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | 3500000 | 3500000 | 100% | 3500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
101 | Completion Of Kithimu Domestic Water Project | Tank installation, pipe laying | Complete pending works to ensure full functionality of water supy | Improved domestic water supply within the th community | Water | Completion Of Kithimu Domestic Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
102 | Kigaa-Gicheche-Gichera Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Kigaa-Gicheche-Gichera Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
103 | Mutunduri-Gatituri-Karurina-Itabua Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Mutunduri-Gatituri-Karurina-Itabua Water Project |  | Itabua |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
104 | Kiambere-Mutuobare Water Project(Pipes And Tanks) | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Kiambere-Mutuobare Water Project(Pipes And Tanks) |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
105 | Nduuri-Ria Njagi-Kamugere-Kamugu Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Nduuri-Ria Njagi-Kamugere-Kamugu Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
106 | Kamumu-Kiathambu-Kabubua Kanyama-Kiogogo Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Kamumu-Kiathambu-Kabubua Kanyama-Kiogogo Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3260000 | 3260000 | 3260000 | County Treasury | N/A | 3260000 | N/A | 3260000 | 100% | 3260000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
107 | Mathirigakenda-Kabuguri Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Mathirigakenda-Kabuguri Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
108 | Karambari-Getua Water Project | pipe laying, tank installation | To improve access to clean water and reliable water | Incresed coverage and reliability of water supply services | Water | Karambari-Getua Water Project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
109 | Construction of Well at Nthagaiya-Kagaari South | Brick laying, drilling | To provide clean and accessible water source | Improved access to clean water for public schools and intitutions | Water | Construction of Well at Nthagaiya-Kagaari South |  | Kagaari South |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 650000 | 650000 | 650000 | County Treasury | N/A | 650000 | N/A | 650000 | 100% | 650000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
110 | Kamarandi CBO Water Intake | pipe installation, construction | Improve access to safe water for domestic use | reliable and safe water intake point established | Water | Kamarandi CBO Water Intake |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
111 | Domestic Water Distribution(Ewasco)-Mavuria | Construction, pipe installation | To build a clean and safe water supply system | Access to clean and safe water | Water | Domestic Water Distribution(Ewasco)-Mavuria |  | Mavuria |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
112 | Purchase of Water Pipes for Muthatari irrigation project | procurement, transportation | Improve water distribution efficiency for agricultural activities | Reliable water supply for irrigation supply | Water | Purchase of Water Pipes for Muthatari irrigation project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
113 | Purchase of Pipes-Nthawa | procurement, transportation | Improved water supply system | Reliable water supply | Water | Purchase of Pipes-Nthawa |  | Nthawa |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
114 | Laying of Pipes at Mbiruri-Runyenjes Central | Digging, pipe laying and back filling | To facilitate reliable and efficient water supply | Pipes installed and functioning efficiently | Water | Laying of Pipes at Mbiruri-Runyenjes Central |  | Runyenjes Central |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
115 | PVC Pipes of Various Sizes-Evurore | procurement, transportation | Install a reliable piping network | Completion of PVC pipeline network | Water | PVC Pipes of Various Sizes-Evurore |  | Evurore |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
116 | Water Pipes-Kagaari North | procurement, transportation | Install a reliable piping network | Completion of a reliable pipeline network | Water | Water Pipes-Kagaari North |  | Kagaari North |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 200000 | 200000 | 200000 | County Treasury | N/A | 200000 | N/A | 200000 | 100% | 200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
117 | Public Toilets Renovations And Development | Construction, plumbling, and lighting | To facilitate clean and safe sanititation services | Improved sanitation and hygiene standards in public spaces | Water | Public Toilets Renovations And Development |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 966 | 966 | 966 | County Treasury | N/A | 966 | N/A | 966 | 100% | 966 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
118 | Kigaa Water Office-Runyenjes Central | pipe laying, digging and construction | Enhance coordination and supervision of water supply operations | Improved operational service delivery | Water | Kigaa Water Office-Runyenjes Central |  | Runyenjes Central |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
119 | Rehabilitation Of Tanks-Kyeni North And Kyeni South | Restoring, upgrading existing water storage tanks | To ensure reliable storage and distribution of wayer | Restored and reliable water storage capacity | Water | Rehabilitation Of Tanks-Kyeni North And Kyeni South |  | Kyeni North And Kyeni South |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 5064815 | 5064815 | 5064815 | County Treasury | N/A | 5064815 | N/A | 5064815 | 100% | 5064815 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
120 | Repair Of Strategic Bore Holes(Kamweli,Gitaraka,Makahawani boreholes among others) | Cleaning, replacement of damaged components | Restore borehole to full operational capacity | Full functionality borehole | Water | Repair Of Strategic Bore Holes(Kamweli,Gitaraka,Makahawani boreholes among others) |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3799200 | 3799200 | 3799200 | County Treasury | N/A | 3799200 | N/A | 3799200 | 100% | 3799200 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
121 | Kikumini Market Borehole Drilling | procurement, drilling | Drill and construct a fully functional borehole for clean water extraction | Fully operational borehole | Water | Kikumini Market Borehole Drilling |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 4000000 | 4000000 | 4000000 | County Treasury | N/A | 4000000 | N/A | 4000000 | 100% | 4000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
122 | Water Tanks for Njeruri-Kyeni North | procurement, transportation | Construct durable and appropriate sized water tanks | Increased water storage capacity | Water | Water Tanks for Njeruri-Kyeni North |  | Kyeni North |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
123 | Water Tanks,Slaps and Water Connections-Kagaari North | leveling, tank installation | To install reliable water connections to deliver water efficiently | Functioning water connections | Water | Water Tanks,Slaps and Water Connections-Kagaari North |  | Kagaari North |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 498632.3 | 498632.3 | 498632.3 | County Treasury | N/A | 498632.3 | N/A | 498632.3 | 100% | 498632.3 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
124 | Desilting of Water Pans-Mavuria | Rehabilitation, removal of blockages | To ncrease the storage capacity of existing water pans | Restored water pans | Water | Desilting of Water Pans-Mavuria |  | Mavuria |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 561280 | 561280 | 561280 | County Treasury | N/A | 561280 | N/A | 561280 | 100% | 561280 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
125 | Water Project for Ngambari Primary School | pipe laying, tank installation | To provide safe,reliable source of clean water for the students and staff | Continuous access to clean water | Water | Water Project for Ngambari Primary School |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 760000 | 760000 | 760000 | County Treasury | N/A | 760000 | N/A | 760000 | 100% | 760000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
126 | Getua Water Tank and reticulation | procurement, construction of central water storage tank and development of a reticulation network | To improve water storage, disrtibution, and accessibiltiy | Improved water accessibility and supply reliabiltiy | Water | Getua Water Tank and reticulation |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
127 | Completion of Jica water project | pipe laying, tank installation and construction | To improve access to clean water and reliable water | Reliable access to clean and safe water | Water | Completion of Jica water project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 17605938 | 17605938 | 17605938 | County Treasury | N/A | 17605938 | N/A | 17605938 | 100% | 17605938 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
128 | Kune distribution network | Digging, pipe laying | To deliver clean, safe, and reliable water | Improved water coverage and reliability | water | Kune distribution network |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
129 | Nginda/Ngandori Water system | Diggging, construction | To provide safe and accessible water | Safe and sustainable water supply | Water | Nginda/Ngandori Water system |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
130 | Runyenjes central distribution network | pipe laying, tank installation | To deliver clean, safe, and reliable water | Improved water coverage and reliability | Water | Runyenjes central distribution network |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
131 | Green paradise water project in Ishiara | pipe laying, tank installation | To improve access to clean water and reliable water | Reliable access to clean and safe water | Water | Green paradise water project in Ishiara |  | Ishiara |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
132 | Iriari water project | pipe laying, tank installation | To improve access to clean water and reliable water | Reliable access to clean and safe water | Water | Iriari water project |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
133 | Gaturi south distribution network | Digging, pipe laying | To deliver clean, safe, and reliable water | Improved water coverage and reliability | Water | Gaturi south distribution network |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
134 | Karimari Rutune completion work | procurement | To improve access to clean water and reliable water | Reliable access to clean and safe water | Water | Karimari Rutune completion work |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
135 | Mbeti south distribution network | pipe laying, tank installation | To deliver clean, safe, and reliable water | Improved water coverage and reliability | Water | Mbeti south distribution network |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
136 | Muthanthara water pipeline | Digging, pipe laying | To improve distribution of clean water | Reliable delivery of clean and safe water | Water | Muthanthara water pipeline |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
137 | Hydro-geological survey of Newsite borehole | Identifying suitable drilling site,determining the depth of water table | To ensure successful development | Accurate identification of the best drilling location | Water | Hydro-geological survey of Newsite borehole |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 3000000 | 250000 | 250000 | County Treasury | N/A | 250000 | N/A | 250000 | 100% | 250000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
138 | Supply of UPVC Pipes-EWASCO (Supply of pipes and construction works to the following; Kawanjara-Ugweri Line(5.3KM), Muchonoke-Siakago Line (5.4KM), Gachoka-Gachuriri Line (6.6KM) and Kiambere-Mutuobare line (7.9KM) | Procurement, delivery, and quality assurance | To provide high quality UPVC pipes | Availability of high-quality upvc PIPES | Water | Suooly of UPVC PIPES |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 31188550.75 | 31188550.75 | 31188550.75 | County Treasury | N/A | 31188550.75 | N/A | 31188550.75 | 100% | 31188550.75 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
139 | Construction of BPTS | Development, design, and erection | To ensure compliance with safety, environmental, and technical standards | Operational BPTS facility | Water | Construction of BPTS |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 1625810.4 | 1625810.4 | 1625810.4 | County Treasury | N/A | 1625810.4 | N/A | 1625810.4 | 100% | 1625810.4 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
140 | Supply of UPVC Pipes-JICA | Procurement, delivery, and quality assurance | To provide high quality UPVC pipes | Availability of high-quality upvc PIPES | Water | Supply of UPVC Pipes-JICA |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 7235007 | 7235007 | 7235007 | County Treasury | N/A | 7235007 | N/A | 7235007 | 100% | 7235007 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
141 | Rehabilitation and fencing of Makawani Borehole | Cleaning, desilting and repair | To ensure safe and reliable water supply | Improved and sustainable water supply | Water | Rehabilitation and fencing of Makawani Borehol |  |  |  | Water | Water | Water | 30/6/2017 | 2016-01-07 | 30/6/2017 | 30/6/2017 | 379000 | 379000 | 379000 | County Treasury | N/A | 379000 | N/A | 379000 | 100% | 379000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kune Water Project – Nthawa Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Kune Water Project – Nthawa Ward |  | Nthawa |  | Water | Water | Water | 26/06/2018 | 2018-04-04 | 26/06/2-18 | 20/06/2018 | 37115430 | 37115430 | 3590430 | County Treasury | N/A | 37115430 | N/A | 3590430 | 65% | 3590430 | 0 | 0 | Stalled | 65% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Itabua Muthatari Water Project – Mbeti North Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Itabua Muthatari Water Project – Mbeti North Ward |  | Mbeti north |  | Water | Water | Water | 26/06/2018 | 2018-04-04 | 26/06/2018 | 26/06/2018 | 1999126.76 | 1999126.76 | 1999126.76 | County Treasury | N/A | 1999126.76 | N/A | 1999126.76 | 100% | 1999126.76 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kune-Kthagutari Water Project – Evurore Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Kune-Kthagutari Water Project – Evurore Ward |  | Evurore |  | Water | Water | Water | 2018-12-06 | 2018-04-04 | 12/062018 | 2018-12-06 | 2738844.6 | 2738844.6 | 2738844.6 | County Treasury | N/A | 2738844.6 | N/A | 2738844.6 | 100% | 2738844.6 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Makutano Borehole Water Distribution Supply – Mwea Ward | project description for a borehole water distribution supply | To increase water storage capacity | Increased water storage capacity | Water | Makutano Borehole Water Distribution Supply – Mwea Ward |  | Mwea |  | Water | Water | Water | 30/05/2018 | 2018-04-04 | 30/05/2018 | 30/05/2018 | 999995 | 999995 | 999995 | County Treasury | N/A | 999995 | N/A | 999995 | 100% | 999995 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Runyenjes Pipeline Extension | Procurement, pipe installation | To expand water distribution system | Expanded access to safe and reliable water | Water | Construction of Runyenjes Pipeline Extension |  | Runyenjes |  | Water | Water | Water | 20/06/2018 | 2018-04-04 | 20/06/2018 | 20/06/2018 | 1990513 | 1990513 | 1990513 | County Treasury | N/A | 1990513 | N/A | 1990513 | 100% | 1990513 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kangaru & Nthambo Water Project – Kirimari Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Kangaru & Nthambo Water Project – Kirimari Ward |  | kirimari |  | Water | Water | Water | 17/01/209 | 2018-04-04 | 17/01/2019 | 17/01/2019 | 1999997 | 1999997 | 1999997 | County Treasury | N/A | 1999997 | N/A | 1999997 | 100% | 1999997 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Expansion and Rehabilitation of Muchonoke Earth Dam | Repair, reinforcement | To restore and enhance the functionality of the existing dam | Dam restored and functioning effiently | Water | Expansion and Rehabilitation of Muchonoke Earth Dam |  | Muchonoke |  | Water | Water | Water | 25/10/2019 | 17/06/2018 | 25/10/2019 | 25/10/2019 | [6 empty] | N/A
| Construction of Kabachi Water Project – Nthawa Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Kabachi Water Project – Nthawa Ward |  | Nthawa |  | Water | Water | Water | 26/06/2018 | 2018-04-04 | 26/062018 | 26/06/2018 | 348497 | 348497 | 348497 | County Treasury | N/A | 348497 | N/A | 348497 | 100% | 348497 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kariguri Karambari Dam | Construction, design | To improve water storage, supply and management | Water available | Water | Construction of Kariguri Karambari Dam |  | Kariguri |  | Water | Water | Water | 27/06/2019 | 2018-04-04 | 27/06/2019 | 27/06/2019 | 3994199 | 3994199 | 3994199 | County Treasury | N/A | 3994199 | N/A | 3994199 | 100% | 3994199 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Karimari – Kiang’anja Village Pipeline | Procurement, construction | To provide access to clean and safe water for public schools and institutions | water available to pubic shools and institutions | Water | Construction of Karimari – Kiang’anja Village Pipeline |  | kirimari |  | Water | Water | Water | 20/06/2018 | 2018-04-04 | 26/06/2018 | 26/06/2018 | 1248472.6 | 1248472.6 | 1248472.6 | County Treasury | N/A | 1248472.6 | N/A | 1248472.6 | 100% | 1248472.6 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Gitiburi Water Project – Nthawa Ward | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Gitiburi Water Project – Nthawa Ward |  | Nthawa |  | Water | Water | Water | 2019-12-06 | 2018-04-04 | 2019-12-06 | 2019-12-06 | 349719 | 349719 | 349719 | County Treasury | N/A | 349719 | N/A | 349719 | 100% | 349719 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Ena – Kawanjara – Ugweri - Karurumo Pipeline | Procurement, construction | To provide access to clean and safe water for public schools and institutions | water available to pubic shools and institutions | Water | Construction of Ena – Kawanjara – Ugweri - Karurumo Pipeline |  | Ugweri |  | Water | Water | Water | 18/06/2018 | 2018-04-04 | 18/06/2018 | 18/06/2018 | 2999690 | 2999690 | 2999690 | County Treasury | N/A | 2999690 | N/A | 2999690 | 100% | 2999690 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Gicherori – Kibugu Pipeline Extension 1.2Km Manyatta – Nginda Ward | Procurement, construction | To ensure access to clean and safe water | Improved water reliability and safety | Water | Gicherori – Kibugu Pipeline Extension 1.2Km Manyatta – Nginda Ward |  | Manyatta |  | Water | Water | Water | 2018-06-06 | 2018-04-04 | 2018-06-06 | 2018-06-06 | 3493200 | 3493200 | 3493200 | County Treasury | N/A | 3493200 | N/A | 3493200 | 100% | 3493200 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kagumori Water Scheme – Gaturi South Ward | Procurement, construction | To provide clean and reliable water supply | Reliable and safe water supply | Water | Construction of Kagumori Water Scheme – Gaturi South Ward |  | Gaturi South |  | Water | Water | Water | 16/06/2018 | 2018-04-04 | 16/06/2018 | 16/06/2018 | 1488260 | 1488260 | 1488260 | County Treasury | N/A | 1488260 | N/A | 1488260 | 100% | 1488260 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Distribution of Water Gachuriri and Kamunyange – Mbeti South Ward | Procurement, construction | To ensure access to clean and safe water | Improved water accessibility and supply reliabiltiy | Water | Distribution of Water Gachuriri and Kamunyange – Mbeti South Ward |  | Mbeti south |  | Water | Water | Water | 19/06/2018 | 2018-04-04 | 19/06/2018 | 19/06/2018 | 1985500 | 1985500 | 1985500 | County Treasury | N/A | 1985500 | N/A | 1985500 | 100% | 1985500 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Mukororia – Ngoce Water Project | Tank instalation, construction | To develop a sustainable and reliable water source | Reliable water supply supply system | Water | Construction of Mukororia – Ngoce Water Project |  | Ngoce |  | Water | Water | Water | 26/06/2018 | 2018-04-04 | 26/06/2018 | 26/06/2018 | 3241238.7 | 3241238.7 | 3241238.7 | County Treasury | N/A | 3241238.7 | N/A | 3241238.7 | 100% | 3241238.7 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Purchase of Runyenjes Central Pipes | Procurement, delivery, and quality assurance | Improved water supply system | Reliable water supply | Water | Purchase of Runyenjes Central Pipes |  | Runyenjes |  | Water | Water | Water | 23/06/2018 | 2018-04-04 | 23/06/2018 | 23/06/2018 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kandomba Pipeline/ Water Kiosk – Muminji Ward | Procurement, constructionof water kiosk, pipe installation | To improve access to clean water and reliable water | Improved quality of access to clean water | Water | Construction of Kandomba Pipeline/ Water Kiosk – Muminji Ward |  | Kandomba |  | Water | Water | Water | 26/06/2018 | 2018-04-04 | 26/06/2018 | 26/06/2018 | 993928.6 | 993928.6 | 993928.6 | County Treasury | N/A | 993928.6 | N/A | 993928.6 | 100% | 993928.6 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Survey and Design for Mutuobare Karura Water Supply System | Feasibility study | To ensure a quality water supply system | Feasibility study report including source selection and system design options | Water | Consultancy Services for Survey and Design for Mutuobare Karura Water Supply System |  | Karura |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 2496454 | 2496454 | 2496454 | County Treasury | N/A | 2496454 | N/A | 2496454 | 100% | 2496454 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kamburu Machang’a Water Supply System | Construction, pipe laying | To improve access to clean water and reliable water | Improved quality of access to clean water | Water | Construction of Kamburu Machang’a Water Supply System |  |  |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 1879700 | 1879700 | 1879700 | County Treasury | N/A | 1879700 | N/A | 1879700 | 100% | 1879700 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Gwakarigu Earth Dam Kaithungu | Procurement, design, site preparations | To increse water availabiltfy for irrigation, livestock and domestic use | A fully functional earth dam with safe water storage capacity | Water | Construction of Gwakarigu Earth Dam Kaithungu |  | Kathingu |  | Water | Water | Water | 2019-10-06 | 2019-09-05 | 2019-10-06 | 2019-10-06 | 2333804 | 2333804 | 2333804 | County Treasury | N/A | 2333804 | N/A | 2333804 | 100% | 2333804 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Wamikuyu Earth Dam – Mwea Ward | Procurement, design, site preparations | To increase water availabilty for irrigation, livestock and domestic use | A fully functional earth dam with safe water storage capacity | Water | Construction of Wamikuyu Earth Dam – Mwea Ward |  | Mwea |  | Water | Water | Water | 2019-10-06 | 2019-09-05 | 2019-10-06 | 2019-10-06 | 2400000 | 2400000 | 2400000 | County Treasury | N/A | 2400000 | N/A | 2400000 | 100% | 2400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Survey and Design for Gitaru – Mathigira Kenda Pipeline | Feasibility study | To ensure quality water pipeline system | Feasibility study report including source selection and system design options | Water | Consultancy Services for Survey and Design for Gitaru – Mathigira Kenda Pipeline |  | Gitaru |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 1499883 | 1499883 | 1499883 | County Treasury | N/A | 1499883 | N/A | 1499883 | 100% | 1499883 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Riakanau Malikini Water Supply | Pipe laying, design, and tank installation | To increase water availability and accessibility | clean water available for domestic, agricultural and institutonal use | Water | Construction of Riakanau Malikini Water Supply |  |  |  | Water | Water | Water | 25/06/2019 | 2019-09-05 | 25/06/2019 | 25/06/2019 | 1968120 | 1968120 | 1968120 | County Treasury | N/A | 1968120 | N/A | 1968120 | 100% | 1968120 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Makima – Kiveli Water Supply Phase I – Makima Ward | Pipe laying, design, and tank installation | To incerease water availability and accessibillity | clean water available for domestic, agricultural and institutonal use | Water | Construction of Makima – Kiveli Water Supply Phase I – Makima Ward |  | Makima |  | Water | Water | Water | 2021-01-02 | 2019-09-05 | 2021-01-02 | 2021-01-02 | 999944 | 999944 | 999944 | County Treasury | N/A | 999944 | N/A | 999944 | 100% | 999944 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Acquisition of Pipes for Muthambiri and Kabachi – Nthawa Ward | Procurement, delivery, and quality assurance | To supply durable and compliment pipes | Identification of required pipe types | Water | Acquisition of Pipes for Muthambiri and Kabachi – Nthawa Ward |  | Nthawa |  | Water | Water | Water | 2019-12-06 | 2019-09-05 | 2019-12-06 | 2019-12-06 | 392645 | 392645 | 392645 | County Treasury | N/A | 392645 | N/A | 392645 | 100% | 392645 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Survey and Design for Mbondoni – Kithecu Water Supply Project | Feasibility study | To ensure quality water pipeline system | Feasibility study report including source selection and system design options | Water | Consultancy Services for Survey and Design for Mbondoni – Kithecu Water Supply Project |  | Mbandoni |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 1975000 | 1975000 | 1975000 | County Treasury | N/A | 1975000 | N/A | 1975000 | 100% | 1975000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kiageni, Mwanyani, Riakanau, Malikini, Kithecu Water Supply System | Pipe laying, design, and tank installation | To improve accesibilty okf clean and reliable water | clean water available for domestic, agricultural and institutonal use | Water | Construction of Kiageni, Mwanyani, Riakanau, Malikini, Kithecu Water Supply System |  |  |  | Water | Water | Water | 2019-08-11 | 2019-10-05 | 2019-08-11 | 2019-08-11 | 48844361.3 | 48844361.3 | 48844361.3 | County Treasury | N/A | 48844361.3 | N/A | 48844361.3 | 100% | 48844361.3 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Mashamba Sand Dam – Makima Ward | Procurement, design, site preparations | To increase water availabilty for irrigation, livestock and domestic use | A fully functional earth dam with safe water storage capacity | Water | Construction of Mashamba Sand Dam – Makima Ward |  | Makima |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 999980.18 | 999980.18 | 999980.18 | County Treasury | N/A | 999980.18 | N/A | 999980.18 | 100% | 999980.18 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kiamurwa Water Intake | Design, procurement | To provide a dependable and efficient water abstraction point | A fully functional water intake facility | Water | Construction of Kiamurwa Water Intake |  |  |  | Water | Water | Water | 2021-04-02 | 2019-09-05 | 2021-04-02 | 2021-04-02 | 3496640.64 | 3496640.64 | 3496640.64 | County Treasury | N/A | 3496640.64 | N/A | 3496640.64 | 100% | 3496640.64 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Ewasco Line – Ndutori, Rukuriri, Itira, Karambari and Kirii, Kavairi Shopping Centre and Water Kiosk – Muminji Ward | Procurement, design, and pipe laying | To icrease water accessibilty an d reliability | Water available and easily accessible | Water | Construction of Ewasco Line – Ndutori, Rukuriri, Itira, Karambari and Kirii, Kavairi Shopping Centre and Water Kiosk – Muminji Ward |  | Muminji |  | Water | Water | Water | 27/06/2019 | 2019-09-05 | 27/06/2019 | 27/06/2019 | 2296544.8 | 2296544.8 | 2296544.8 | County Treasury | N/A | 2296544.8 | N/A | 2296544.8 | 100% | 2296544.8 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kabachi Water Project – Purchase of Pipes – Nthawa Ward | Tank installation, Procurement, and pipe laying | To increase water supply and accessibility | Water easily accessible | Water | Kabachi Water Project – Purchase of Pipes – Nthawa Ward |  | Nthawa |  | Water | Water | Water | 2019-07-06 | 2019-09-05 | 2019-07-06 | 2019-07-06 | 999490.8 | 999490.8 | 999490.8 | County Treasury | N/A | 999490.8 | N/A | 999490.8 | 100% | 999490.8 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Gwakigumba Earth Dam – Kiambere Ward | Design, procurement | To increase water availabilty for irrigation, livestock and domestic use | A fully functional earth dam with safe water storage capacity | Water | Construction of Gwakigumba Earth Dam – Kiambere |  | Kiambere |  | Water | Water | Water | 2021-01-02 | 2019-09-05 | 2021-01-02 | 2021-01-02 | 2359143 | 2359143 | 2359143 | County Treasury | N/A | 2359143 | N/A | 2359143 | 100% | 2359143 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Minoori Water Project – Mbeti South Ward | Tank installation, Procurement, and pipe laying | To improve access to clean water and reliable water | Increased number of households with access to clean and safe water | Water | Construction of Minoori Water Project – Mbeti South Ward |  | Mbeti south |  | Water | Water | Water | 2019-07-06 | 2019-07-05 | 2019-07-06 | 2019-07-06 | 1499566.8 | 1499566.8 | 1499566.8 | County Treasury | N/A | 1499566.8 | N/A | 1499566.8 | 100% | 1499566.8 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water at Gachuriri Main Line | Pipe laying, procurement | To incerease water availability and accessibillity | Water available and easily accessible | Water | Supply of Water at Gachuriri Main Line |  | Gachuriri |  | Water | Water | Water | 19/06/2019 | 2019-09-05 | 19/06/2019 | 19/06/2019 | 1999798.24 | 1999798.24 | 1999798.24 | County Treasury | N/A | 1999798.24 | N/A | 1999798.24 | 100% | 1999798.24 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Survey and Design for Kiageni Mwanyani Water Supply Project | Feasibility study | To ensure quality water supply system | Feasibility study report including source selection and system design options | Water | Consultancy Services for Survey and Design for Kiageni Mwanyani Water Supply |  |  |  | Water | Water | Water | 25/06/2019 | 2019-09-05 | 25/06/2019 | 25/06/2019 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Sedimentation Basin for Ngandori Nginda Water Project | Design, procurement | To reduce turbidity and suspended solids in raw water | A fully functional sedimentation basin | water | Construction of Sedimentation Basin for Ngandori Nginda Water Project |  |  |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2999899.1 | 2999899.1 | 2999899.1 | County Treasury | N/A | 2999899.1 | N/A | 2999899.1 | 100% | 2999899.1 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Sectoral Plans for Water and Sanitation | Baseline assessment, stakeholder engagement | To assess the current state of water and sanitation services in the region | Comprehensive water and sanitation sectoral plans with phased implementation stretegies | Water | Consultancy Services for Sectoral Plans for Water and Sanitation |  |  |  | Water | Water | Water | 28/01/2020 | 18/12/2019 | 28/01/2020 | 28/01/2020 | 1690000 | 1690000 | 1690000 | County Treasury | N/A | 1690000 | N/A | 1690000 | 100% | 1690000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Consultancy Services for Sectoral Plans for Irrigation and Drainage | Baseline assessment, stakeholder engagement | To assess the current state of water, irrigation and drainage services | Comprehensive water and irrigation system | Water | Consultancy Services for Sectoral Plans for Sectoral Plans for Irrigation and Drainage |  |  |  | Water | Water | Water | 17/02/2020 | 18/12/2019 | 17/02/2020 | 17/02/2020 | 1295000 | 1295000 | 1295000 | County Treasury | N/A | 1295000 | N/A | 1295000 | 100% | 1295000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation of Water Supply – Nthawa Ward (AGPO) | Restoring, upgrading existing water storage tanks | To provide clean and safe water | A fully rehabilitated water supply system | Water | Rehabilitation of Water Supply – Nthawa Ward (AGPO) |  | Nthawa |  | Water | Water | Water | 26/08/2021 | 2020-05-03 | 26/08/2021 | 26/08/2021 | 3587656.5 | 3587656.5 | 3587656.5 | County Treasury | N/A | 3587656.5 | N/A | 3587656.5 | 100% | 3587656.5 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Upgrading Of Kyeni Water And Sanitation Company System | Infrastructure upgrades, ICTand digital system, customer service mechanisms | To improve the quality and reliability of water supply and sanitation services | Incresed service coverage and improved water quality and pressure | Water | Upgrading Of Kyeni Water And Sanitation Company System |  |  |  | Water | Water | Water | 26/08/2021 | 2020-05-03 | 26/08/2021 | 26/08/2021 | 10000000 | 10000000 | 10000000 | County Treasury | N/A | 10000000 | N/A | 10000000 | 100% | 10000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kianjogu Dam-Muminji | Procurement, design | To provide reliable and safe water for irrigation and domestic use | Fully finctional dam with safe and reliable water | Water | Kianjogu Dam-Muminji |  | Muminji |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Desilting Of Mbarwari Dam -Muminji | Desilting operations, post-desilting operations | To restore the dams original water storage capacity | Increased water storage capacity of the dam | Water | Desilting Of Mbarwari Dam -Muminji |  | Muminji |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Platform For Water Tanks | Site preparation, constructions and structural design | To provide structural sound and elevated base for water storage tanks | A high-quality, long lasting platform ready for water tank installation | Water | Platform For Water Tanks |  |  |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 512132 | 512132 | 512132 | County Treasury | N/A | 512132 | N/A | 512132 | 100% | 512132 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction Of Kabachi Water Project | Procurement, tank installation, and pipe laying | To provide clean, safe and reliable water for community use | Clean and safe water available for community use | Water | Construction Of Kabachi Water Project |  |  |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 348497 | 348497 | 348497 | County Treasury | N/A | 348497 | N/A | 348497 | 100% | 348497 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kangaru, Nthambo Water Project | Procurement, tank installation, and pipe laying | To provide clean, safe and reliable water for community use | Clean and safe water available for domestic water | Water | Kangaru, Nthambo Water Project |  | Nthambo |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1999997 | 1999997 | 1999997 | County Treasury | N/A | 1999997 | N/A | 1999997 | 100% | 1999997 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction Of Kariguri-Karambari Earth Dam | design, procurement | To provide reliable and safe water for irrigation and domestic use | Fully finctional dam with safe and reliable water | Water | Construction Of Kariguri-Karambari Earth Dam |  | Karambari |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 3994199 | 3994199 | 3994199 | County Treasury | N/A | 3994199 | N/A | 3994199 | 100% | 3994199 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kune, Kathangutari Water Project | Procurement, tank installation, and pipe laying | To provide clean, safe and reliable water for community use | clean and safe water avalable for domestic use | Water | Kune, Kathangutari Water Project |  | Kathangutari |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2738844 | 2738844 | 2738844 | County Treasury | N/A | 2738844 | N/A | 2738844 | 100% | 2738844 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Scooping Of Kirimiuru Dam-Mbeti South | Rehabilitation, site preparation and spillway cleaning | Restore the dams original water storage capacity | Increased water storage capacity of the dam | Water | Scooping Of Kirimiuru Dam-Mbeti South |  | Mbeti south |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply Of Pipes And Storage WaterTanks-Mbeti South | procurement, quality assurance | To ensure availability of quality materials for efficient water distribution systems | Reliable and long-lasting piping infrastructure | Water | Supply Of Pipes And Storage WaterTanks-Mbeti South |  | Mbeti south |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1500000 | 1500000 | 1500000 | County Treasury | N/A | 1500000 | N/A | 1500000 | 100% | 1500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Extension Of EWASCO Water Lines-Mavuria | survey and design, supply of materials and installatin of water lines | To expand water service coveage to unconnected communities | Increased number of households with access to piped water | Water | Extension Of EWASCO Water Lines-Mavuria |  | Mavuria |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| KENGEN Water Line Extension- Mavuria | Procurement, design, and pipe laying | To expand water service coveage to unconnected communities | Increased number of households with access to piped water | Water | KENGEN Water Line Extension- Mavuria |  | Mavuria |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2500000 | 2500000 | 2500000 | County Treasury | N/A | 2500000 | N/A | 2500000 | 100% | 2500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Nguthi EWASCO Piped Water-Muminji | pipedline network installation, water source development | To provide continuous access to clean and safe piped water | Increased access to piped potable water in the target area | Water | Nguthi EWASCO Piped Water-Muminji |  | Muminji |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1200000 | 1200000 | 1200000 | County Treasury | N/A | 1200000 | N/A | 1200000 | 100% | 1200000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Drilling And Solar Equipping Of Kamaunju Borehole-Kiambere | Borehole drilling, solar pump installation | To provide a clean, reliable, and a year-round water source | Reliable clean and safe water source | Water | Drilling And Solar Equipping Of Kamaunju Borehole-Kiambere |  | Kiambere |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 3500000 | 3500000 | 3500000 | County Treasury | N/A | 3500000 | N/A | 3500000 | 100% | 3500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation To Solar Power Of Ntharawe Borehole-Kiambere | Cleaning, installation of suitable solar submersible pump | To restore sustainable, safe water access to the community | Clean water supply restored | Water | Rehabilitation To Solar Power Of Ntharawe Borehole-Kiambere |  | Kiambere |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation To Electric Power Of Gacabari Borehole-Kiambere | Installation of electric water pump, restoration | To rehabilitate an existing non functional borehole | A fully rehabilitated and operational borehole using electric power | Water | Rehabilitation To Electric Power Of Gacabari Borehole-Kiambere |  | Kiambere |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1800000 | 1800000 | 1800000 | County Treasury | N/A | 1800000 | N/A | 1800000 | 100% | 1800000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply Of Water To Kitololoni- Makima | Pipe laying, design, and tank installation | To provide safe and accessible water | Clean, safe and reliable water available for use | Water | Supply Of Water To Kitololoni- Makima |  | Makima |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1450000 | 1450000 | 1450000 | County Treasury | N/A | 1450000 | N/A | 1450000 | 100% | 1450000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rukuriri Water Pipes-Kyeni North | Procurement, delivery, quality assurance | To provide high quality pipes for wateer supply | High quality water pipes supplied | Water | Rukuriri Water Pipes-Kyeni North |  | Kyeni North |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Karaba Dispensary Borehole-Power Connection Pump, Elevated Tanks And Distribution-Mwea | Borehole drilling, power pump installation | To provide a reliable and clean water supply for the effective operation of the dispensary | Reliable, safe water supply available everytime | Water | Karaba Dispensary Borehole-Power Connection Pump, Elevated Tanks And Distribution-Mwea |  | Mwea |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Musingini Borehole –Distribution To Musingini Market-Mwea | Design, pipe laying and construction | To provide the market with clean and safe water for use | Clean, safe and reliable water available for use | Water | Musingini Borehole –Distribution To Musingini Market-Mwea |  | Mwea |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 700000 | 700000 | 700000 | County Treasury | N/A | 700000 | N/A | 700000 | 100% | 700000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Malikini Borehole-Connection to the Primary and Secondary Schools, tanks and Community Water Point-Mwea | Construction, design, tank installation | To provide the students with clean and safe water to use | Clean and safe water available in the school compound | Water | Malikini Borehole-Connection to the Primary and Secondary Schools, tanks and Community Water Point-Mwea |  | Mwea |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 750000 | 750000 | 750000 | County Treasury | N/A | 750000 | N/A | 750000 | 100% | 750000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Enhancement Of Water Supply-Nthawa | System upgrade assessment and planning | To increase the coverage, reliability and cpacity of the existing water suplly system | Enhanced access to safe and adequate water for institutions | Water | Enhancement Of Water Supply-Nthawa |  | Nthawa |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 3000000 | 3000000 | 3000000 | County Treasury | N/A | 3000000 | N/A | 3000000 | 100% | 3000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Kune-Kathagutari-Ibutuka Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Kune-Kathagutari-Ibutuka Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 1000000 | 1000000 | 1000000 | County Treasury | N/A | 1000000 | N/A | 1000000 | 100% | 1000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Gaikungugu-Muti Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Gaikungugu-Muti Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Mbaci-Kianjoya Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Mbaci-Kianjoya Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Mbothere-Murangu Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Mbothere-Murangu Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Kavengero-Kanduviu Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Kavengero-Kanduviu Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Kathigagaceru-Ndithiri Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Kathigagaceru-Ndithiri Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Kigwambiti-Kambu Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Kigwambiti-Kambu Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 400000 | 400000 | 400000 | County Treasury | N/A | 400000 | N/A | 400000 | 100% | 400000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation Of Mutirieguru Primary School Water Pipeline-Evurore | Excavation and remove of damaged pipes | To restore and improve the functionality of the existing water pipeline system | Fully rehabilitated and operational water pipeline system | Water | Rehabilitation Of Mutirieguru Primary School Water Pipeline-Evurore |  | Evurore |  | Water | Water | Water | 19/01/2021 | 13/02/2020 | 19/01/2021 | 19/01/2021 | 500000 | 500000 | 500000 | County Treasury | N/A | 500000 | N/A | 500000 | 100% | 500000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Desilting of Mbarwari Dam – Muminji Ward | Repair, desilting operations | To remove accumulated silt to restore the dams original storage capacity | Restored dam storage capacity | Water | Desilting of Mbarwari Dam – Muminji Ward |  | Muminji |  | Water | Water | Water | 30/06/2020 | 19/06/2020 | 30/06/2020 | 30/06/2020 | 985512.1 | 985512.1 | 985512.1 | County Treasury | N/A | 985512.1 | N/A | 985512.1 | 100% | 985512.1 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes – Mbeti South Ward | Procurement, delivery | To procure and supply high-quality water pipes | Timely delivery of high-quality water pipes | Water | Supply of Water Pipes – Mbeti South Ward |  | Mbeti south |  | Water | Water | Water | 2020-06-04 | 2020-09-03 | 2020-06-04 | 2020-06-04 | 3492076 | 3492076 | 3492076 | County Treasury | N/A | 3492076 | N/A | 3492076 | 100% | 3492076 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation of Electric Power of Gacavari Borehole | Testing and commissioning, rapair and technical assessment | To restore functionality of the electric power supply for the borehole pump system | Fully restored and operational electric power system for the borehole | Water | Rehabilitation of Electric Power of Gacavari Borehole |  | Gacavari |  | Water | Water | Water | 18/02/2021 | 24/10/2020 | 18/02/2021 | 18/02/2021 | 1793992.5 | 1793992.5 | 1793992.5 | County Treasury | N/A | 1793992.5 | N/A | 1793992.5 | 100% | 1793992.5 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Karaba Dispensary Borehole – Mwea Ward | Drilling, installation of storage tanks | Ensure consistent access to clean and safe water for the dispensary | Increased efficiency and effectiveness of healthcare service delivery | Water | Karaba Dispensary Borehole – Mwea Ward |  | Mwea |  | Water | Water | Water | 23/04/2021 | 19/06/2020 | 23/04/2021 | 23/04/2021 | 1971809.55 | 1971809.55 | 1971809.55 | County Treasury | N/A | 1971809.55 | N/A | 1971809.55 | 100% | 1971809.55 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kianjogu Dam – Muminji Ward | Site preparation, constructions and structural design | To provide reliable and safe water for irrigation and domestic use | Fully finctional dam with safe and reliable water | Water | Construction of Kianjogu Dam – Muminji Ward |  | Muminji |  | Water | Water | Water | 30/06/2020 | 19/06/2020 | 30/06/2020 | 30/06/2020 | 1860928.7 | 1860928.7 | 1860928.7 | County Treasury | N/A | 1860928.7 | N/A | 1860928.7 | 100% | 1860928.7 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kengen Water Line (Extension) – Makima Ward | Site survey, pipe laying | Extend the communal water supply to underseved | Increased water access | Water | Kengen Water Line (Extension) – Makima Ward |  | Makima |  | Water | Water | Water | 2020-07-07 | 19/06/2020 | 2020-07-07 | 2020-07-07 | 2499108 | 2499108 | 2499108 | County Treasury | N/A | 2499108 | N/A | 2499108 | 100% | 2499108 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation of Solar Power for Ntharawe Borehole | Repair of faulty solar pannels, technical assessment | To restore functionality of the borehole by rehabilitating its solar power system | Restoration of reliable water supply for the community | Water | Rehabilitation of Solar Power for Ntharawe Borehole |  | Ntharawe |  | Water | Water | Water | 18/02/2021 | 19/06/2020 | 18/02/2021 | 18/02/2021 | 1999521.25 | 1999521.25 | 1999521.25 | County Treasury | N/A | 1999521.25 | N/A | 1999521.25 | 100% | 1999521.25 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Water Extension – Mavuria Ward | Site survey, pipe laying | Extend the communal water supply to underseved | Increased water access | Water | Water Extension – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2021-08-11 | 25/06/2021 | 2021-08-11 | 2021-08-11 | 1999840 | 1999840 | 1999840 | County Treasury | N/A | 1999840 | N/A | 1999840 | 100% | 1999840 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Pipes for Various Pipelines – Evurore Ward | procurement, transportation | To support the expansion of the water distribution network | Availability of required pipe materials for pipeline installation | Water | Supply of Pipes for Various Pipelines – Evurore Ward |  | Evurore |  | Water | Water | Water | 2022-04-03 | 2022-02-02 | 2022-04-03 | 2022-04-03 | 2000000 | 2000000 | 2000000 | County Treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Hire of Machinery for Dams – Muminji Ward | Hire and deploy machinery on site, | Facilitate efficient constrection of dams through the use of appropriate machinery | Timely and efficient completion of dam excavation and destilting | Water | Hire of Machinery for Dams – Muminji Ward |  | Muminji |  | Water | Water | Water | 2022-04-03 | 26/06/2021 | 2022-04-03 | 2022-04-03 | 2698740 | 2698740 | 2698740 | County Treasury | N/A | 2698740 | N/A | 2698740 | 100% | 2698740 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Unblocking of Karaba Borehole – Mwea Ward | Removal of blockages, mechanical cleaning | To restore the functionality of the borehole by removing blockages | Restoration of clean and safe water supply frm the borehole | Water | Unblocking of Karaba Borehole – Mwea Ward |  | Mwea |  | Water | Water | Water | 2022-04-03 | 25/06/2021 | 2022-04-03 | 2022-04-03 | 1140076 | 1140076 | 1140076 | County Treasury | N/A | 1140076 | N/A | 1140076 | 100% | 1140076 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Environment and Social Impact Report Assessment for Marikiti Market | Stakeholder consultations, baseline data collection | To ensure the project complies with legal and regulatory requirements | A clear understanding of the environmental and social risks and opportunities associated with the market project | Water | Environment and Social Impact Report Assessment for Marikiti Market |  |  |  | Water | Water | Water | 2022-08-03 | 2022-02-02 | 2022-08-03 | 2022-08-03 | 1458120 | 1458120 | 1458120 | County Treasury | N/A | 1458120 | N/A | 1458120 | 100% | 1458120 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rehabilitation of Existing Borehole – Mavuria Ward | Mechanical clening, repair and desilting the borehole | To restore the functionality and water yield of the existiong borehole | Fully rehabilitated and operational borrehole with improved water flow | Water | Rehabilitation of Existing Borehole – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2021-04-11 | 25/06/2021 | 2021-04-11 | 2021-04-11 | 499960 | 499960 | 499960 | County Treasury | N/A | 499960 | N/A | 499960 | 100% | 499960 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Provision of Water Tanks – Mavuria Ward | procurement, transportation | To facilitate reliable water holding facilities | High quality water holding capacities | Water | Provision of Water Tanks – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2021-03-11 | 25/06/2021 | 2021-03-11 | 2021-03-11 | 599720 | 599720 | 599720 | County Treasury | N/A | 599720 | N/A | 599720 | 100% | 599720 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Water Supply at Makima – Makima Ward | Procurement, pipe laying and excavation | To ensure access to clean and safe water | Reliable access to clean and safe water | Water | Water Supply at Makima – Makima Ward |  | Makima |  | Water | Water | Water | 2022-11-02 | 29/06/2021 | 2022-11-02 | 2022-11-02 | 1466062 | 1466062 | 1466062 | County Treasury | N/A | 1466062 | N/A | 1466062 | 100% | 1466062 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Mbarwari Ewasco Line – Muminji Ward | Site survey, pipe laying | To extend the Ewasco water distribution network to underserved areas | Reliable and continuous supply of clean water to pupblic instituions | Water | Mbarwari Ewasco Line – Muminji Ward |  | Muminji |  | Water | Water | Water | 15/10/2021 | 25/06/2021 | 15/10/2021 | 15/10/2021 | 999804 | 999804 | 999804 | County Treasury | N/A | 999804 | N/A | 999804 | 100% | 999804 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Renovation of Kanjari Tanks – Mavuria Ward | Repair, cleaning and desludging of tanks interiors | To restore the structure integrity, storage capacity | Fully renovated water tants with improved water retention and safety | water | Renovation of Kanjari Tanks – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2021-03-11 | 25/06/2021 | 2021-03-11 | 2021-03-11 | 399910 | 399910 | 399910 | County Treasury | N/A | 399910 | N/A | 399910 | 100% | 399910 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Purchase and Installation of Water Tanks at Ngiiri Market – Muminji Ward | procurement, construction | To facilitate reliable water holding facilities | Installed water tanks functioning to full capacity | Water | Purchase and Installation of Water Tanks at Ngiiri Market – Muminji Ward |  | Muminji |  | Water | Water | Water | 2021-03-11 | 25/06/2021 | 2021-03-11 | 2021-03-11 | 499800 | 499800 | 499800 | County Treasury | N/A | 499800 | N/A | 499800 | 100% | 1498422 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Desilting of Dams – Mavuria Ward | Sediment removal, transport and disposal | To restore the reserviors original storage capacity | A fully desilted dam | Water | Desilting of Dams – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2021-01-09 | 25/06/2021 | 2021-01-09 | 2021-01-09 | 1498422 | 1498422 | 1498422 | County Treasury | N/A | 1498422 | N/A | 1498422 | 100% | 1498422 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kivue Base Spring – Water Piping and Storage Project | Pipe line installation, construction of storage facilities and spring source development | To capture and convey clean spring water efficiently from source to end user | A constructed spring intake structure to ensure clean water capture | Water | Construction of Kivue Base Spring – Water Piping and Storage Project |  |  |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 1499295 | 1499295 | 1499295 | County Treasury | N/A | 1499295 | N/A | 1499295 | 100% | 1499295 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Kabuguri Water Line – Mavuria Ward | survey and design, supply of materials and installatin of water lines | To provide a reliable and safe water supply to underseved communities | Potential water pipeline installed | Water | Construction of Kabuguri Water Line – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 999344 | 999344 | 999344 | County Treasury | N/A | 999344 | N/A | 999344 | 100% | 999344 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes – Kagaari South Ward | Procurement, Transportation, qualty confirmation | To procure and supply high-quality water pipes | Quality pipes distributed | Water | Supply of Water Pipes – Kagaari South Ward |  | Kigaari south |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 699948 | 699948 | 699948 | County Treasury | N/A | 699948 | N/A | 699948 | 100% | 699948 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Purchase of Tanks, Pipes and Fittings for Gitare Water Line – Kiambere Ward | Procurement, qauality assurance | To ensure | Quality pipes distributed | Water | Purchase of Tanks, Pipes and Fittings for Gitare Water Line – Kiambere Ward |  | Kiambere |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 1491300 | 1491300 | 1491300 | County Treasury | N/A | 1491300 | N/A | 1491300 | 100% | 1491300 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Drilling and Equipping of Boreholes – Muminji Ward | Procurement, Pipe laying, tank installation | To provide clean and safe water | Clean and safe water available to the community use | Water | Drilling and Equipping of Boreholes – Muminji Ward |  | Muminji |  | Water | Water | Water | 27/06/2023 | 24/04/2023 | 27/06/2023 | 27/06/2023 | 3495315 | 3495315 | 3495315 | County Treasury | N/A | 3495315 | N/A | 3495315 | 100% | 3495315 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kirathe Borehole – Mavuria Ward | procurement, drilling | To provide cleand and safe water | Reliable, safe and clean water available | Water | Kirathe Borehole – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 21/03/2024 | 24/04/2023 | 21/03/2024 | 21/03/2024 | 2499940 | 2499940 | 2499940 | County Treasury | N/A | 2499940 | N/A | 2499940 | 100% | 2499940 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Repair of Boreholes in Mwea, Makima, Mbeere South, Mavuria, Kiambere, Nthawa and Kyeni South Wards | Procurement, construction | To provide clean and reliable water supply | Clean and reliable water available for domestic use | Water | Repair of Boreholes in Mwea, Makima, Mbeere South, Mavuria, Kiambere, Nthawa and Kyeni South Wards |  | Mwea, makima, Mbeere south, Mavuria, Kiambere, Nthawa and kyeni south |  | Water | Water | Water | 27/06/2023 | 23/05/2023 | 27/06/2023 | 27/06/2023 | 5957196 | 5957196 | 5957196 | County Treasury | N/A | 5957196 | N/A | 5957196 | 100% | 5957196 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Ewasco Water Project for Tende Karurina – Gaturi South Ward | Procurement, pipe laying and excavation | To ensure reliable water for the community and public institutions | water easily accessible for community and public institutions use | Water | Ewasco Water Project for Tende Karurina – Gaturi South Ward |  | Gaturi South |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 1486336 | 1486336 | 1486336 | County Treasury | N/A | 1486336 | N/A | 1486336 | 100% | 1486336 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Water Pipes for Nguviu Kibugu Water Project – Nginda Ward | Site survey, pipe laying | To install a durable and effective water distribution network | Improved water delivery with reduced service interuptions | Water | Water Pipes for Nguviu Kibugu Water Project – Nginda Ward |  | Nginda |  | Water | Water | Water | 2023-12-06 | 24/04/2023 | 2023-12-06 | 2023-12-06 | 1970960 | 1970960 | 1970960 | County Treasury | N/A | 1970960 | N/A | 1970960 | 100% | 1970960 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Pipes for Gitaru Water Line – Mavuria Ward | procurement, quality assurance | To ensure use of durable and corrosion-resistant piping materials | Enhanced water supply reliability | Water | Supply of Pipes for Gitaru Water Line – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 29/06/2023 | 24/04/2023 | 29/06/2023 | 29/06/2023 | 499848 | 499848 | 499848 | County Treasury | N/A | 499848 | N/A | 499848 | 100% | 499848 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes for Various Projects – Evurore Ward | procurement, quality assurance | To ensure use of durable and corrosion-resistant piping materials | Enhanced water supply reliability | Water | Supply of Water Pipes for Various Projects – Evurore Ward |  | Evurore |  | Water | Water | Water | 30/06/2023 | 24/04/2023 | 30/06/2023 | 30/06/2023 | 2488296 | 2488296 | 2488296 | County Treasury | N/A | 2488296 | N/A | 2488296 | 100% | 2488296 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes for Kyewasco – Kyeni North Ward | procurement, quality assurance | To ensure use of durable and corrosion-resistant piping materials | Enhanced water supply reliability | Water | Supply of Water Pipes for Kyewasco – Kyeni North Ward |  | Kyeni North |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 499835.6 | 499835.6 | 499835.6 | County Treasury | N/A | 499835.6 | N/A | 499835.6 | 100% | 499835.6 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Ivondo Borehole Improvement – Mavuria Ward | Rehabilitation, upgrading of pump system and installation of water storage components | To restore and enhance the boreholes water production capacity | Increased and consistent water yield | Water | Ivondo Borehole Improvement – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 2495477.5 | 2495477.5 | 2495477.5 | County Treasury | N/A | 2495477.5 | N/A | 2495477.5 | 100% | 2495477.5 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes – Mbeti South Ward | procurement, quality assurance | To ensure use of durable and corrosion-resistant piping materials | Enhanced water supply reliability | Water | Supply of Water Pipes – Mbeti South Ward |  | Mbeti south |  | Water | Water | Water | 2023-07-06 | 24/04/2023 | 2023-07-06 | 2023-07-06 | 1998568 | 1998568 | 1998568 | County Treasury | N/A | 1998568 | N/A | 1998568 | 100% | 1998568 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Supply of Water Pipes for Ndamunge – Kagaari North Ward | procurement, quality assurance | To ensure use of durable and corrosion-resistant piping materials | Enhanced water supply reliability | Water | Supply of Water Pipes for Ndamunge – Kagaari North Ward |  | Kagaari north |  | Water | Water | Water | 27/06/2023 | 24/04/2023 | 27/06/2023 | 27/06/2023 | 999750 | 999750 | 999750 | County Treasury | N/A | 999750 | N/A | 999750 | 100% | 999750 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Construction of Mugoro Gitituri Water Storage Tank – Muminji Ward | Site survey, foundation preparation, desing and constriction | To provide safe and reliable water storage to meet daily and emergency needs | Increased water storage capacity and supply security | Water | Construction of Mugoro Gitituri Water Storage Tank – Muminji Ward |  | Muminji |  | Water | Water | Water | 2023-02-05 | 24/04/2023 | 2023-02-05 | 2023-02-05 | 1499900 | 1499900 | 1499900 | County Treasury | N/A | 1499900 | N/A | 1499900 | 100% | 1499900 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Cieria Ewasco Line – Muminji Ward | Site survey and route mapping, excavation and pipe laying | Toensure a consistent and safe supply of clean water | Improved water access and distribution efficiency | Water | Cieria Ewasco Line – Muminji Ward |  | Muminji |  | Water | Water | Water | 2024-12-06 | 2024-12-02 | 2024-12-06 | 2024-12-06 | 1197079 | 1197079 | 1197079 | County Treasury | N/A | 1197079 | N/A | 1197079 | 100% | 1197079 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Operationalization of Water Drilling Rig | Assessment and site selection, rig mobilization and setup | To provide sustainable access to groundwater for communities, institutions | Fully functional water drilling rig system | Water | Operationalization of Water Drilling Rig |  |  |  | Water | Water | Water |  | 2024-07-03 |  |  | 2252400 | 2252400 | 2252400 | County Treasury | N/A | 2252400 | N/A | 2252400 | 100% | 2252400 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Installation of Water Tanks at Karurina – Gaturi South Ward | Pocurement, site assessment and preparation and installation and fitting | To enhance water storage for continuous availabilty during supply interruptions | Operational water storege tanks serving households, school and clinics | Water | Installation of Water Tanks at Karurina – Gaturi South Ward |  | Gaturi South |  | Water | Water | Water | 25/04/2024 | 30/01/2024 | 25/04/2024 | 25/04/2024 | 1496360 | 1496360 | 1496360 | County Treasury | N/A | 1496360 | N/A | 1496360 | 100% | 1496360 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Powering and Elevation of Mutus Borehole – Mavuria Ward | Pump installation, elevated tank construction | To enable reliable, powered water extraction from the borehole | Fully operational borehole with a sustainable power source | Water | Powering and Elevation of Mutus Borehole – Mavuria Ward |  | Mavuria |  | Water | Water | Water | 2024-03-06 | 2024-12-02 | 2024-03-06 | 2024-03-06 | 2499684.25 | 2499684.25 | 2499684.25 | County Treasury | N/A | 2499684.25 | N/A | 2499684.25 | 100% | 2499684.25 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Drilling of Borehole and installation of Powered Pump System with a Raised Storage Tank of Micegethiu Borehole – Muminji Ward | Borehole drilling, pump installation and power system setp | To provide a dependable and clean water source through bprehole driling | A fully functionality borehole system with clean and accessible water | Water | Drilling of Borehole and installation of Powered Pump System with a Raised Storage Tank of Micegethiu Borehole – Muminji Ward |  | Muminji |  | Water | Water | Water | 13/06/2024 | 20/12/2023 | 13/06/2024 | 13/06/2024 | 3498984 | 3498984 | 3498984 | County Treasury | N/A | 3498984 | N/A | 3498984 | 100% | 3498984 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Repair of Ngiiri Storage Tank – Muminji Ward | Structural repairs, cleaning and waterproofing and coating | To restore the integrity and safety of existing water storage tanks | Fully rehabiitated and operational water storage tanks | Water | Repair of Ngiiri Storage Tank – Muminji Ward |  | Muminji |  | Water | Water | Water | 20/06/2024 | 2024-12-02 | 20/06/2024 | 20/06/2024 | 997368 | 997368 | 997368 | County Treasury | N/A | 997368 | N/A | 997368 | 100% | 997368 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Rerouting of Kyewasco Pipeline | Site survey and planning, design and mapping | To ensure efficient and leak-free pipeline network | A fullyfunctional and leak-free pipeline network | Water | Rerouting of Kyewasco Pipeline |  | Kyeni North |  | Water | Water | Water | 22/04/2024 | 25/01/2024 | 22/04/2024 | 22/04/2024 | 3998062 | 3998062 | 3998062 | County Treasury | N/A | 3998062 | N/A | 3998062 | 100% | 3998062 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Purchase of Drilling Rig Casings | Procurement, logistics and delivery | To ensure availabilty of essential casing materials for ongoing and future borehole drilling operations | Timely procucerement and delivery of required casing materials | Water | Purchase of Drilling Rig Casings |  |  |  | Water | Water | Water | 2024-12-04 | 21/02/2024 | 2024-12-04 | 2024-12-04 | 2997503.8 | 2997503.8 | 2997503.8 | County Treasury | N/A | 2997503.8 | N/A | 2997503.8 | 100% | 2997503.8 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Kirithiga Ewasco Line – Muminji Ward | Planning and design, procurement and excavation and pipe laying | To provide a safe and efficent means of transporting waterr from the source to user | A fully operational water line delivering clean water to intend users | Water | Kirithiga Ewasco Line – Muminji Ward |  | Muminji |  | Water | Water | Water | 2024-11-04 | 2024-12-02 | 2024-11-04 | 2024-11-04 | 1399899 | 1399899 | 1399899 | County Treasury | N/A | 1399899 | N/A | 1399899 | 100% | 1399899 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Purchase of Drilling Rig | Procurement, logistics and delivery | Increase the capacity for independent water borehole drilling | Fully acquired and operarional drilling rig available for field use | Water | Purchase of Drilling Rig |  |  |  | Water | Water | Water | 2024-11-04 | 2023-07-12 | 13/05/2024 | 13/05/2024 | 39450000 | 39450000 | 39450000 | County Treasury | N/A | 39450000 | N/A | 39450000 | 100% | 39450000 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
| Augmentation of Mbondoni, Kithecu and Mwanyani Water Pipeline | Design and planning, procurement and assessment of existing infrastucture | Increase the water-carrying capacity of the pipeline system to meet current and future demand | Upgraded and expanded pipeline infrastructure capable of delivering suffient water to target areas | Water | Augmentation of Mbondoni, Kithecu and Mwanyani Water Pipeline |  |  |  | Water | Water | Water | 13/06/2024 | 19/01/2024 | 13/06/2024 | 13/06/2024 | 4995980.2 | 4995980.2 | 4995980.2 | County Treasury | N/A | 4995980.2 | N/A | 4995980.2 | 100% | 4995980.2 | 0 | 0 | Completed | 100% | N/A | N/A | N/A | N/A | N/A | NO | Compete | N/A | No | N/A | Yes | Environmental action taken and risks addressed | Yes | project was opperational | opperational
Report prepared by:
Designation:
Signature:
Date:
Report approved by:
Designation:
Signature:
Date:

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled