## instructions1
INSTRUCTIONS ON COMPLETION OF PROJECT STOCK TAKE TEMPLATE
1. All fields are mandatory and should be populated.
2. DO NOT EDIT the CONFIGURATION worksheet.
3. ONLY populate rows applicable in your respective Counties &Ward Location(s) and Hide the rest of the rows (DO NOT DELETE the Rows).
4. The scope of this exercise is projects started between the year 2013 and 30th June, 2024
5.Remember to SAVE the document after populating the required details in the worksheet.

## Project Stocktaking Template
PROJECT DETAILS | [6 empty] | PROJECT LOCATION |  |  | IMPLEMENTATION DETAILS | [6 empty] | FINANCIAL INFORMATION |  |  |  |  | DISBURSMENT |  |  |  | EXPENDITURE |  |  | PROJECT STATUS |  |  | ACTIONS FOR STALLED |  |  |  | RISKS AND RECOMMENDATIONS |  |  | CLIMATE & DISASTER RISK SCREENING |  | ENVIRONMENTAL , SOCIAL AND OCCUPATIONAL HEALTH, SAFETY AND GENDER SCREENING |  | TECHNICAL, FINANCIAL, AND ECONOMIC VIABILITY SCREENING |  | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
| Purchase Of Automation Equip. Software, Design, For Records Mwea Scheme Land | Procurement, software acquisition, system design | To digitize and centralize all land scheme records | A fully digitized and automated record-keeping system for land schemes |  | Purchase Of Automation Equip. Software, Design, For Records Mwea Scheme Land |  | Mwea |  | Land | Land | Land | 30/6/2015 | 2014-01-07 | 30/6/2015 | N/A | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 350379.9 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land Purchase Advert &Wat |  |  |  | l | Land Purchase Advert &Wat |  |  |  | Land | Land | Land | 30/6/2015 | 2014-01-07 | 30/6/2015 | N/A | 10000000 | 10000000 | 10000000 | County treasury | N/A | 10000000 | N/A | 10000000 | 100% | 122148 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Geo Referencing Services Of 331 Parcels At Mwea Scheme | Geo-referencing survey plan, | To support smarter land use, better planning, and efficient management of spatial resources | Geographic data aligning with real-world locations | Physical planning | Geo Referencing Services Of 331 Parcels At Mwea Scheme |  | Mwea |  | Physical planning | Physical planning | Physical planning | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 2665095 | 2665095 | 2665095 | County treasury | N/A | 2665095 | N/A | 2665095 | 100% | 2665095 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Geo Referencing Services Of 258 Parcels At Mwea Scheme | Geo-referencing survey plan, | To support smarter land use, better planning, and efficient management of spatial resources | Geographic data aligning with real-world locations | Physical planning | Geo Referencing Services Of 258 Parcels At Mwea Scheme |  | Mwea |  | Physical planning | Physical planning | Physical planning | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 2686080 | 2686080 | 2686080 | County treasury | N/A | 2686080 | N/A | 2686080 | 100% | 2686080 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Geo-Referencing At Mwea 58 Parcels Of Land | Geo-referencing survey plan, | To support smarter land use, better planning, and efficient management of spatial resources | Geographic data aligning with real-world locations | Physical planning | Geo-Referencing At Mwea 58 Parcels Of Land |  | Mwea |  | Physical planning | Physical planning | Physical planning | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 2495260 | 2495260 | 2495260 | County treasury | N/A | 2495260 | N/A | 2495260 | 100% | 2495260 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Geo-Referencing At Mwea 58 Parcels Of Land | Geo-referencing survey plan, | To support smarter land use, better planning, and efficient management of spatial resources | Geographic data aligning with real-world locations | Physical planning | Geo-Referencing At Mwea 58 Parcels Of Land |  | Mwea |  | Physical planning | Physical planning | Physical planning | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 1876000 | 1876000 | 1876000 | County treasury | N/A | 1876000 | N/A | 1876000 | 100% | 1876000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Geo-Referencing At Mwea 58 Parcels Of Land-Other Parcels Of Lands | Geo-referencing survey plan, | To support smarter land use, better planning, and efficient management of spatial resources | Geographic data aligning with real-world locations | Physical planning | Geo-Referencing At Mwea 58 Parcels Of Land-Other Parcels Of Lands |  | Mwea |  | Physical planning | Physical planning | Physical planning | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A |  |  |  | County treasury | N/A |  | N/A | [12 empty] | N/A | N/A | N/A
| Rehabilitation ,Paving And Cabros For Runyenjes Town And Ishiara. | Cabro paving, Drainage works, landscaping and road marking | To enhance mobility and raod safety within renyenjes town | Economic growth, reduced dust and erosion | Urban development | Rehabilitation ,Paving And Cabros For Runyenjes Town And Ishiara. |  | Runyenjes |  | Minning house | Minning house | Minning house | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 50800000 | 50800000 | 50800000 | County treasury | N/A | 50800000 | N/A | 50800000 | 100% | 17362160 | N/A | N/A | Ongoing | 34% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Paving Works At Runyenjes & Ishiara | Site preparation, paving installation, drainage enhancement | To enhanc walkability and usability of town streets and footpaths | Improved public service delivery, and raised quality life for residents | Urban development | Paving Works At Runyenjes & Ishiara |  | Runyenjes |  | Urban development | Urban development | Urban development | 30/6/2019 | 2018-01-07 | 30/6/2019 | N/A | 3536090 | 3536090 | 3536090 | County treasury | N/A | 3536090 | N/A | 3536090 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Provision Of Georeferencing Services For 401 Percels Of Land At Mwea Scheme | Collection and review of existing land data, field data collection, coordinate computation and mapping | To provide accurate spatial referencing | Improved planning, resource allocation and land related decision making | Physical planning | Provision Of Georeferencing Services For 401 Percels Of Land At Mwea Scheme |  | Mwea |  | Land | Land | Land | 30/6/2020 | 2019-01-07 | 30/6/2020 | N/A |  |  |  | County treasury | N/A |  | N/A | [12 empty] | N/A | N/A | N/A
| Town Beautification (Planting Trees) Programme-Kirimari | Site identification and preparation, tree planting | To enhance thee beauty and livability of the town | Transformed town with greener, cleaner and more vibrant urban space | Urban development | Town Beautification (Planting Trees) Programme-Kirimari |  | Kirimari |  | Urban development | Urban development | Urban development | 30/6/2020 | 2019-01-07 | 30/6/2020 | N/A | 2097600 | 2097600 | 2097600 | County treasury | N/A | 2097600 | N/A | 2097600 | 100% | 2097600 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Purchase Of Land (Kagaari/Kanja 5352) | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Purchase Of Land (Kagaari/Kanja 5352) |  |  |  | Land | Land | Land | 30/6/2021 | 2020-01-07 | 30/6/2021 | N/A | 620000 | 620000 | 620000 | County treasury | N/A | 620000 | N/A | 620000 | 100% | 620000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Purchase Of Land (Kagaari/Kanja 5351) | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Purchase Of Land (Kagaari/Kanja 5351) |  |  |  | Land | Land | Land | 30/6/2021 | 2020-01-07 | 30/6/2021 | N/A | 620000 | 620000 | 620000 | County treasury | N/A | 620000 | N/A | 620000 | 100% | 620000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Purchase Of Land (Kagaari/Kanja 5147) | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Purchase Of Land (Kagaari/Kanja 5147) |  |  |  | Land | Land | Land | 30/6/2021 | 2020-01-07 | 30/6/2021 | N/A | 2100000 | 2100000 | 2100000 | County treasury | N/A | 2100000 | N/A | 2100000 | 100% | 2100000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Purchase Of Land (Kagaari/Kanja 8527) | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Purchase Of Land (Kagaari/Kanja 8527) |  |  |  | Land | Land | Land | 30/6/2021 | 2020-01-07 | 30/6/2021 | N/A | 1850000 | 1850000 | 1850000 | County treasury | N/A | 1850000 | N/A | 1850000 | 100% | 1850000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Public Land At Njagairi In Gaturi South | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Acquisition Of Public Land At Njagairi In Gaturi South |  |  |  | Land | Land | Land | 30/6/2023 | 2022-01-07 | 30/6/2023 | N/A | 10000000 | 10000000 | 10000000 | County treasury | N/A | 10000000 | N/A | 10000000 | 100% | 9000000 | N/A | N/A | Ongoing | 90% | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A
| Acquisition Of Land For Karaba Stock Market-Mwea | Site identification, valuation, negotiation and purchase, and documentation | To secure land ownesrship for planned developments | A suitable land acquired | Land | Acquisition Of Land For Karaba Stock Market-Mwea |  | Mwea |  | Land | Land | Land | FY 2023/2025 | FY 2022/2024 | FY 2023/2025 | N/A | 3100000 | 3100000 | 3100000 | County treasury | N/A | 3100000 | N/A | 3100000 | 100% | 3000000 | N/A | N/A | Ongoing | 97% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Access Road In Kyeni South | Identification for affected parcels, stakeholder engagement, land acquisition and compesantion | To secure legal and physical access to land for road constructed | Enhanced transport efficiency, and grown socio-economy | Land | Land For Access Road In Kyeni South |  | Kyeni |  | Land | Land | Land | 30/6/023 | 2022-01-07 | 30/6/023 | N/A | 520000 | 520000 | 520000 | County treasury | N/A | 520000 | N/A | 520000 | 100% | 520000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Access Road In Kyeni South | Identification for affected parcels, stakeholder engagement, land acquisition and compesantion | To secure legal and physical access to land for road constructed | Enhanced transport efficiency, and grown socio-economy | Land | Land For Access Road In Kyeni South |  | Kyeni |  | Land | Land | Land | 30/6/023 | 2022-01-07 | 30/6/023 | N/A | 620000 | 620000 | 620000 | County treasury | N/A | 620000 | N/A | 620000 | 100% | 620000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Kathuriri Dispensary In Runyenjes Central | Site identification and preparation, building and construction | To improve access to affordable and quality primary healthcare services | Improved community healthcare | Land | Land For Kathuriri Dispensary In Runyenjes Central |  | Runyenjes |  | Land | Land | Land | FY 2022/2023 | FY 2021/2022 | FY 2022/2023 | N/A | 3800000 | 3800000 | 3800000 | County treasury | N/A | 3800000 | N/A | 3800000 | 100% | 3600000 | N/A | N/A | Ongoing | 95% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Access Road In Kithimu | Identification for affected parcels, stakeholder engagement, land acquisition and compesantion | To secure legal and physical access to land for road constructed | Enhanced transport efficiency, and grown socio-economy | Land | Land For Access Road In Kithimu |  | Kithimu |  | Land | Land | Land | FY 2022/2023 | FY 2021/2022 | FY 2022/2023 | N/A | 875000 | 875000 | 875000 | County treasury | N/A | 875000 | N/A | 875000 | 100% | 875000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Access Road In Kithimu | Identification for affected parcels, stakeholder engagement, land acquisition and compesantion | To secure legal and physical access to land for road constructed | Enhanced transport efficiency, and grown socio-economy | Land | Land For Access Road In Kithimu |  | Kithimu |  | Land | Land | Land | 30/6/2022 | 2021-01-07 | 30/6/2022 | N/A | 520000 | 520000 | 520000 | County treasury | N/A | 520000 | N/A | 520000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Access Road In Kithimu | Identification for affected parcels, stakeholder engagement, land acquisition and compesantion | To secure legal and physical access to land for road constructed | Enhanced transport efficiency, and grown socio-economy | Land | Land For Access Road In Kithimu |  | Kithimu |  | Land | Land | Land | FY 2022/2023 | FY 2021/2022 | FY 2022/2023 | N/A | 1030000 | 1030000 | 1030000 | County treasury | N/A | 1030000 | N/A | 1030000 | 100% | 1030000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Land For Kwa Andu Ambogo Dispensary | Site identification and preparation, building and construction | To improve access to affordable and quality primary healthcare services | Improved community healthcare | Land | Land For Kwa Andu Ambogo Dispensary |  |  |  | Land | Land | Land | FY 2022/2023 | FY 2021/2022 | FY 2022/2023 | N/A | 2000000 | 2000000 | 2000000 | County treasury | N/A | 2000000 | N/A | 2000000 | 100% | 2000000 | N/A | N/A | Complete | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Kawanjara Climate Smart Container Market | Site preparation, container odification and installation | To provide a safe, clean and dignified space for vendors and consumers | Enhanced food and goods security | Urban development | Kawanjara Climate Smart Container Market |  | Kawanjara |  | Urban development | Urban development | Urban development | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 4180000 | 4180000 | 4180000 | County treasury | N/A | 4180000 | N/A | 4180000 | 100% | 3891243 | N/A | N/A | Ongoing | 93% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Counter Fund For Kawanjara Climate Smart Container Market | Procurement, container modification and installation | To prvide a clean, accessible and morden market space | Efficient infrastructure that boosts local trade | Urban development | Counter Fund For Kawanjara Climate Smart Container Market |  | Kawanjara |  | Urban development | Urban deveopment | Urban development | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 6000000 | 6000000 | 6000000 | County treasury | N/A | 6000000 | N/A | 6000000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Completion Of Ardhi House And Gis Premises | Structural completion, mechanical and electrical works, ICT infrastructure and furnishing | To provide a permanent, morden work sapce for land and GIS departments | A fully functional Ardhi House and GIS premises | Minning house | Completion Of Ardhi House And Gis Premises |  |  |  | Minning house | Minning house | Minning house | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 4500000 | 4500000 | 4500000 | County treasury | N/A | 4500000 | N/A | 4500000 | 100% | 2066273 | N/A | N/A | Ongoing | 46% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Rehabilitation Of Existing Government Houses | Structural repairs, interior upgrades | To restore government housing units to safe and livable standards | Restored dignity, functionality and safety to government housing | Urban development | Rehabilitation Of Existing Government Houses |  |  |  | Urban development | Urban development | Urban development | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Renovation Of Geographical Information System (Gis) Laboratory | Procurement, | To modernize the physical infrastructure to support current and future GIS technologies | A technologically advanced GIS lab equiped to support research, teaching, and project-based learning | Urban development | Renovation Of Geographical Information System (Gis) Laboratory |  |  |  | Urban development | Urban development | Urban development | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 4000000 | 4000000 | 4000000 | County treasury | N/A | 4000000 | N/A | 4000000 | 100% | 3999425 | N/A | N/A | Ongoing | 99.9% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Development Of County Spatial Plan | Data collection, analyzing and stakeholder engagement | To identify opportunities and constraints for future development, ensuring balanced urban and rural growth | A comprehensive County spatial plan document | Urban development | Development Of County Spatial Plan |  |  |  | Urban development | Urban development | Urban development | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 15000000 | 15000000 | 15000000 | County treasury | N/A | 15000000 | N/A | 15000000 | 100% | 14999999 | N/A | N/A | Ongoing | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Public Land At Njagairi In Gaturi South | Site identification, valuation, negotiation and purchase, and documentation | To indentify and secure suitable public land required for priority government projects and services | Successful transfer of land ownership | Land | Acquisition Of Public Land At Njagairi In Gaturi South |  | Gaturi south |  | Land | Land | Land | FY 2023/2024 | FY 2022/2023 | FY 2023/2024 | N/A | 10000000 | 10000000 | 10000000 | County treasury | N/A | 10000000 | N/A | 10000000 | 100% | 9900000 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Land For Kamugere Dispensary In Gaturi North | Site identification and preparation, building and construction | To acquire a strategically located parcel of land that is accessible to the community | Secure legaland ownership for dispensary construction | Land | Acquisition Of Land For Kamugere Dispensary In Gaturi North |  | Gaturi north |  | Land | Land | Land | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Land For Kamugere Dispensary In Kagaari North | Site identification and preparation, building and construction | To acquire a strategically located parcel of land that is accessible to the community | Secure legaland ownership for dispensary construction | Land | Acquisition Of Land For Kamugere Dispensary In Kagaari North |  | Kagaari north |  | Land | Land | Land | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Land For Kamugere Dispensary Near Catholic- Gaturi North | Site identification and preparation, building and construction | To acquire a strategically located parcel of land that is accessible to the community | Secure legaland ownership for dispensary construction | Land | Acquisition Of Land For Kamugere Dispensary Near Catholic- Gaturi North |  | Gaturi north |  | Land | Land | Land | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 1500000 | 1500000 | 1500000 | County treasury | N/A | 1500000 | N/A | 1500000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Land For Access Road-Kagaari South | Land identification, title verification, landowners engagement, negotiation and purchase | To enable the development of a functional and safe access road | Succesful acquisition of land parcels for road construction | Land | Acquisition Of Land For Access Road-Kagaari South |  | Kagaari north |  | Land | Land | Land | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 1000000 | 1000000 | 1000000 | County treasury | N/A | 1000000 | N/A | 1000000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Acquisition Of Land For Access Road-Kyeni South | Land identification, title verification, landowners engagement, negotiation and purchase | To enable the development of a functional and safe access road | Succesful acquisition of land parcels for road construction | Land | Acquisition Of Land For Access Road-Kyeni South |  | Kyeni south |  | Land | Land | Land | 30/6/2024 | 2023-01-07 | 30/6/2024 | N/A | 700000 | 700000 | 700000 | County treasury | N/A | 700000 | N/A | 700000 | 100% | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Paving Of Parking Spaces In Embu Town (2018/2019). | Site preparation, construction, marking | To provide a durable and well-structured paved area that can accommodate increased vihicle capacity | Increased availability of organized and safe prking spaces | Urban development | Paving Of Parking Spaces In Embu Town (2018/2019). |  | Embu |  | Urban development | Urban development | Urban development | 2019-11-09 | 15/4/2019 | 2019-11-09 | N/A | 50000000 | 50000000 | 50000000 | County treasury | N/A | 50000000 | N/A | 50000000 | 100% | 49046132 | N/A | N/A | Ongoing | 98% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of Kangaru-Kairuri Road (Phase One)) And Upgrading Of Old B6 Junction (Ksg)-Kamiu (Part) Roadto Bitumen Standards | Reconstruction, installation of traffic signals and improvement of drainage systems | To Improve trasnportation infrastructure by enhancing the condition and capacity of the designated road and BJ junction | Improved road quality leading to smoother and safe travel | Urban development | Upgrading Of Kangaru-Kairuri Road (Phase One)) And Upgrading Of Old B6 Junction (Ksg)-Kamiu (Part) Roadto Bitumen Standards |  | k |  | Urban development | Urban development | Urban deveopment | 2020-08-08 | 26/2/2019 | 2020-08-08 | N/A | 60000000 | 60000000 | 60000000 | County treasury | N/A | 60000000 | N/A | 60000000 | 100% | 59390228 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Paving Of Parking Spaces In Embu Town Phase Two 2019/2020 | Site preparation, construction, marking | To provide a durable and well-structured paved area that can accommodate increased vihicle capacity | Increased availability of organized and safe prking spaces | Urban development | Paving Of Parking Spaces In Embu Town Phase Two 2019/2020 |  | Embu |  | Urban development | Urban development | Urban development | 2020-08-10 | 24/2/2020 | 2020-08-10 | N/A | 50000000 | 50000000 | 50000000 | County treasury | N/A | 50000000 | N/A | 50000000 | 100% | 49373578 | N/A | N/A | Ongoing | 99% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading Of B6 Rudisho-Mutunduri -Ngugi Wa Iria Road | Reconstruction, installation of traffic signals and improvement of drainage systems | To Improve trasnportation infrastructure | Improved road quality leading to smoother and safe travel | Urban development | Upgrading Of B6 Rudisho-Mutunduri -Ngugi Wa Iria Road |  | Mutunduri |  | Urban development | Urban development | Urban development | 2020-07-09 | 24/2/2020 | 2020-07-09 | N/A | 68000000 | 68000000 | 68000000 | County treasury | N/A | 68000000 | N/A | 68000000 | 100% | 68570660 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Upgrading To Bitumen Standards Of The First Bus Park, Embu -Runyenjes Stage. | Removal f damaged bitumen layers, improvement of drainage system and re-marking of parking bays | To rehabilitate and upgrade the existing bitumen surface to meet morden quality and durability standards | Enhanced durability and lifespan of the bus park pavement | Urban development | Upgrading To Bitumen Standards Of The First Bus Park, Embu -Runyenjes Stage. |  | Runyenjes |  | Urban development | Urban development | Urban development | 2023-01-12 | 2023-02-06 | 2023-01-12 | N/A | 43800866 | 43800866 | 43800866 | County treasury | N/A | 43800866 | N/A | 43800866 | 100% | 38202391 | N/A | N/A | Ongoing | 87% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Construction Of A Pedestrian Walkway Along Kubukubu Street In Embu Town (Phase 1). | Survey, construction, imstallation of street lights and landscaping | To provide a safe and continuous walkway which protects pedestrians from traffic hazards | Increased pedestrian safety and reduced accidents | Urban development | Construction Of A Pedestrian Walkway Along Kubukubu Street In Embu Town (Phase 1). |  | Embu |  | Urban development | Urban development | Urban development | 17/10/2023 | 29/8/2023 | 17/10/2023 | N/A | 4497900 | 4497900 | 4497900 | County treasury | N/A | 4497900 | N/A | 4497900 | 100% | 4497900 | N/A | N/A | Complete | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Façade In The Embu Bus Park | Repair, Painting and cladding, installation of morden lights and landscaping and cleaning | To enhance the aesthetic appeal of the Embu bus park | Increased sense of safety and comfort for the users | Urban development | Façade In The Embu Bus Park |  | Embu |  | Urban development | Urban development | Urban development | 2024-11-01 | 19/10/2023 | 2024-11-01 | N/A |  |  |  | County treasury | N/A |  | N/A | [12 empty] | N/A | N/A | N/A
Report prepared by:
Designation:
Signature:
Date:
Report approved by:
Designation:
Signature:
Date:

## Formula Sheet
GOK
Development Partner
GOK & Development Partner
Yes
No
Compete
Cancel
Defer
Completed
Ongoing
Stalled